## Sheet1
ID | MAP Meeting Date | Topic | Action | Owner | Due | Status | Comment | Action Completion date
202401 | 2024-07-30 | Metalyse update | Metalyse NRDL-Medicine team preparation. Action: RA and TA to provide a summary of the engagement activities (with CDE&Chp for RA, and with top KEE for TA) that have been completed, and planned future engagement initiatives, to ensure Metalyse NRDL listing in Jul 2025 after NDA approval | Gloria Sun | Mid Aug 2024 | Completed | Sep 2024:The Summary presented at asset team meeting discussion. | 2024-08-22
202402 | 2024-07-30 | TA INFL update | PRO for PF in China Action: Follow up on current status of PI communication and expert management | Grace Wang | 2024-08-01 | Completed | Sep 2024: PI confirmed. Will revisit the study proposal/timeline and progress at Oct CEC | 2024-09-20
202403 | 2024-07-30 | TA INFL update | Nerandomilast Publication Regularly check with global MA colleagues and provide updates regarding Asian subgroup publication authorship. | Grace Wang | 2024-08-01 | Completed | Sep 2024: Confirmed with global team and leading PI. | 2025-04-22
202404 | 2024-07-30 | TA INFL update | Medical team to follow up with the consensus development for Lung cancer combined ILD (led by Prof. Jinghong Dai from Nanjing Gulou and by Prof. Dai from China-Japan Friendship Hospital respectively) | Grace Wang | 2024-08-01 | Ongoing | Sep 2024: Holistic plan for ILD consensus and guidelines (including lung cancer combined ILD) will be kicked off in Sep 2024.
202405 | 2024-07-30 | TA oncology update | To confirm the impacts on CIO meeting format/overall presentation from collaboration with CTONG | Meiruo Liu | 2024-08-01 | Completed | Jul 2024: PMN: Based on team current evaluation, the situation is generally well managed with no significant deviations from previous CIOs | 2024-07-30
202406 | 2024-09-20 | Follow up action: Metalyse NRDL-Medicine team preparation | Ensure a thorough understanding of the NMPA internal review process to provide feedback to NHSA, and make concrete plan for engagement activities | Medicine team taskforce | Nov 2024 MAP | Completed | Boehringer successfully presented in ChPC panel meeting on Nov 22rd and the panel well understood the situation and Boehringer’s position. ChPC’s oral feedback: 1. Metalyse generic name should be unchanged as Tenecteplase 2. Recomlyse generic name should be Tenecteplase if NHSA consult them with appropriate narrative and questions. | 2024-11-22
202407 | 2024-09-20 | Follow up action: IPF local competitor intelligence | Update the intelligence on local competitors, focusing on two competitors in IPF who recently received positive ph2 data | Grace Wang | Nov 2024 MAP | Completed | Nov 2024: the intelligence report will be shared in ILD Data Generation WS | 2024-11-11
202408 | 2024-09-20 | TA CREA update | Iclepertin submission strategy 1. Confirm whether the version of MCCB used in TW for Ph3 has been officially validated. 2. Confirm the previous pooling strategy communicated with CDE, and assess if we have the flexibility to submit either data from China mainland or pooled data with Taiwan | Sarah Liang | 2024-10-01 | Completed | Nov 2024: Officially translated and certified by MAI (copyright owner) and comms multilingual Ltd in 2014, but not validated after confirmation with TW RA and MAI (usually the validation study is conducted by external experts) We referred to“中国/中国患者” w/o specify as China mainland or TCM in pre-IND. The allocation form with mentioning “China mainland” number was submitted in CTA as CDE request. "Great China" will be back-up strategy if mainland not showing consistency and TW ph3 data will be used for MCCB/VRFCAT validation in case CDE required during review | 2024-10-30
202409 | 2024-09-20 | TA CREA update | NR2B global acceleration - Local team to request CRO to evaluate recruitment number in China under the expedited timeline | Jiaqi Lu | 2024-10-01 | Completed | Nov 2024: Be realistically to target 10 pts by end of Dec 2024 as LPI, will try every effort to enroll more. | 2024-10-25
202410 | 2024-09-20 | TA CRM update | Vicadrostat+EMPA delay issue Raise the delay issue and the impact to global asst lead and global evidence lead for their assistance. | Vicadrostat+EMPA China evidence team | Nov 2024 MAP | Completed Ongoing | EASi-KIDNEY late SSU in China update: Reason of late SSU in China is an operation strategy by Oxford. Oxford initiates start-up in sequential way considering the country enrollment capacity, availability ,etc . ​ Oxford promised the target of 1,100 for China, and recruitment window will still be kept open until China gets the targeted number. ​ In case of lower recruitment than expected, China will evaluate some additional candidate sites to Oxford.​ | 2024-11-28
202411 | 2024-09-20 | TA INFL update | Catci in nCFB ph3 1. Gather the information on sub-I team of the leading PI candidate 2. Close collaboration between RA and CO is essential for this IND acceleration pilot | Grace Wang | 2024-10-01 | Completed Ongoing | Nov 2024: CatCi leading PI and sub-I has been fully engaged and motivated in the cooperation. The project is well on-track so far. ILD MSL team and CD&O are continuously exploring a systematic collaboration model which can enhance ICP-based KEE engagement and maximize MSLs' value in frontloading activities. | 2024-10-30
202412 | 2024-11-28 | EASi-HF Reduced trial leading PI selection | 1. Arrange a meeting for Dr. Zhang with leading PI and director of site GCP office 2. Involve Carol and TW team to follow up with global team on TW leading PI selection | Empa+vicadrostat evidence team | 2024-12-01 | Completed | 1.Exchange meeting with Zhongshan Hospital is scheduled on 10th Jan. 2.Alignment was reached by TW team and CPL regarding the leading PI selection, based on the proposal by TW team. | 4-Dec-2024 18-Dec-2024
202413 | 2024-11-28 | Zongertinib NDA timeline update | 1. MAP suggests raising the topics of waiving dataset translation to RDPAC from BDS working group or RA working group | Hongjie Deng and Kuncy Xia | 2025 | Completed | The topic was already raised at RDPAC RA core meeting， and currently not considered as an issue by other MNCs | 2025-01-14
|  |  | 2. Proactively seek CDE reviewers feedback on pre-NDA meeting request, especially on NDA rolling submission | Lijie Yu | 2024-12-01 | Completed | CDE agreed with the proposed NDA rolling submission plan | 2024-12-20
202414 | 2024-11-28 | TA CREA update | NR2B Nam MDD adjunct/mono CD&O to work with CRO to communicate with Beijing Huilongguan Hospital regarding not able to initiate the site due to global recruitment acceleration | Alex Zhang | 2024-12-01 | Completed | Team worked with external partner to communicate with the site PI & GCP officer as the same day of global decision making, they all understood the background of no site opening, also expected the future collaboration with BI for upcoming Ph3 studies in NR2B Nam asset. | 2024-11-29
202415 | 2024-11-28 | TA CRM update | Jardiance HFrEF & HFpEF ONI feasibility report delay: TA to collaborate with RA to assess the available data from the ONIS study for Jardiance license renew in 2026, and develop a HA communication strategy for CEC review | Julia Zhu | Next MAP | Completed | Risk assessment on license renewal has been reported to MAP and MBR. HA communication strategy and mitigation plan has been aligned by CRM CEC. | 2024-12-19
202416 | 2024-11-28 | TA CRM update | SYNCHRONIZE trials GI AE: Escalate the comments from China investigators regarding increased GI AE to global team through multiple channels, to obtain guidance from global team on how to respond to investigators | Survodutide Evidence team | Next MAP | Ongoing | 1. GMA provided slides as reference to summarize GI AE in key ph2 and ph3 trials involving GLP-1 based compounds. 2. Consulted with global trial team, it was determined the current SYNCHRONIZE GI AE data could not be shared with investigators due to the trial ongoing status. 3. Communication stratetgy and key messages were developed by local to guide CTM/CRA and msl team for response. 4. Local trial team should focus on data monitoring to ascertain whether the GI AE issue represents an implication of higher occurrence in Chinese subgroup or just perceptions from some individual sites. | 2024-12-16
202417 | 2024-11-28 | TA CRM update | EASi-KIDNEY China Delay issue Archive the slide deck provided by global team at MAP sharepoint on global commitment to ensuring China patients sample size despite with late site initiations | Julia Zhu | 2024-12-01 | Completed | Slides deck was archived in both CEC and MAP folder. | 2024-12-10
202418 | 2024-12-12 | Jardiance PAC studies status Update and health authority interaction plan | 1. Collect the information of LTF(2025-2029) for Empa HFrEF & HFpEF for team scenario evaluation. 2. Prepare a draft of official communication letter to CDE, introducing the current situation and challenges for Jardiance PAC study and seeking CDE’s opinion. Forward the draft to Dr. Zhang for review. 3. Kick off the preparation of formal health authority interaction with CDE, concurrently expecting feasibility report from PI in March 2025. | Jardiance evidence team | 2024-12-20 | Completed | 1. LTF was collected. 2. HA communication letter was finalized after internal and PI's review. 3. HA interaction slides deck and meeting request to be submitted before Chinese New Year Holiday. The communication objective for the requirement on extending final report to the next round of license renewal, along with the mitigation plan for submitting the interim period report within the upcoming license review timeframe has been aligned in CEC. | 2024-12-31
202419 | 2024-12-16 | Additional Compensation for Chinese Patients in Placebo Arm in SYNCHRONIZE Trials | 1. MAP agrees with team to submit the proposal for site EC review after the following revisions: 1.1 Emphasize that the compensation allowance will not impact the blinding setting 1.2 Modify the rationale of compensation amount 1.3 Revise the proposed ICF content, with the focus on: 1.3.1 Benefits of subjects participating SYNCHRONIZE trials 1.3.2 Awareness of the new AOM launch in China market 1.3.3 Subjects have the options to decide whether to stay in our trials 2. Prepare the allowance disposition plan, including the actions for any money not successfully delivered to subjects | Local team (Evidence lead, CD&O, BDS, QM, Legal and Compliance) under the governance lead of Julia | Next MAP | Completed | 1. ICF wording of compensation has been internally reviewed and finalized. ICF has been submitted to site EC for review. 2. The tracking log will be prepared to document the allowance disposition status. | 2025-01-02
202501 | 2025-01-14 | Reflecting 1m NDA Submission Gap (China vs. global 1st submission) in FOCUS system | MAP advised refining the proposal wording to “within 1m (30 days)” as the default timeline between global 1st NDA submission and China NDA submission in FoCUS system, for all projects without (yet) detailed NDA planning. | Yuting Li | 2025-01-01 | Completed | 1. Slides have been revised based on MAP advice, and shared with LRA for further communication with EMRA. 2. EMRA is coordinating with other global functions (e.g. sPM) with a decision expected in Mar 2025 | 2025-01-22
202502 | 2025-01-14 | TA INFL update | To follow up on the risk evaluation on the DS Stability during NDA review for the Nerandomilast IPF NDA. | Jun Lu | 2025 | Completed | Description: Intended commercial Neran DS process in submitted dossier package (B3) & QC Testing sample (B2) Potential risk: Deficiency letter (DL) (probability: high) and/or 2nd round QC Testing (probability: low)à Worst scenario may delay ~3m NDA approval Aligned mitigations: 1. Proactively Preparing for DL responses to maximize B3 approval chance: inclusion in global PARL; global preparation of documents for response to CDE request to demonstrate equivalence between B2/B3 (to be ready within 1~2 weeks upon receipt of verbally request or deficiency letter) 2. Preparation for potential 2nd round QC Testing: proactive shipment of US B3 DS & B3/C2 DP samples to China; possible acceleration of 2nd QC testing | 2025-03-18
202503 | 2025-03-04 | Leading PI Selection for Vicadrostat & Empagliflozin CVRR Trial(1378-0041) | 1. MAP suggested that team should initially reach out to Prof. Tang, to confirm his willingness to be the leading PI of this study, and operational feasibility for tight recruitment timeline. 2. Revisit trial SUU timeline and explore the opportunities for acceleration | Iris Huang, Angela Xiao& Lian Zheng | Next MAP | Completed | 1. Accompanied by the leadership team, the trial team visited the Prof. Yida Tang and the GCP office of Peking University Third Hospital on 11Mar. 2. Prof. Tang is willing to be the Leading PI of this study and is fully aware of the tight timeline. The GCP office is willing to give the green light and support the accelerated timeline. 3. Peking University Third Hospital will be added to HOPE project in order to accelerate the contract negotiation. 4, Prof. Tang brought up the topic of publication. Evidence lead will contact global team on this topic 5. Trial team is evaluating th efeasilibity of CO-PI process based on feedback from Prof. Tang's assistant which was obtained by CRA during SQV. 5. The submission strategy is no HA interaction which has been endorsed by CEC. The China timeline has been revisited. The planned first SIV date has been accelerated from 15Dec2025 to 30Oct2025. | 2025-03-18
202504 | 2025-03-19 | TA CREA Update and eAT Goal Setting Calibration | MAP suggested including the activities from Value and Access into the overall early asset team goal. | Meiruo Liu | 2025-03-01 | Completed | Slides deck was uploaded into MAP folder. | 2025-03-28
202505 | 2025-03-19 | TA CREA Update and eAT | For NR2B NAM, to confirm which global steering committee or advisory board. Prof. Gang Wang is participating for NR2B NAM asset. | Meiruo Liu | 2025-03-01 | Completed | PMN: Completed on Mar 21st . Prof. Wang is NR2B NAM asset level steering committee member. | 2025-03-21
202506 | 2025-03-19 | TA CREA Update and eAT Goal Setting Calibration | Type III HA meeting with CDE: Precision psychiatry approach to clinical development To evaluate other experts as potential invitees to the HA meeting, e.g. experts from Peking University sixth hospital, taking into account their impact and expertise in this specific field. | Meiruo Liu | 2025-03-01 | Completed | Prof. Zhen Wang from Shanghai Mental Health Center was proposed to be invited as the external expert in HAI considering his expertises on the three questions of precision psychiatry concept, drug development in impulsivity, and objective task-based measures. | 2025-04-01
202507 | 2025-03-19 | TA CREA Update and eAT Goal Setting Calibration | Local Asset team setup process Clarify with TCM HP TA regarding the process of local asset team setup | Meiruo Liu | 2025-03-01 | Completed | Aligned in Mar TALT that NR2B NAM local AT will be set up following RMMT and local HPLT guidance. | 2025-03-25
202508 | 2025-03-19 | TA Oncology Update and eAT Goal Setting Calibration | To follow up with Dr. Zhang on why global decided not to adopt Prof. Ying Cheng & Prof. Shun Lu’s advice and modify study design for Obrixtamig Daron-Lung 1&2 | Sally Chen | 2025-03-01 | Completed | PMN: Competed on Mar 20th | 2025-03-20
202509 | 2025-03-19 | TA INFL Update and eAT Goal Setting Calibration | Spesolimab NS To confirm the Spesolimab NS pivotal study results communication plan and share the data with local team accordingly | Helen Tao | 2025-04-01 | completed | TLR results were communicated to local AT on 14th May. | 2025-05-14
202510 | 2025-03-19 | TA INFL Update and eAT Goal Setting Calibration | Nerandomilst PPF To verify the planned NDA submission date for US and China respectively | Helen Tao | 2025-03-01 | Completed | US NDA submission date： May 5th and CN NDA submission date： Apr 30th | 2025-03-24
202511 | 2025-03-19 | TA INFL Update and eAT Goal Setting Calibration | PROFINA To communicate with study PI Prof. Xu regarding the current status of contract negotiation and seek his support. | Helen Tao | 2025-03-01 | Completed | PMN (March 25th, 2025) face to face interaction with Prof. Xu on current status of contract negotiation done on Mar 28tth | 2025-03-25
202512 | 2025-03-19 | Follow-up actions from last MAP | For Leading PI Selection for Vicadrostat & Empagliflozin CVRR Trial (1378-0041), to follow up with Prof. Tang regarding his recommendation of site PI for Peking University Third Hospital. Team needs to further evaluate. | Emma Xie | 2025-04-01 | Completed | Prof. Tang has nominated site PI Shaomin Chen (陈少敏), who is also the PI for EASi HF of this site. | 2025-04-11
202513 | 2025-03-19 | TA CRM Update and eAT Goal Setting Calibration | Metalyse ORIENTAL study To invite Dr. Zhang to the investigator meeting for the ORIENTAL study | Emma Xie | 2025-07-01 | Completed | Dr. Zhang's calendar has been booked, detailed invitation will be sent out after confirmation with PI. | 2025-05-07
202514 | 2025-04-23 | Tenecteplase before interhospital transfer for thrombectomy in patients with acute anterior circulation large vessel occlusion at 4.5 to 24 hours- TREASURE | MAP agrees with the study proposal, with the following suggestions. Study design 1. Include distribution of transferring time in the results analysis. 2. Work with statisticians to assess the study power reduction and the scenarios of interim analysis 3. Re-evaluate the drop-out rate, leveraging ORIGINAL study results 4.Confirm the feasibility of current total budget proposal with PI 5. Confirm with RA regarding the current regulation on leveraging IIS study results for registration. | Leo Bao | 2025-05-01 | Completed | 1.(1) In the existing survey, distribution of transferring time could not be analyzed due to lack of patient level data. (2) in this TREASURE study, it has been included. 2.Study power has been updated from 0.9 to 0.85. Interim analysis is not recommended from neither PI or BDS. 3.Drop out rate has been updated from 10% to 5%. (early discontinuation rate of 4.4% in the ORIGINAL). 4.Sample size has been reduced from 706 to 572. The study team has confirmed at least a 1:1 matching of funds from the hospital, and the current budget is feasible. 5.Confirmed with RA, these IIS cannot directly support the registration. | 2025-05-13
202515 | 2025-04-23 | Intra-arterial tenecteplase for acute primary medium vessel occlusion stroke (ANGEL-MeVO-TNK) | MAP agrees with the study proposal, with the following suggestions in study design. 1. Re-evaluate the drop-out rate, leveraging ORIGINAL study results 2. Assess the timing of interim analysis, ensuring a balance between the data amount for IA and the remaining study duration 3. Check the registry study database from Tiantan Hospital regarding the condition of patients with MevO treated with IAT, for a more accurate treatment effect proposal | Luoki Liu and Leo Bao | 2025-05-01 | Completed | 1.Drop-out rate maintain 5% (early discontinuation rate of 4.4% in ORIGINAL study). 2.Interim analysis is not recommended from neither PI or BDS. 3.Treatment effect keep as 13% based on PI’s clinical assumption (No available database from Tiantan Hospital to evaluate the efficacy of IA in Mevo. While the efficacy of IA with rtPA/TNK in anti-bridging in LVO and IA with Urokinase in M1/M2 occlusions could be referred.) | 2025-05-13
202516 | 2025-04-23 | Tenecteplase vs. Medical Management in 4.5-24h LVO-AIS with no access to EVT | MAP agrees with the study proposal, and recommended team to work with statisticians to 1. Re-evaluate the power of the study 2. Assess the scenarios and timing of interim analysis | Luoki Liu | 2025-05-01 | Completed | 1.Confirmed 80% is reasonable and common; 2..Interim analysis is not recommended from neither PI or BDS. | 2025-05-13
202516 | 2025-04-23 | ECR vs. IIS | MAP suggested the team to consult with Legal on the wording of “BI study invention” in the ECR contract. | Liqun Tian | 2025-05-01 | completed | Already provided feedback to the legal department, and they will discuss the modification of the Chinese translation internally with the intellectual property attorney. | 2025-05-13