## Slide 1: Follow up actions (Cross-TA topics)
Action owners
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Follow up actions from previous PEC (Mar. 2026)
Topic | Action | Owner | Due Day | Update | Completion (Y/N)
Sample size commitment to CDE | To review the previous sample size commitments and assess any potential risks. To evaluate the pre-IND package review process and update as needed. | TA and RA PPM to lead | Apr PEC | RA TAHs reviewed the previous TA pre-IND packages for any disclosure of unnecessary sample size allocation breakdown (Mainland/TW/HK). No additional cases identified. The current case was a single case, and review process was followed. Process strengthened: Add a note in the process document “China Sample Size Proposal for Joining Pivotal Studies (Registration Purpose)”: “Do not share unnecessary allocation details (esp. Mainland/TW/HK), which is internal execution-level alignment; default to Greater China total sample size for HA communication.” | Y
Communication on CFDI/CDE comments/questions | To report comments/questions from CFDI/CDE immediately once received and share the responses with related MLT. | RA | Apr PEC | RA function has embedded the agreed process into daily practice to immediately inform CFDI/CDE formal questions and circulate responses to the relevant MLT. | Y

## Slide 3
China Sample Size Proposal for Joining Pivotal Studies (Registration Purpose)
CD physicians will lead Local Project Team to evaluate and propose sample for registration purpose trial, as part of China integration plan.
Evaluation Items | Considerations | Responsible
Statistical Perspective | PMDA Method 1: primary choice, to allow 80% chance to meet consistency criteria PMDA Method 2: secondary choice Special considerations for multiple comparisons and multiple trial participation | Statistician
Regulatory Consideration | 15-20% of overall study population in general Sample size of successful precedents with similar indication | RA
Operation Feasibility | Benchmark data reference (Internal & External, Global & Local) Global strategic feasibility for reference, if applied Preliminary feasibility evaluation, eg. EE feedback Participation patient number of TW/HK and other East Asian countries, if available | ClinOps
Clinical Consideration | Target patient population and medical practice in China Rare disease in China or not Mega trial Sample size and data from early phase trials if China has joined Sample size of trials with similar indication | CD
Team proposal is a balance of the four aspects.
If certain requirement cannot be met, LPT need to assess the risk and mitigation plan, and incorporate into China integration proposal.
Do not share unnecessary allocation details (esp. Mainland/TW/HK), which is internal execution-level alignment; default to Greater China sample size information only for HA communication.
CO will lead OPU feasibility, final commitment to individual study should rely upon final OPU allocation. If any deviation to proposed sample size by OPU feasibility, China development plan re-assessment and mitigation may be considered, please consider to raise to PEC and/or core team.