## Slide 1: Portfolio Executive Committee (PEC) Review Meeting TA INFL
  Ying Chen, Bo Wang, Yayun Zhu, Lindsay Xu, Yuting Li | Apr. 23rd, 2026 | 20 min
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Part II: Pipeline Update

## Slide 3
TA INFL Portfolio Summary - Pipeline Project
FiH - PoC
Verducatib
BE
COPD
Nerandomilast
IPF
PPF
SSc
Myositis
Autotaxin inh.
IPF/PPF
Spesolimab
GPP
PG
cGAS inh.
SLE；SSc
IFN
Anti-TREM1
IBD (CD and UC)
STING inh. BI 3009947
SSC; IFN
Anti-IL11
IPF/PPF
Anti-CTGF
IPF/PPF
QPCTL inh.
IPF/PPFr
DcR3-Fc
IBD
PAPP-A inh.
fCD
15-PGDH inh.
IBD
Next wave
Ongoing/under planning
Post PoC
Under evaluation
Sustain
CS - FiH
Stop/Park
Launched
Termination of STING inh. BI 3009947 in IFN and SSc
The current front-runner compound program was terminated as the PK/PD data from SRD failed to meet the required target engagement, and unable to meet efficacy criteria.
A backup compound is under planning.
Notes: mann

## Slide 4: TA INFL Portfolio Summary - PMS Studies
All planned and ongoing studies remain on track.
1199- Ofev
1305- Nerandomilast

## Slide 5: Study Status
TA INFL Portfolio Summary - PMS Studies
1199- Ofev
1305- Nerandomilast
Notes: ECR
No alt text provided
pivotTable
No alt text provided
image
No alt text provided
textbox
No alt text provided
textbox
No alt text provided
card
No alt text provided
IIS
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
BI-ONISed
No alt text provided
BI-ONISnd
No alt text provided
EAP
No alt text provided
BI-Clinical trial
No alt text provided
image
No alt text provided

## Slide 6: Mature Product/PMS Overview – INFL(Neradomilast)
Product/Study | Indication | Study type (Study no.: FPI-LPO, CTR) | Current Status | Next Mile-stone | Key Updates | 
Nerandomilast PROFINA (Xiehe Hospital, Prof. XU Zuojun) | PPF | ECR (1305-0105: Oct2025-Jul2028, Dec2028) | FPI (23Sep 2025) | LPI (Jul 2026) | PFI: 23Sep 2025 Enrollment: 5 /600(actual / plan); site: 1/ 30 (initiated/ plan) The new CRO was on board, and the study timeline is under assessment. | 
Nerandomilast ILD EPI study in China (Zhongguancun Big Data, Prof. ZHOU Maigen) | ILD | ECR (1305-0111: May 2025- Aug 2025, Sep 2026) | Data analysis of part 1&2 (30Sep 2025) | Data analysis of part 3 (Jun 2026) | The Part3 is ongoing. | 
Nerandomilast Non-interventional study based on existing data: claims data of Beijing (Binhai ,Prof. YIN Peng) | IPF | ECR (Jun 2026- Jan 2027, Sep 2027) | PEC approval (Nov 2025) | Global approval (Mar 2026) | PEC endorsed on 17Nov 2025. Hybrid review was completed in 25Feb 2026, and the result is approved with comments. All reviews approved in Lectrona and waiting for GMA to complete the MM of global release in Lectrona. | 
Nerandomilast Exploring patients’ experiences with nerandomilast: a longitudinal qualitative research among IPF patients (Peking University Third Hospital, Prof. CHU Hongling) | IPF | ECR(TBD ) | TBD | TBD | Offline preparation and discussion on proposal before CEC Adhoc CEC 0413 | 
Epidemiology and Disease Burden of Systemic Sclerosis (SSc) ​in Beijing: A Study Based on the Beijing Claims Database （Peking University Third Hospital，Prof. ZHUO Lin） | SSc | ECR(TBD ) | TBD | TBD | Offline preparation and discussion on proposal before CEC Adhoc CEC 0413 | 
Nerandomilast (Serum Exosome Combined with Radiomics to Predict Early Progressive Pulmonary Fibrosis) （The first affiliated hospital of Guangzhou medical university，Prof. HAN Qian） | PPF | ECR (1305-0123) (Dec2025-Dec2027, Jun2028) | Amendment EC approval | LPI (Dec 2026) | FPI completed on 20 Oct 2025 Enrollment progress: 178(+24)/325(actual/plan), till 16 Mar 2026; | 
Multimodal for detection of early IPF (Shanghai Chest Hospital, Prof. LI Feng ) | IPF | IIS (1305-0161) (Jul2018-July2026,July2027) | Protocol approval (Apr 2026) | Contract (Nov 2026) | CEC approval on 1 Sep 2025 Global proposal approved on 3 Nov 2025 Proposal released on 24 Nov2025 Protocol approval on 12 Feb 2026 Contract awaiting the investigator's first-round feedback. | 
Nerandomilast Biomarker Changes in High-Risk IIM-ILD Patients Treated with Nera plus IS (Renji hospital, Prof. YE Shuang) | IIM-ILD | IIS (TBD) | Proposal submit (Feb2026) | Proposal release (May2026) | PEC approval on 20260209 Proposal submit on 0317 and was locally approved on 0318. Global proposal approve and release process. AMP applied in Mar by email from MA | 

## Slide 7: Mature Product/PMS Overview – INFL(OFEV)
Product/Study | Indication | Study type (Study no.: FPI-LPO, CTR) | Current Status | Next Mile-stone | Key Updates | 
Ofev (China IPF Registry Study (PORTRAY) (China-Japan friendship hospital, Prof.DAI Huaping) | IPF | IIS (1199-0302) (Jul2018-July2026,July2027) | Follow up | LPO (Jul 2026) | Follow-up visit report will be sent to BI at the early of Apr2026; CDC link：under negotiation between investigator and sponsor Publication for baseline data : Under revision as Prof. Dai‘s comments | 
Study on the Status Quo of Diagnosis and Treatment of IPF and Quality of Life in China Implementation Protocol (IPF SURVEY) (Peking University Third Hospital, Prof. CHU Hongling) | IPF | ECR (1199-0562; Sep2023-Oct2026) | Phase1 report (May2025) | Ph2 report (May2026) | Phase II enrollment completed on 0324. Total 251 visits(plan 245). Data analysis. | 

## Slide 8: Follow-up action
Product | Indication | Study no. | China Dev. Strat. | actions
Afatinib 40mg | SqCC | IIS (1200-0279) | China alone | Publication plan (ongoing) Budget summary （site template）with PI signature (done on 23Jan 2025)

## Slide 9: Mature Product Overview – INFL
Product/Study | Indication | Study type (Study no.: FPI-LPO, CTR) | Current Status | Next Mile-stone | Key Updates | 
Nerandomilast PROFINA Xiehe Hospital | PPF | ECR (1305-0105: Oct2025-Jul2028, Dec2028) | FPI (23Sep 2025) | LPI (Jul 2026) | PFI: 23Sep 2025 Enrollment: 5 /600(actual / plan); site: 1/ 30 (initiated/ plan) The new CRO was on board, and the study timeline is under assessment. | 
Nerandomilast ILD EPI study in China National CDC | ILD | ECR (1305-0111: May 2025- Aug 2025, Sep 2026) | Data analysis of part 1&2 (30Sep 2025) | Data analysis of part 3 (Jun 2026) | The Part3 is ongoing. | 
Nerandomilast Non-interventional study based on existing data: claims data of Beijing National CDC | IPF | ECR (Jun 2026- Jan 2027, Sep 2027) | PEC approval (Nov 2025) | Global approval (Mar 2026) | PEC endorsed on 17Nov 2025. Hybrid review was completed in 25Feb 2026, and the result is approved with comments. All reviews approved in Lectrona and waiting for GMA to complete the MM of global release in Lectrona. | 
Study on the Status Quo of Diagnosis and Treatment of IPF and Quality of Life in China Implementation Protocol (IPF SURVEY) (Peking University Third Hospital, Prof. Chu) | IPF | ECR (1199-0562; Sep2023-Oct2026) | Phase1 report (May2025) | Ph2 report (May2026) | Phase II enrollment completed on 0324. Total 251 visits(plan 245). Data analysis. | 
 |  | ECR(Nera定性调查研究) |  |  | Offline preparation and discussion on proposal before CEC Adhoc CEC 0413 | 
 |  | EPI study of SSc |  |  | Offline preparation and discussion on proposal before CEC Adhoc CEC 0413 | 
Nerandomilast (Serum Exosome Combined with Radiomics to Predict Early Progressive Pulmonary Fibrosis) （The first affiliated hospital of Guangzhou medical university，Prof. Han） | PPF | ECR (1305-0123) (Dec2025-Dec2027, Jun2028) | Amendment EC approval | LPI (Dec 2026) | FPI completed on 20 Oct 2025 Enrollment progress: 178(+24)/325(actual/plan), till 16 Mar 2026; | 

## Slide 10: Mature Product Overview – INFL
Product/Study | Indication | Study type (Study no.: FPI-LPO, CTR) | Current Status | Next Mile-stone | Key Updates | 
Ofev (China IPF Registry Study (PORTRAY) (China-Japan friendship hospital, Prof.Dai) | IPF | IIS (1199-0302) (Jul2018-July2026,July2027) | Follow up | LPO (Jul 2026) | Follow-up visit report will be sent to BI at the early of Apr2026; CDC link：under negotiation between investigator and sponsor Publication for baseline data : Under revision as Prof. Dai‘s comments | 
multimodal for detection of early IPF (Shanghai Chest Hospital, Prof. Li ) | IPF | IIS (1305-0161) (Jul2018-July2026,July2027) | Protocol approval (Apr 2026) | Contract (Nov 2026) | CEC approval on 1 Sep 2025 Global proposal approved on 3 Nov 2025 Proposal released on 24 Nov2025 Protocol approval on 12 Feb 2026 Contract awaiting the investigator's first-round feedback. | 
Nerandomilast Biomarker Changes in High-Risk IIM-ILD Patients Treated with Nera plus IS (Renji hospital, Prof. Ye) | IIM-ILD | IIS () | Proposal submit (Feb2026) | Proposal release (May2026) | PEC approval on 20260209 Proposal submit on 0317 and was locally approved on 0318. Global proposal approve and release process. AMP applied in Mar by email from MA | 

## Slide 11: Update Nerandomilast

## Slide 12: Overview: China Development Plan - Nerandomilast
Projects | Study ID | Current status | NDA approval (best case)
IPF | 1305-0024 Phase 1 CN PK study | Completed | /
 | 1305-0014 FIBRONEER-IPF, ph3, IPF | NDA approved | US: Oct 7, 2025 CN: Oct 21, 2025
 | 1305-0031 FIBRONEER-ON, ph3 OLE, IPF + PPF | Follow-up ongoing | /
PPF | 1305-0023 FIBRONEER-ILD, ph3, PPF | NDA approved | US: Dec 19, 2025 CN: Dec 9, 2025
 | 1305-0046 FIBRONEER-SARD, ph3b, SARD-ILD | Recruitment ongoing | /
 | 1305-0152 FIBRONEER-ACT, ph3b, non-IPF fibrosing ILD | CTA under preparation | /
chILD | 1305-0022 Ph3, chILD | CTA under review | US: Mar 2030 CN: Aug 2030
SSc | 1305-0052 Ph3, SSc | CTA submitted | US: Feb 2031 CN: Jul 2031
IIM | 1305-0146 Ph3, IIM | Pre-IND mtg request submitted | US: Mar 2031 CN: Aug 2031

## Slide 13: CCDS/China LPI update
Dispatch date | 18 February 2026
CCDS/CC IFU version | 0306-04
Urgency Level | URGENCY LEVEL 2
Rationale for the update | For the update in Dosage and in Interactions: Integration of results from drug-drug interaction studies 1305-0119 and 1305-0113 for concomitant use with strong or moderate CYP3A inducers. Additional edits to enhance accuracy and clarity*
Submission plan | US: sub in Mar 2026 and implemented in Sept 2026 EU: sub during MA review and implemented with MA approval CN: submission planned by end of Mar and approval around Aug 2026
* Add the subgroup result for primary endpoint in FIBRONEER-IPF.
* Change the description of exposure duration to observation time in [clinical trial] section.
* Clarification on non-clinical and PK study result.
The revised LPI proposal was submitted to CDE on March 31st, with acceptance notice on April 17th. Approval is anticipated by August 12th.

## Slide 14: Nerandomilast (PDE4b inhibitor): Idiopathic Pulmonary Fibrosis(IPF) and Progressive Pulmonary Fibrosis (PPF) Development Plan
Sep 26
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Ph3-1305.14
Ph3-
1305.14
FSS
Dec 2024
CN ML N=97
TW: N=22
China PK 1305.24
IPF N=1077
US NDA Sub
7 Feb 2025
US NDA appr.
7 Oct 2025
NDA review for IPF
NDA Sub
NDA Appr.
China
CTA Review + EC + HGRAC + 1st SIV (5.5 M)
Dec2022
CTA Sub
1st SIV
Jul2022
PF-ILD N=1078
Ph3-1305.23
CN PK
17Mar2023
SIV
CTA Review + EC + HGRAC (6M)
LPO
13 Jan 2023
CTR
CTA Sub
Aug 2024
Ph3-
1305.23
Allocated China ML N=155, TW: N=28
CTA Review + EC + HGRAC + 1st SIV (5.5 M)
CTA Sub
14Jul2023
Jan 2024
LSS: Last subject screening
LSLV: Last subject last visit
DBL: database lock
HAI: Healthy authority interaction
INN: International Nonproprietary Names
ChP: Chinese Pharmacopoeia Commission
BE: Bioequivalence
OLE: Open label extension
19 Feb 2025
We are here
Nov 8
DBL
5Jun 2023
US NDA Sub
5 May 2025
US NDA appr.
19 Dec 2025
NDA review for PPF
NDA Sub
Ph3 OLE-
1305.31
Ph3 OLE-
1305.31
Ph3 OLE
FSS
26Sep 2024
LSC
Jan 2027
CTA Review + EC + HGRAC + 1st SIV
1Nov2023
Sep 2023
FSS
26Sep 2024
LSC
Jan 2027
LSS
Last patient Primary
endpoint
Oct 2025
Dec 9 2025
Apr 30 2025
Last patient Primary
endpoint
NDA App
CDE Panel Meeting
12 Sep 2025
CDE Panel Meeting
12 Nov 2025
CTP 7.0 dispatched in Mar and considered as non-substantial change, will be reported by DSUR in May 2026
IMPD 4.0 dispatched on Apr 2, will be implemented in DSUR.

## Slide 15
Ongoing: Nerandomilast (PDE4b inhibitor): Systemic autoimmune rheumatic diseases-associated Interstitial Lung Diseases (SARD-ILD) Development Plan
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph3b-1305.46
Ph3b-1305.46
Recruitment window = 16 M
152 sites, N = 400
TDO: trial design outline
FSS: first subject screen
LSS: last subject screen
LPO: last patient out
We are here
CTA Sub
21 Aug 2024
Recruitment window ~16 M
17 sites, N=27
CTR
30 Dec 2027
CTA Review + EC + HGRAC + 1st SIV (6 M)
21 Aug 2024
CTA Sub
FSS
13 Sep 2025
LSS
15 Dec 2026
LPO
30 Jul 2027
CTA appr
22 Oct 2024
LSS
15 Dec 2026
LPO
30 Jul 2027
FSS
13 Sep 2025
11 Nov 2024
CTA appr
Recruitment is ongoing.

## Slide 16: China Level Report: recruitment
Trial Number: 1305-0046
BI Substance: BI 1015550
Mode of Action: PDE4b inhibitor
Therapeutic Area: INFL
Target population: 27 (China)
400 (Global)
Phase: IIIb
Cut-off date: 2026.04.15
Total Screened = 35 (China. +8) / 308 (Global)
Total Randomized = 19 (China, +4) / 161 (Global)
Total Screen failure = 14 (China) / 68 (Global)

## Slide 17
Ongoing: Nerandomilast (PDE4b inhibitor): non-IPF fibrosing ILD Development Plan
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph3b-1305.152
Ph3b-1305.152
180 sites, N = 466
TDO: trial design outline
FSS: first subject screen
LSS: last subject screen
LPO: last patient out
We are here
CTA Sub
15 May 2026
18 sites, N=49 (pre-liminary allocation)
CTA Sub
FSS
TBU
LPO
31Aug 2026
LPO
Dec 2028
FSS
CTA preparation is ongoing.
SQVs in 18 sites are ongoing.
22 May
2026
Dec 2028

## Slide 18
Onogoing: Nerandomilast (PDE4b inhibitor): Pediatric Fibrosing Interstitial Lung Diseases (chILD) Development Plan
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2
Ph3-1305.22 (include OLE)
N = 30
Main DBL
1 Jun 2029
15 Jun 2026
3 sites, N=2
Ph3-1305.22 (include OLE)
We are here
CTA sub.
15 Jan 2026
CTA appr.
Feb
2026
NDA sub.
22 Sep 2029
OLE
LPO
14 Apr 2031
Pre-IND sub.
12 Sep 2025
CTA sub.
CTA appr.
1Jun 2026
1st SIV
10 Aug
2026
FSS
LSS
23 Jun 2028
The China CTA was submitted on Mar 13, with approval expected by mid-June.
The China IM is scheduled for Jul 3 in Shanghai.
NDA appr.
20 Mar 2030
NDA sub.
22 Oct 2029
NDA appr. (best case)
20 Aug 2030
13 Mar 2026

## Slide 19: Ongoing: Nerandomilast (PDE4b inhibitor): Systemic Sclerosis (SSc) Development Plan
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph2b-1305.40
Ph3-
1305.52
12Apr
2030
Aug
2030
Feb
2031
China
SSc Ph3 (N=448)
Ph3-1305.52
9 Jun 2026
31Jan 2027
12 Mar 2026
SSc Ph3 (N=45)
Sep
2030
Jul
2031
We are here
15Apr 2028
13 Apr
2026
CONQUEST Trial, SSc-ILD, ph2b
12 Oct 2026
15 Aug 2025
21 Aug 2025
US IND open was achieved on Apr 10. Non-hold comments from FDA are anticipated in May, which may trigger CTP amendment. ODD was granted by FDA on Apr 9.
The China CTA was submitted on Apr 13, with acceptance notice received on Apr 17. Approval is expected by Jul 15.
Leading site GCP submission is completed on Apr 20 and currently under review.
IA
Key results
HAI
CTA sub.
FSS
DBL
NDA sub.
NDA appr.
HAI
CTA sub.
FSS
NDA sub.
NDA appr.
RoFD
18 Nov 2025

## Slide 20: Ongoing: Nerandomilast (PDE4b inhibitor): Idiopathic Inflammatory Myopathies (IIM) Development Plan
IIM Ph3 (n~270)
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph3-1305.146
Ph3-
1305.146
Sep 2030
Mar 2031
China
9 Jan
2026
We are here
Release of SoD
2 Jul 2025
HAI sub.
RoFD
27 Mar 2026
17 Jun 2026
CTA sub.
Sep 2026
FSS
NDA sub.
NDA Appr.
Mar/Apr 2030
DBL
IIM ph3
HAI sub.
Mid Jun
2026 (TBC)
CTA sub.
15 Jan
Oct 2030
Aug 2031
NDA sub.
NDA Appr.
Dec 2026
FSS
RoFD was released on Mar 27.
Final feedback from the FDA and EMA for HAI has been received, along with initial feedback from the PMDA. Updates for TDO/CTP are in progress, and the CTA is currently being prepared. China HAI is still under review.
SQVs in 21 sites are in progress.

## Slide 21: Summary of HAI feedbacks, risks and mitigation plan
Summary of HAI feedbacks | Current status | Key risks | Mitigation plan
FDA (written response): Insufficient evidence and a ph2 dose‑ranging POC study is strongly recommended. A broad IIM indication not supported and development should focus on specific disease subgroups (e.g., DM). Primary endpoint (TIS) validity and clinical meaningfulness must be justified per disease subgroups. EMA (written response): Rationale supports direct ph3 entry in IIM; design and dose selection are acceptable. TIS acceptable as primary endpoint despite remaining validation limitations. Exclusion of IBM/IMNM may affect the indication label. Supportive evidence is limited; MA remains uncertain. PMDA (preliminary feedback): An exploratory ph2 PoC study is recommended prior to ph3, but study initiation and Japan participation are not precluded. CDE (under review): Summaries of the feedback from FDA and EMA have been submitted. | RoFD of IIM ph3 program was released. TDO and CTP update are in progress. Ph3 CTA preparation is ongoing and submission will proceed as planned (Jun). | CTA approval: CDE may challenge the scientific justification for initiating a ph3 study directly. EC approval: EC may request the CDE’s feedback on HAI. If concerns are documented in the written response, site EC may also raise concerns or delay approval. | Closely follow with global team to ensure incorporation of key regulatory feedback from all HAs into the final CTA/EC packages. Collaborate with global team and strengthen the overall evidence package by proactively addressing identified data gaps, including clear justification of endpoints, target population, and supportive evidence strategy.

## Slide 22: Summary of HAI feedbacks from FDA/EMA/PMDA
 | FDA-written response | EMA-written response | PMDA-preliminary feedback
Summary of HAI feedback | We do not agree with your proposal for a general indication for IIM, and we strongly recommend that you base your development program on specific, clearly defined diseases (e.g., DM). You will need to justify the content validity of TIS and the clinical meaningfulness of observed differences for each of the different diseases you evaluate. The adequacy of your justification will be a review issue. Given the limitations of the available data from the small subgroup of IIM-ILD subjects from Study 1305-0023, it is highly uncertain how this information could reasonably serve as confirmatory evidence. The relevance of the proposed mouse bleomycin model to inflammatory myopathies is minimal. We reiterate that you currently have very limited clinical information to inform the preliminary efficacy and safety of nerandomilast for IIM and strongly recommend that you conduct a phase 2, dose-ranging, POC study or studies. Whether a single well-controlled trial, together with supportive data (e.g. from a well-designed, well-conducted POC study), will be sufficient will depend on review of the data and strength of the results. The sufficiency of a single study to support approval will depend on factors beyond only achieving small p-value. Such a determination would also depend on a lack of new safety signals in a treatment population that would require further characterization. | There is sufficient rationale to proceed directly to a pivotal Phase III clinical trial in IIM, based on a sufficient non‑clinical package, a supported mechanistic rationale, supportive PD signals observed in IIM‑ILD, and extensive safety experience in related fibrosing ILDs. Overall, the proposed study design seems acceptable. The exclusion of subgroups (IBM, IMNM) will likely have implications on the indication label. Certain limitations seem to remain regarding the validation status and interpretability of TIS. However, its use as the primary endpoint—supported by a responder analysis (TIS-40) and complementary analyses of the individual Core Set Measures—can be considered overall acceptable. Current dose selection is acceptable. The non-clinical efficacy data and data from a subgroup of IIM patients from the ILD trials are considered to provide only limited supportive evidence. Whether a single pivotal trial will provide sufficiently robust and compelling evidence to support MA will be a matter of assessment. | Mar 23, PMDA preliminary feedback: PMDA 's opinion is such that it is desirable to conduct an exploratory study in IIM patients to collect information that would support the selection of an appropriate target population and the determination of primary efficacy endpoints and then design and conduct a confirmatory study based on such findings. But PMDA does not preclude from initiation the study and join from Japan. Apr 1, Meeting outcome (internal interpretation) : PMDA does not object to the initiation of the 1305-0146 study, as there appears to be no significant safety concerns. PMDA considers the primary endpoint to be TIS with a cut off level (e.g. TIS-40, etc.), which has international consensus. There have been changes to the target population (inclusion, exclusion criteria) after providing PMDA’s pre-opinion, they could not be able to conclude their opinion for these changes.
Next step | TDO/CTP update and CTA submission will proceed. |  | 

## Slide 23: Update Verducatib

## Slide 24: Verducatib/BI 1291583 (DPP-1 inhibitor): Bronchiectasis
2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Phase 2
1397-0012
Airleaf Ph II 1397-0012
Aug 2022
PoCP
Jan 2023
LSS
Sep 2023
PoCC
Jun 2024
Dec 2024
RoFD
Clairafly 1397-0013 CF Profiling study
Nov 2023
Q4 2024
Phase 2
1397-0013
Clairleaf Phase 2 CFBE + nCFBE roll-over study
Q3 2023
Q3 2026
Phase 2
1397-0017
Phase 3
1397-0014
AIRTIVITY 1397-0014 Phase 3
1397-0018 Phase 3 nCFB+/- CFB roll-over study
CTA
Feb 2025
16 Jun 2025 FSS
20 Sep 2027, DBL1 (adults)
US NDA
Dec 2027
US Approval
Aug 2028
Phase 3
1397-0018
AIRTIVITY 1397-0014 Phase 3
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Feb 2025
Jul 2025
1st SIV
EoP2 HAI
Req. Subm.
Sep 2024
China Approval
Best: Dec 2028
Phase 3
1397-0014
Phase 1 PK
1397-0027
we are here
China PK
CTA Review + EC + HGRAC + 1st SIV (6m) *
Protocol develop
13 Jul 2026
Key PK results
Apr 2027
FSS
11 Oct 2026
LSO
1397-0018 Phase 3 nCFB+/- CFB roll-over study
Phase 3
1397-0018
CN NDA
Dec 2027
China Approval
Base: June 2029
Jan 31, 2028, DBL-2 (adolescents)
20 Sep 2027, DBL1 (adults)
Jan 31, 2028, DBL-2 (adolescents)
CTP v2
1755 (1680 adults + 75 adols)
1680 adults
1440 NCFBE
240 CFBE
75 adolescents
≥70% NCFBE
≤30%CFBE
CTP v3 – Mid Apr 2026
DBL Timing - Flexibility

## Slide 25: Global Recruitment (by Apr 20th, 2026)
Chart: Global Recruitment
| 45824 | 45854 | 45885 | 45916 | 45946 | 45977 | 46007 | 46038 | 46069 | 46097 | 46128 | 46158 | 46189 | 46219
Planned Screened | 9 | 20 | 36 | 139 | 294 | 479 | 670 | 866 | 1122 | 1442 | 1762 | 2082 | 2305 | 2305
Actual Screened | 9 | 22 | 52 | 146 | 329 | 531 | 843 | 1255 | 1633 | 2120 | 2243
Planned Randomized | 0 | 7 | 18 | 42 | 105 | 229 | 377 | 530 | 735 | 945 | 1145 | 1460 | 1680 | 1915
Actual Randomized | 0 | 8 | 18 | 43 | 128 | 251 | 459 | 704 | 998 | 1324 | 1558
Cut-off date: 20-Apr-2026
Total Screened = 2243
Patient in Screening= 407
Total Randomized = 1558
Total Screen failure = 335
Screen failure rate = 15%
TOP 3 screening
1 China, 323
2 Germany, 267
3 USA, 265
TOP 3 randomization
1 China, 242
2 Germany, 199
3 USA, 150
11 adolescent patients were screened, 2 were randomized
Notes: Global并未提供3-7月筛选和随机的具体计划，根据现有数据进行推测。

## Slide 26: Local Recruitment (by Apr 20th, 2026)
Chart: Recrutiment - Mainland- accelerated
| Jul 2025 | Aug 2025 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26
 | 0 | 4 | 16 | 32 | 105 | 135 | 180 | 200 | 230 | 260 | 268 | 268 | 268
Screening Total-a | 1 | 8 | 32 | 46 | 110 | 170 | 250 | 270 | 323 | 323
Enrollment Total-p | 0 | 0 | 4 | 12 | 37 | 60 | 87 | 112 | 137 | 162 | 187 | 200 | 201
Enrollment Total-a | 0 | 2 | 10 | 19 | 69 | 91 | 145 | 182 | 219 | 242
Cut-off date: 20-Apr-2026
Total Screened = 323
Patient in Screening= 15
Total Randomized = 242
Total Screen failure = 68
Screen failure rate = 21%

## Slide 27: Status Update: New Indication(s) Evaluation for Verducatib Ongoing
COPD:
Reactivation of the COPD program and RoFD were granted.
  HAI starting from June, China CTA in Sep 2026.
Request conditional approval for RoFD for TWO indications for asset maximization for verducatib.
BUEC Decision in Mar 26.
ANCA-AV:
RoFD not granted, but there are some follow ups to review and then BUEC will decide on the next steps.
Next Steps for China team:
HAI in June, CTA in Sep 2026
Leading PI & Steering committee member proposal by Q2 2026

## Slide 28: Update Spesolimab

## Slide 29: Overview: China Development Plan - Spesolimab
Projects | Study ID | Current status | Planned start of operational transfer*
GPP | 1368-0025 Effisayil ON, ph2, Open label extention study | Recruitment completed, treatment ongoing | Q1-2026
 | 1368-0120 Effisayil REP, ph3b/4, GPP flare retreatment | Recruitment completed, treatment ongoing | N/A, Completion to Final CTR: Feb 2027
PG | 1368-0140 Capsayil, Ph3, PG | Recruitment ongoing | N/A, Completion to All site closure: Jun 2028
NS | 1368-0104 Ph2/3, NS | Terminated | /
HS | 1368-0098 Ph2b/3, HS | Terminated | /
* Source: Spevigo licensing and transfer to Leo Pharma Playbook for Countries, Date: 30 September 2025
MAH: Marketing Authorization Holder
The sponsorship transfer applications (included in protocol amendment) :
1368-0025: 1) as CDE required, will be submitted in parallel with the MAH transfer, which is targeted for 23 April (several days delay and waiting for LEO update this week) , aiming to be approved by 31Jul and sponsorship transfer competed by 30Sep with HGRAC approval. 2) protocol & ICF amendment approved by leading site EC on 4Mar.
1368-0140: CDE approval obtained on 31Mar2026.

## Slide 30
2020 |  | 2021 |  | 2022 |  | 2023 |  | 2023 |  | 2024 |  | 2024 |  | 2025 |  | 2023 |  | 2026 |  | 2024 |  | 2027 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4
N=130
LSS
Feb 2023
LSC
Jan 2028
N=14
Sep 2020
1st SIV
Ph2 OLE-1368.25
Ph2 OLE-1368.25
LSS
Oct 2022
LSC
Dec 2027
Ph3b/4-1368.120
We are here
NDA App (US)
for GPP Flare Sep 2022
recruitment (N=40)
Oct 2023
FSS
LSS
Jun 2024
LSC
Nov 2026
China Mainland: N=5 TW: N=2
16Oct2023
1st SIV
LSS
Jun 2024
Ph3b/4-1368.120
NDA App for GPP Flare
CN ML: 13Dec2022
TW: 6Jan2023
EC + HGRAC + 1st SIV
Jun 2023
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
CN ML: China mainland
TW: Taiwan
LSC
Nov 2026
Spesolimab (Anti-IL36R): General Pustular Psoriasis (GPP)
1368-0025 OLE study:
Trial on track. Planned start of operational transfer in Q1 2026*
1368-0120 Flare retreatment study:
Trial on track. Completion to final CTR* in Feb 2027
* Source: Spevigo licensing and transfer to Leo Pharma Playbook for Countries, Date: 30 September 2025

## Slide 31: Spesolimab (Anti-IL36R): Pyoderma Gangrenosum (PG)
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1-Q4
CTA Jul2024
Pre-IND
Meeting request
Jan2024
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
CTA Jul 2024
Aug 2028
LSR-LSC
Apr 2027
LSR-LSC
Feb 2027
Jun 2028
FSS: 20Feb2025
Recruitment timeline extended for ~6 months in Apr 2026:
  Changed Last Subject Randomized to Apr 2027 from Oct 2026
      China mainland: changed to Feb 2027 from Aug 2026
  Changed DBL date to Sep 2028 from Feb 2028
FSS-LSR n=90, recruit. Window: ~26m,
FSS-LSR n=14, recruit. window: ~24m
1st SIV: 14Jan2025
1st SIV: 15Jan 2025
FSS: 4Feb2025
CTA Review + EC + HGRAC
We are here

## Slide 32: Spesolimab (Anti-IL36R): Pyoderma Gangrenosum (PG)
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1-Q4
CTA Jul2024
Pre-IND
Meeting request
Jan2024
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
CTA Jul 2024
Aug 2028
LSR-LSC
Apr 2027
LSR-LSC
Feb 2027
Jun 2028
FSS: 20Feb2025
FSS-LSR n=90, recruit. Window: ~26m,
FSS-LSR n=14, recruit. window: ~24m
1st SIV: 14Jan2025
1st SIV: 15Jan 2025
FSS: 4Feb2025
CTA Review + EC + HGRAC
We are here
Recruitment ongoing (as of 17April):
  Global: 142 (+11) patients screened, 54 randomized(+7), 87 screen failed, 2 in screening.
  China: 24(+1) patients screened, 6 randomized(+1), 17 screen failed, 1 in screening.
Activities to boost recruitment:
  On-site boosting visits: Ongoing – leading site visit 14April, CHN15_12March, CHN13_17April, CHN5_15April.
  Global One On One call set up for the sites had no screened patients: Ongoing – CHN12 on 27Jan. CHN16 9th Feb.
  Offline Recruitment vendor Jsure Onboarding since mid of March 2026.

## Slide 33: Global Recruitment Curve
Cut-off date: 2026.04.17
Total Screened : 142
Total Randomized: 54
Total Screen failure: 89
In screening : 5
Screen failure rate = 62.6%
Chart: 
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46260 | 46291 | 46321
Patients Enrolled/Randomized (Actual) | 0 | 2 | 4 | 7 | 10 | 14 | 18 | 23 | 24 | 28 | 31 | 36 | 40 | 47 | 54
Patients Enrolled/Randomized (orginial plan) | 3 | 7 | 12 | 17 | 22 | 28 | 32 | 39 | 44 | 48 | 52 | 55 | 57 | 63 | 69 | 75 | 83 | 86 | 87 | 88 | 90
Patient Screened(Actual) | 0 | 5 | 11 | 19 | 31 | 44 | 52 | 61 | 77 | 89 | 96 | 104 | 115 | 126 | 137 | 142
Patient Screened(Planned) | 7 | 14 | 20 | 29 | 37 | 47 | 52 | 62 | 70 | 79 | 87 | 96 | 105 | 117 | 128 | 140 | 151 | 155 | 158 | 159
Patients Enrolled/Randomized (updated plan)

## Slide 34: China recruitment Curve
Cut-off date: 2026.04.17
Total Screened : 24
Total Randomized: 6
Total Screen failure: 17
In screening : 1
Screen failure rate = 70.8%
Chart: 
| 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6
Patients Enrolled/Randomized (Revised plan 20250915) | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 14 | 14
Patient Screened(Actual) | 0 | 1 | 1 | 2 | 6 | 10 | 12 | 14 | 19 | 20 | 20 | 21 | 21 | 21 | 23 | 24
Patient Screened(Revised Planned 20250915) | 1 | 2 | 4 | 6 | 8 | 14 | 18 | 20 | 22 | 24 | 26 | 27 | 29 | 31 | 33 | 35 | 35
Patients Enrolled/Randomized (orginial plan)
Patient Screened(Planned)
Patients Enrolled/Randomized (updated plan)
Patients Enrolled/Randomized (Revised plan 20250722)
Patient Screened(Revised Planned 20250722)

## Slide 35: Challenges and actions for PG Ph III study enrollment
Recruitment Challenges
Actions
CDO
&CD
MSLs
2025 |  |  |  | 2026 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Last patient Randomization Aug2026(China)
Co-visit for SIVs
(by CTM and Local Physician)
Co-visit for sites
Weekly Newsletter delivery
MSL Training
CRA Workshop
Interim IM
Low patient willingness for clinical trials​
  Low awareness ​
  Potential patients with disease controlled with current treatments
  Placebo trial design : patients with high disease burden with high need for timely and effective treatments​​
Limited Recruitment Pool
  Rare disease
  Difficult for PG diagnosis – exclusive diagnosis
  Potential patients with stable disease ​(ulcer healed)
  Complex comorbidities and treatments of PG
Uncertain patient source: patients scattered in different departments (dermatology, rheumatology, gastroenterology, burns and traumatology)
Pre-screening for potential patients (by sites)
Advertisements (by Sites & subsidiary hospitals)
MSL Activities (site engagement and referral mapping)
HCP and Patient Trial Materials
Trial Awareness @ congresses (Derm, GI, Rheum, Wound Care)
Monthly meeting with CD&O to share medical insights
CFT
leverage by PAG support
Media Outreach
CRA refresh training
Investigator Exchange forum @ CHN7
Investigator Exchange forum per needs
Investigator Exchange forum @all sites
We are here
CRA Workshop
Offline Recruitment vendor
Global One on One call

## Slide 36: Update Early Pipeline

## Slide 37: Early Assets Overview
Asset | Indication | CN Approval (best case) | Status | Notes
BI 1819479 (ATXi) | IPF | TBD | Ph II trial(1462-0004) results available. | PoC criteria not met. Meetings with IUPC and IUEC for decision on the future of the project scheduled for May.
BI 3000202 (cGASi) | SLE and IFN | 2034 | Ph II trial (1509-0004) ongoing | See next slide.
BI 3032950 (anti-TREM1) | IBD (CD and UC) | TBD | Integration strategy to Ph2b endorsed | PoC criteria was not met at current dose. Clear target engagement and tissue-level pathway and disease biomarker modulation observed. Data suggests incomplete tissue target modulation in non-responders at current dose. A higher-dose study currently is proposed. PoC milestone moved from Mar IUEC to Apr IUEC.
BI 3810477 (Anti-CTGF) | IPF | 2035 | PhI MRD ongoing. Integration strategy to Ph2a under discussion. | China has been added to the potential allocated country list in draft TDO communication for trial 1530‑0005. Country feasibility to be completed by May 12th

## Slide 38: cGASi in SLE Ph2 (1509-0004) Global and China Timeline
2025
64 days
2028
381 days
293 days
Today
25 m N=405
21 m, 11 sites, N=25
Global
China
ul
Dec
May
Oct
Mar
1/13/2026 – 2/13/2026
(30WD CTA Pathway）
CTA submission-approval
4/20/26 - 6/25/28
LSS
4/20/2026
1st SIV
4/13/2026
Key Results
1/21/2029
FSS-LSS
Aug
Jan
1st SIV
4/13/2026
64 days
5/27/2025 - 8/29/2025
pre-IND submission-approval
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
6/25/2028
CTA获批后9周内启动项目（首例知情签署）
Global 1st SIV: China 1st site initiation on Apr 13th
Global 1st FSS: China 1st patient screen on Apr 20th, 3 weeks ahead of the commitment to HA (within 12 weeks to achieve FPI).
Investigator meeting planned on 16May in Xi’an.
Leading PI Prof. Li was invited to join global expert group. Global AB meetings planned in May and June.

## Slide 41: Ongoing: BI 1819479 (Autotaxin inhibitor): IPF/ PPF
2024 |  | 2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 | 
H1 | H2 | H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2 IPF (N=300)
LSR
FSS
Ph3 in IPF
Q4 2027
FSS: First subject Screen
LSC: Last Subject complete
LSR: Last subject randomization
US NDA
Q4 2031
US sub
Q4 2030
Aug 2024
FSS
LSC
PoC in IPF
Mar 2026
Ph2-
1462-0004
Ph2-
1462-0004
Ph3
May 2025
LSC
RoFD
Sep 2027
Ph3
CN NDA
Q4 2030
CN app
Q4 2031
We are here
Ph3 in PPF
FSS
LSC
Ph3 in IPF
Ph3 in PPF
Jan 2026
~3m
( N=24)
LSR
FSS
Sep 2024
Jan 2025
LSC
Jan 2026
CMC packages backloaded after PoC
Q2 2030
EoPII Meeting
Feb 2027
EoPII submission
Dec 2026
TLR in Mar indicated PoC was not achieved. PoC milestone moved from Mar IUEC to Apr IUEC.​

## Slide 42: BI 3000202 (cGASi): Program Overview
2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
2024
Today
Jun 10 - Jul 25
Mar 11 - Aug 4
Jul 15 - Nov 22
Sep 1
Oct 1
Jun 17
814.6 days
410.6 days
Aug 20 - Mar 17
885.4 days
1135.4 days
1169.4 days
May 16 - Nov 7
379.4 days
Jan 13 - Jun 27
495 days
Feb 17 - Jan 11
1394.6 days
Dec 15 - Apr 19
Jun 13
Mar 30
Oct 13
1179 days
318 days
Aug 23
Aug 24
Oct 1
Aug 4
Jun 2
Oct 11
761 days
May 24 - Apr 26
1118.6 days
Mar 14 - Jun 27
Jan 15
Apr 22
Apr 6
May 26
Mar 30
Dec 12 - Jun 20
Sep 16 - Dec 4
Sep 2
327 days
Sep 11 - Dec 14
535 days
Jan 9 - Jan 27
Mar 11
Aug 30
495 days
Jan 11 - Dec 4
May 16
Aug 20
Sep 24
Oct 2
Sep 23
Oct 1
Jan 26
SLE
SSc
IFN
Ph II(PoC study) SLE 32w+extension to 52w
Ph III pivotal trial SLE 52 treatment
Ph III pivotal trial SLE 52 treatment
RoFD
Ph III
Ph II-PoC study 24w
US approval
US approval
US approval
PoC in SLE and SSC
Based on ph II 32w data
RoFD
Ph III pivotal trial SSc 52 treatment
PoC in IFN
RoFD

## Slide 43: Overview of the Early Assets for China Integration -Studies to initiate by 2028
2026 |  |  |  | 2027 |  |  |  | 2028 |  |  | 
Jan | Apr | Jul | Oct | Jan | Apr | Jul | Oct | Jan | Apr | Jul | Oct
Trials with Integration to be further evaluated.
cGASi
Anti-CTGF
Apr 2026
IPF- gPh2b
Jan 2028
UC- gPh2b (1486-0030)
Jan 2028
IPF-gPh2b(1493-0010)
Nov 2026
SLE- gPh2 (1509-0004)
Nov 2027
Anti-TREM1
CD- gPh2b (1486-0029)
IPF-gPh2a
DcR3-Fc
Mar 2028
IBD- gPh2 (2007-0005))
IL-11
Nov 2027
To be updated

## Slide 44: Back-up

## Slide 45: SPEVIGO® (Spesolimab): - License out
Boehringer Ingelheim will grant global licensing rights for SPEVIGO® to LEO Pharma on 1 Oct 2025.
Boehringer Ingelheim and LEO Pharma will collaborate closely to ensure continuity in the ongoing clinical programs for GPP and PG during the transition period.

## Slide 50: China is the current Top 1 recruiter (cut-off date: Sep 15, 2025)
Chart: 1368-0140 Country Recruitment
| Argentina | Australia | Austria | Bdlgium | Brazil | Canada | China | Finland | France | Germany | Italy | Japan | Malaysia | Norway | Poland | Portugal | Spain | Sweden | Switzerland | Taiwan | United States
End of Treatment | 1 | 1
In Treatment | 4 | 1 | 1 | 4 | 1 | 2 | 2 | 1 | 2
Screen Failed | 2 | 1 | 3 | 1 | 9 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 9
Screened | 1 | 6 | 1 | 1 | 1 | 3
19 Screened
6 In screening
4 Randomized
9 Screen failed

## Slide 51: 1397-0014 Amendment for the inclusion of adolescents LCI
LCI (lung clearance index): 11 countries have the capabilities to perform the LCI (25 sites)
LCI/MBW is a procedure which is difficult to standardize and interpret.
CORC centralizes and trains sites to conduct LCI in a standardized manner but also does a central readout.
  CORC is based in UK and was already validated and contracted for the Lenitvirus program
  CORC has partners in the US and Australia which might depending on capabilities perform these services in Australisia and the US, however, these partners are not validated by BI and would require separate contracts
  Team is currently collating all relevant information from the sites for the discussions with CORC and aims to have a contract only with this institute
  Evidence Team agreed to go with the sites first who can be covered by the CORC institute and if need be these will be the only ones; however, trial team to look into further solutions in parallel

## Slide 52: 1397-0018 trial (OLE) design (tbd Airtivity-on) Long term safety and efficacy of BI 1291583 in patients with bronchiectasis
Verducatib 2.5mg
R
open label, uncontrolled trial for patients with bronchiectasis who completed AIRTIVITY or CLAIRLEAF
Primary endpoint
Occurence of TEAs
Secondary endpoint
Annualized rate of PEx (no adjudication)
Change from baseline in FEV1 and FVC
D1
w12
w26
w40
w52
Substudy
HRCT follow up for participants of the AIRTIVITY HRCT substudy 2 years after initial baseline CT in AIRTIVITY
Site visit every 6 months
In between 1 phone visit
Currently no further exploratoy efficacy endpoints planned – tbc by Value
AIRTIVITY 2.5mg
AIRTIVITY placebo

## Slide 53: Key assessments AIRTIVITY vs OLE trial comparison
Category | AIRTIVITY | OLE
Safety | Adverse events reporting incl. PEx review - PEx adjudication | Adverse events reporting incl. PEX review – no adjudication
 | Physcial exam, height, BW, Tanner stage | Physcial exam, height, BW, Tanner stage
 | Safety lab | Safety lab
PFT | PFT (LCI) | PFT (LCI)
PROs | PROs: BEST, Qol-B, CAAT, abbrev. SNOT-22, cough severity NRS (SGRQ at baseline) | x x
Biomarkers | Sputum: biomarkers, Murray sputum color chart, P.aeruginosa | x x
 | Blood biomarker samples | x
HRCT Sub study | Substudies: cough and sputum, HRCT | Substudies: follow up HRCT
PK | PK blood samples | x

## Slide 54: NDA Submission Strategy Snapshot
2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 |  | H2 | H1 | H2
AIRTIVITY 1397-0014 Phase 3
CTA
Feb 2025
16 Jun 2025 FSS
DBL-1
Sep 2027
US NDA
Dec 2027
US Approval
Aug 2028
AIRTIVITY 1397-0014 Phase 3
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Feb 2025
Jul 2025
1st SIV
EoP2 HAI
Req. Subm.
Sep 2024
China Approval
Best: Dec 2028
Phase 3 1397-0014
CN NDA
Dec 2027
China Approval
Base: June 2029
LPI (adults)
Ready to recruit adult pts
Ready to recruit adol. pts
LPI (adults)
LPI (adols.)
LPI (adols.)
CTP v1
1680 (only enroll adults)
1440 NCFBE
240 CFBE
CTP v2
1755 (1680 adults + 75 adols)
1680 adults
1440 NCFBE
240 CFBE
75 adolescents
≥70% NCFBE
≤30%CFBE
CTP v2
CTP v1
DBL-2
Mar/Apr 2028
NDA with Data from all adult pts & Data from partial of the planned adolescent pts
SNDA with data from all adolescent pts
LPI (adols.)
LPI (adols.)
Global challenge: to simultaneously complete adol. recruitment with adults recruitment
5 months recruitment window for adolescent pts. (critical path)

## Slide 55: BI 1291583/verducatib (CatC/DPP-1 inhibitor): Bronchiectasis
2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Phase 3
1397-0014
AIRTIVITY 1397-0014 Phase 3
1397-0018 Phase 3 nCFB+/- CFB roll-over study
CTA
Feb 2025
16 Jun 2025 FSS
19 Dec 2028, DBL
US NDA
Mar 2029
US Approval
Nov 2029
Phase 3
1397-0018
AIRTIVITY 1397-0014 Phase 3
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Feb 2025
Jul 2025
1st SIV
EoP2 HAI
Req. Subm.
Sep 2024
China Approval
Best: Mar2030
Base: Sep2030
Phase 3
1397-0014
we are here
1397-0018 Phase 3 nCFB+/- CFB roll-over study
Phase 3
1397-0018
Nov 17, 2025
AIRTIVITY 1397-0014 Phase 3
16 Jun 2025 FSS
20 Sep 2027, DBL
US NDA Sub.
Feb 2028
US Approval
Oct 2028
China NDA Sub.
Feb 2028
CN Approval (best case)
Feb 2029
CN Approval (base case)
Aug 2029
AIRTIVITY 1397-0014 Phase 3
20 Sep 2027, DBL
DBL: - 14.7 months
CN Approval: - 13 months
(best or base case)
Updated timeline
Initial timeline
CN NDA Approval | Best Case | Base Case
Initial timeline | Mar 2030 | Sep 2030
Updated timeline | Feb 2029 | Aug 2029
Notes: All adult subjects are expected to complete the trial by 2 August 2027.
All adolescent subjects are expected to complete the trial by April 2028.

## Slide 56: Verducatib – Approval timeline in focus countries (adults + adols) (not finalized for socialization)
 | 2027 |  |  |  | 2028 |  |  |  |  |  |  |  |  |  |  |  | 2029 |  |  |  |  |  |  |  |  |  |  | 
 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Best Submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Base Submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DBL, 20 Sep 2027​
US/EU NDA Subm
JP NDA Subm
CN NDA Subm
US approval & launch (best)
US/EU NDA Subm
JP NDA Subm
CN NDA Subm
US approval & launch (base)
JP approval (best)
JP approval (base)
CN approval & Lanuch (best)
CN approval & Launch (base)
US approval & launch (best)
JP approval (best)
JP approval (base)
CN approval & Launch (best)
CN approval & Launch (base)

## Slide 58: NDA scenario analysis
Scenarios | Pros | Cons | MItagation plan
Scenario #1 (Global Goal): Adolescent and adult recruitment completes simultaneously; and the labelled population includes 12 year and older patients with BE (no sNDA). | Simultaneous completion of recruitment, saving cost and budget; One DBL + One NDA + Broader Population (12y and older) (China) Priority review, NRDL premium pricing | NA | NA
Scenario #2: Adolescent recruitment completes much later than adult recruitment (DBL 1 for adults and DBL 2 for adols.); but the available adolescent data at DBL 1 is sufficient to support label inclusion of adols (no sNDA). | Same as above | Medium to high risk of sNDA, depending on the data totality; China HA may have objections as well | China contribution more adols. & CF patients. (see next slide)
Scenario #3: Adolescent recruitment completes much later than adult recruitment (DBL 1 for adults and DBL 2 for adols.); but the available adolescent data at DBL 1 is NOTsufficient to support label inclusion of adols (sNDA). | NA | (China)Chance for Priority review, NRDL premium pricing will be much lower | 

## Slide 59: Next step actions – mitagation plan To support global adolescent (and CF) recruitment
#1: Submit for EC/GCP Approval at Existing Sites
Currently, two sites were seleced and added for adols recruitment More sites from the exisitng site list that are capable of adols recruitment could be considered.
#2: Engage The Two Adols. Sites for Recruitment
Proactively communicate start of adols. Recruitment per country (globa and local IMs, CTM/CRA/CRC site communication) Line up of adol. Patients Regular f/u with sites on progress/challenges of adol recruitment
Others
To be updated

## Slide 60: In-Class Competitor landscape in NCFBE/ ‘One’ BE
BI 1291583
Launch US CN
Brensocatib
Launch US, EU/JP in NCFBE
Ph III data
Ph II data
Launch CN
Launch US, EU/JP
Ph III: AIRTIVITY® (‘One’ BE)
~4.5 years gap
Similar time of entry
Ph IIb/ III: outside China – tbd*
Ph III: China only
* Little knowledge about this program currently
2025
2026
2027
2028
2029
2030
2031
2024
~2 years gap
Ph II China
Ph II outside China – tbd*
Ph III China - timeline tbd
Licensed out
Aug 11, 2025
HSK31858
XH-S004
Ph III outside China – tbd*
LPLV 2027-04-28
Launch CN (tbd)
~1 year later？(TBD)
Licensed out
Nov 20, 2023
Ph II China
LPLV 2027-12
Ph III China - timeline tbd*
RSS0343
We are here
Launch CN (tbd)
~2 year later？(TBD)
15 sites in overlap
15 sites in overlap
12 sites in overlap
Notes: EU Feb
JP Apr
CN (end of) Jun

## Slide 61: Competitor landscape beyond DPP1 inhibitors in NCFBE/ ‘One’ BE
BI 1291583
Launch US, EU, JP, CN
Ph III: AIRTIVITY® (‘One’ BE)
Similar time of entry
* Little knowledge about this program currently
2025
2026
2027
2028
2029
2030
2031
2024
China Joining Global Ph II (NCFBE, n=363)
LPLV 2027-12
GSK3862995B
(aIL-33 mAb)
China Joining Global Ph III (tbd*)
Launch CN (tbd*)
China Joining Global Ph II (NCFBE, n=363)
Itepekimab
(aIL-33 mAb)
China Joining Global Ph II (NCFBE, n=312) (Enrolment completed)
LPLV 2026-02-02
China Joining Global Ph III (tbd*)
Launch CN (tbd*)
7 sites in overlap
8 sites in overlap
Local competitions for trial enrolment：
Two ph2 and 1 ph3 trials for other DPP1 inhibitors are ongoing
  10-15 overlapping sites with each competitor
Two aIL-33 mAb ph2 trials are ongoing
  7-8 overlapping sites with each competitor
Notes: EU Feb
JP Apr
CN (end of) Jun

## Slide 62
Overview of In-Class DPP1/CatC Inhibitor Competition
62
Coming ~4.5 years (globally) and ~2 year (China) later, having strong and differentiating* data at launch is key.
Several areas for differentiation are being explored and focused investment into evidence generation beyond Ph III is proposed to react flexibly to competitive positioning and market development
*Statements regarding differentiation or comparison to competitors are aspirational only; no superiority or comparative claims will be made upon approval due to lack of head-to-head data. All claims must be approved by HPRC.
 | BI 1291583 phase 2 data | HSK31858 (Florensocatib) phase 2 data
MoA | DPP1/CatC inhibitor | 
Formulation & RoA | Once daily oral tablet (2.5mg) | Once daily two oral tablets (2x20mg)
Description of MoA / pharma-cological effect | Reduces NSPs and with that neutrophilic inflammation in the lung | 
Population | BE ≥ 2 PEx in past year or 1 PEx + high symptom score | NCFBE (primary diagnosis of COPD/asthma was excluded) ≥ 2 PEx in past year (Haisco)
EP - reduction in PEx | Key 2° EP: 32.3% (47% for Asian sub-group, n=14) at 2.5mg | 1° EP: 46.8% (20 mg, n=74) and 60.1% (40mg, n=75)
EP - time to first pulmonary exacerbation | 1° EP: 34% risk reduction in events at 2.5 mg (n=53) (HR=0.66) (59% for Asian sub-group, n=14) | 2° EP: 57% and 67% reduction in events at 20 mg (n=74) and 40 (n=75) mg (HR=0.43 and 0.33)
 | Note: Non-head-to-head comparison & baseline demographics differ between BI and HSK HSK31858 data were only generated in Chinese population BI 129583 data in Asian sub-group was comparable with HSK31858 | 

## Slide 63: Local strategy to move forward… (draft)
Based on the expedited global recruitment timeline & increasing competition from external pipelines in China
Activities | Purpose | Lead Role
Cross-trial comparison: Key Eligibility Criteria Dive-in Key Study Process Dosing form (oral vs IV/SC) Prior efficacy & safety data MoA advantage Trial stage (ph2 vs ph3) | Identify differentiating advantages & benefits for patients | Medical/Clinical
Site/PI Engagement: Boost visit? City Meetings? Ab meeting | Engage trial participating PIs Leverage the connection of the PI with experts not participating AIRTIVITY trials for referral | CD&O
External Promotion: WeiXin/WeChat official platform National/Regional Congress/Conference | Increase exposure to external targeted experts/patients | MA

## Slide 64: BI 3000202 (cGAS inhi) in SLE (1509-0004, ph2) Timeline / Current status_7Jan2026
Milestones | Global |  | China |  | 
 | Planned date | Actual date | 30 CTA accelerate process | Original planned date | Actual date
TDO Final | 06-Oct-25 | 06-Oct-25 | / | / | /
Final Protocol | 17-Nov-25 | 18-Nov-25 | 17-Nov-25 | 17-Nov-25 | 18-Nov-25
First EC submission | 22-Dec-25 | 17-Dec-25 | 5-Jan-26 | 12-Jan-26 | 30-Dec-25
CTA submission | 22-Dec-25 | 17-Dec-25 | 19-Jan-26 | 22-Dec-25 | 
First EC approval | 04-Feb-26 |  | 6-Feb-26 | 28-Feb-26 | 
CTA approval | 11-Feb-26 |  | 6-Mar-26 | 31-Mar-26 | 
HGRAC submission | / | / | 16-Mar-26 | 15-Apr-26 | 
HGRAC approval | / | / | 23-Apr-26 | 25-May-26 | 
First SIV | 06-Apr-26 |  | 30-Apr-26 | 30-May-26 | 
First Subject Screened | 07-Apr-26 |  | 15-May-26 | 15-Jun-26 | 
First Subject Randomized | 12-May-26 |  | 15-Jun-26 | 15-Jul-26 | 
Last Subject Randomized | 25-Jun-28 |  | 25-Jun-28 | 25-Jun-28 | 
DBL | 15-Jul-29 |  | 15-Jul-29 | 15-Jul-29 | 

## Slide 65: Interaction to align with CDE on China participating in the Global Phase II trial of BI 3000202 in SLE – submitted on 27 May 2025
Clinical division | Clin-pharm division
July 25th 2025 Based on the briefing document, China join the global phase II MRCT is reasonable. | Aug 20th 2025 Agree with China join the global Phase II clinical trial.
When submit the CTA, please provide the rationale that no safety risk to increase exposure in Asian SLE patients. The final review decision shall prevail. | It is recommended that in the global Phase II clinical trial, enroll Chinese patients in low-dose (25mgBID) arm firstly and compare the PK, PD and safety data obtained from these Chinese patients with the entire population. If the above characteristics are basically consistent, then enroll Chinese patients in higher dose arms.
 Justify in the CTA that increased exposure poses no safety risk for Asian SLE patients. | Strategy to push back CDE‘s recommendation (submitted on 27 Aug） Alignment meeting on 26 Aug – global & local teams
N.A | CDE accepted with further comment on 29 Aug: Suggest to comprehensively consider the available data to ensure the safety of the subjects. When submit the CTA, please provide the detailed rationale that no safety risk to increase exposure in Asian SLE patients.
 |  Justify in the CTA that increased exposure poses no safety risk for Asian SLE patients.
Feedback from CDE regarding China integration in global phase II study - 1509.0004

## Slide 66: Leading PI endorsed by ad hoc PEC (9th Oct)
Potential investigator name** | Hospital/ department** | Academic experience, especially in clinical studies (weight 15%**) | Impact in Therapeutic Area (weight 20%**) | Leading PI feasibility (weight 30%**) | Leading site start up timeline feasibility (weight 35%**) | Total Grade | Finial proposal for leading PI selection (Y/N)
李梦涛 | 北京协和医院 | Prof Li focus on the treatment of SLE, sjogren syndrome, rheumatoid arthritis, spondyloarthritis, systemic vasculitis, scleroderma, dermatomyositis, connective tissue disease-related pulmonary hypertension and other rheumatoid immunopathy. 1. Clinical trial experience: China Leading PI and global SC member in 1305-0046 ph3b trial (SARD-ILD); China leading PI in Belimumab ph3 in CTD-ILD (GSK), and PIT565 ph1 (Novartis). Lead 3 China single center clinical studies​. Several sub-I experiences in global/local RCT (leading PI 曾小峰） ​ 2. <Recommendations for diagnosis and treatment of systemic lupus erythematosus 2025> author 3. Published 138 Sci-cited papers related to SLE Grade: 9/10 (13.5) | 第十二届中华医学会风湿病学分会委员会主任委员；北京医学会风湿病学分会主任委员；中国医师协会风湿免疫科医师分会副会长兼肺血管/间质病学组组长；亚太抗风湿病联盟（APLAR）系统性红斑狼疮研究组成员；亚太系统性红斑狼疮协作组（APLC）成员；中国系统性红斑狼疮研究协作组（CSTAR）、国家风湿病数据中心（CRDC）、中国风湿免疫病医联体联盟（CRCA）秘书长，国家皮肤与免疫疾病临床医学研究中心（NCRC-DID）办公室主任 Grade: 10/10 (20) | Leading PI of 1305-0046 (SARD-ILD,ph3) CTID: 5 leading I-III studies (2 SLE ph1 studies, collaborate with MNCs like Novartis and GSK, and other local biotechs.) The experience of leading PI is limited, especially for MRCT. Grade：6/10 (18) | Trial Set up: 2 weeks EC approval: 1-1.5 months HGRAC: 2 weeks to get signature Contract negotiation: MSA (renew is under negociation), 2 months to finalize (risk: publication and IP sharing) EC submission ahead of CTA approval; bi-weekly EC meeting; EC/CTA in parallel review Summary: 4-6 months for initiation meets the 6 months benchmark of BI ; Lading site for 1305-0014 & 1305-0023 & 1305-0031 (ILD, ph3)/1305-0046 (SARD-ILD, ph3)/1366-0031(SSc, ph2) study Risk: Potential publication per PI’s request and IP sharing. Grade: 9/10 (31.5%) | 81.25% | Y 1509-0004

## Slide 67: BI 3000202 (cGASi) in SLE (slide under preparation)
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  | 2033 |  | 2034 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2
Phase 2
1509-0004
Ph II 1509-0004
Apr 2026
Key results
Aug 2029
PoC
May 2029
Dec 2024
RoFD
Phase 3
1397-0014
Phase 3
Phase 3
CTA
Feb 2025
16 Jun 2025 FSS
Phase 3
1397-0018
AIRTIVITY 1397-0014 Phase 3
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Feb 2025
Jul 2025
1st SIV
EoP2 HAI
Req. Subm.
Sep 2024
China Approval
Best: Dec 2028
Phase 3
1397-0014
Phase 1 PK
1397-0027
we are here
China PK
CTA Review + EC + HGRAC + 1st SIV (6m) *
Protocol develop
13 Jul 2026
Key PK results
Apr 2027
FSS
11 Oct 2026
LSO
1397-0018 Phase 3 nCFB+/- CFB roll-over study
Phase 3
1397-0018
CN NDA
Dec 2027
China Approval
Base: June 2029
20 Sep 2027, DBL1 (adults)
Jan 31, 2028, DBL-2 (adolescents)
CTP v2
1755 (1680 adults + 75 adols)
1680 adults
1440 NCFBE
240 CFBE
75 adolescents
≥70% NCFBE
≤30%CFBE
CTP v3 – Mid Apr 2026
DBL Timing - Flexibility