## Slide 1: Portfolio Executive Committee (PEC) Review Meeting TA ONCOLOGY
  Oncology Team | 23-Apr-2026 | 20 mins
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Actions from last PEC meeting
Follow up actions | Owner | Due Date | Status update | Completed (Y/N)
Zongertinib-1L NSCLC: To evaluate the NDA approval timeline after the inspection feedback is transferred to CDE from CFDI and reviewed by CDE (expected around early April) . | Zongertinib LPT | Apr PEC | To be covered in the program update. | Y
Zongertinib-IIS: To reconfirm with China commercial team regarding the IMP supply (200 kits) for this study. | Sally Chen | Apr PEC | Confirmed – 200 kits for 2026. | Y
Zongertinib-RWE study: To document the communication with HAMA team regarding the different definitions of PFS & OS between RWE study and clinical study. | Yuhui Huang | Apr PEC | Informed the HAMA team of the different definitions at the meeting and emphasized them in the email sharing preliminary results of the RWE study. | Y

## Slide 3: Part I: Portfolio Update

## Slide 4
TA ONC Portfolio Summary - Pipeline Project
FiH - PoC
Zongertinib
2L NSCLC
1L NSCLC
Adjuvant NSCLC
Pan-Tumor HER2m
Pan-Tumor HER2+
3L+ BC
1L CRC
2L BC
2L GC
CD137/FAP
HNSCC
Obrixtamig
2L epNEC
1L epNEC
1L SCLC
Next wave
Ongoing/under planning
Post PoC
Under evaluation
KISIMA-02
Sustain
CS - FiH
Stop/Park
Non-CDN STING FR
1L sqNSCLC
B7-H6/CD3
CRC
KRASmulti degrader
CRC; NSCLC; PDAC
SIRPα NG
HNSCC
VSV-GP
PDAC; HNSCC; Melanoma
KRAS G12D inh.
CRC
VSV-GP-GSDME-IL12
TNBC
ODC-IL12
Melanoma
ALPG/CD3 TcE
Solid tumors
Anti-LAYN antibody
Solid tumors
BTN3A/CLDN6 gamma-delta TcE
OV; EC; TC; LC; GC
CDCP-1 ADC
NSCLC
HPK1 Degrader
RCC; NSCLC; HNSCC
LY6K-HLA/CD3
NSCLC; HNSCC
TAG72/CD3 ADC
GC; NSCLC; OC
YE IL2-IFNa
TNBC
YE-cGAS/RIG1
HNSCC; Melanoma
Launched
KRASmulti degrader:
Discontinuation of the Front Runner compound due to much more favorable tox profile in the Backup compound
Re-direct CMC investment and activity towards the backup compound
Notes: mannual

## Slide 5: 2026 ONC Key Milestone Overview
Termination
CS/PoC/RoFD
Go-Nogo IP/IA/FA/Key result/TLR
Pre-IND/CTA/SIV
BTD/NDA/Inspection
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
CTA Sub. for
CD137/Fap - NSCLC Ph1b
HAI for Zongertinib - Pantumor development (Q2)
Key results for Zongertinib 1L NSCLC Beamion LUNG-2
CTA Sub. for
STING -1L sqNSCLC Ph1b/2
HAI for Zongertinib –
2L post-marketing requirements (Q2)
HAI for Obrixtamig - 2L epNEC Dareon-5 after futility analysis (Q1/2)
BTD Sub. for Obrixtamig - 2L epNEC Dareon-5 after futility analysis (Q1/2)
CTA Sub. for
Zongertinib - BCGC CTP amend.
CTA Sub. for
Obrixtamig -1L epNEC Ph3
NDA approval - Zongertinib 1L NSCLC (Best)
1st SIV for Zongertinib - NSCLC Combo study
1st SIV for Obrixtamig - 1L epNEC Dareon-Nec-1
Key results for Zongertinib Beamion LUNG-1 cohort 9
FA for Obrixtamig - 2L epNEC Dareon-5
FA for CD137/Fap - NSCLC Ph1b
POC for CD137/Fap - HNSCC
Key result for STING -1L sqNSCLC Ph1a
PoCP for VSV-GP - PDAC
Pre-FiH IP
for KRAS G12D Ph1
POC for SIRPa antago.- HNSCC
IA for SIRPa antago.- HNSCC Ph1b
RoFD fo Zongertinib 2L GC
1st SIV for Zongertinib - Adjuvant NSCLC Beamion LUNG-3
Global milestones
China milestones
RoFD fo Zongertinib 1L CRC
Inspection for
Zongertinib 1L NSCLC NMPA *2.
CTA Sub. for
Obrixtamig -2L epNEC CTP amend.
We are here
FDA Approval for Zongertinib 1L NSCLC (2/26/2026)
1st SIV for Obrixtamig - 1L SCLC Dareon-Lung1

## Slide 6: Part II: Project Update

## Slide 7: Zongertinib (BI 1810631, HER2 TKI)
P1-Lung

## Slide 8: Zongertinib (HERNEXEOS®) – 1L NSCLC Development Plan_AA
AA: Accelerated approval; CNPV: Commissioner’s National Priority Voucher
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph Ia/b
1479-0001
Beamion LUNG-1
Ph Ia/b
1479-0001
Beamion LUNG-1
June 2026
NDA app
Aug 2025
BTD granted
Ph Ib cohort 2
N=74
May 2025
TLR
Feb 2026
Jul 2025
BTD sub.
30 Sep
2025
NDA sub.
NDA app.
LPI
Jun 2024
FPI
Sep 2025
Ph Ib cohort 2
N=18
May 2025
TLR
29 Oct 2025
NDA sub.
LPI
Jun 2024
FPI
Sep 2025
CFDI completed the GCP inspection assessment report and CDE registered the GCP inspection report on April 9, 2026
Response to CDE GCP related queries was submitted on April 20.
Aug 2025
Pre-NDA sub.
US approval on Feb 26, 2026
STRICTLY CONFIDENTIAL
We are here

## Slide 9: Key Milestones of Zongertinib 1L NSCLC NDA(with PR)
Rolling submission:
Exposure efficacy and safety report;
272 summary;
Pop PK report( only as request)
1479-0020 CTR
2025 |  |  |  | 2026 |  |  |  |  |  |  | 
Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
CDE Technical review（1st round review,130WD）
Nov-25 to May-26
GCP Inspection
Feb 2026 to Apr 2026
Sub:
29-Oct -25
We are here
Without DL-7m
Accept.
:31-Oct-25
NMPA approval*
* If CDE trigger deficiency letter, then approval may be in Aug 2026
Rolling submission:
Updated 12m efficacy and safety data
Updated CNPI based on CCDS0305-05
Rolling submission:
1st rolling submission : already submitted to CDE website and completed formal submission as approach of e-CTD.
2th rolling submission: already submitted to CDE website and wait for CDE agreement formal submission
GCP inspection:
CFDI completed the GCP inspection assessment report on April 8 with a conclusion of "passed, please CDE pay attention during review(通过，需审评重点关注)," CDE registered the GCP inspection report on April 9 .
Queries:
Until 13-Apr, received 4 queries from clinical reviewer, 4 verbal queries from Statistical Reviewer,4 queries from clinical pharmacology reviewer.

## Slide 10: Zongertinib (HERNEXEOS®) – 1L NSCLC Development Plan_ Full Approval
10
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph3
1479-0008
Beamion LUNG-2
Ph 3 N=416
Ph3, N=88
TLR
Nov 2026
FPI
Jan 2024
LPI
Jan 2026
Mar 2024
1st SIV
Mar 3 2027
sub.
Jul 2027
app.
Apr 2028
app.
PMA (Plan Meeting A) will take place during Apr 22 to 23, 2026.
Local needs (e.g. subgroup outputs, post-marketing requirements) will be discussed during PMA.
* 1L NDA based on 12-month review period
Ph3
1479-0008
Beamion LUNG-2
LPI
Jan 2026
TLR
Nov 2026
Apr 2 2027
sub.
We are here

## Slide 11: HER2 Non-TKD Mutant Population 2L NSCLC AA Post Marketing Requirement in China
Global Status
The pre-sNDA/Type B meeting package for zongertinib (Cohort 3/non-TKD) was submitted to the FDA on April 1, 2026.
This Type B Meeting was granted, by the FDA, as a teleconference for May 5, 2026.
Need to align within global brand team
Will keep China team posted
China Status
China local team prefer to re-open Cohort 3 and the local position has been discussed with global team
Briefing book for pre-IND meeting is under reviewing by global team and local CEC members. Will submit the meeting request after FDA feedback received (May/Jun, 2026).

## Slide 12: Zongertinib (HERNEXEOS®) – Adjunctive NSCLC Development Plan
12
2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
FPI
Nov 2025
Ph3, N=400
LPI
Nov 2029
Key results
Oct 2030
Feb
2031
NDA
sub.
Jun
2031
NDA
app.
Ph3, N=70
5 Jan 2026
CTA Review + EC + HGRAC + 1st SIV
Aug 2025
1st SIV
CTA Sub
Enrollment status 3 enrolled
Initiated site: 22 site
Mar
2031
NDA sub.
Jan
2032
NDA app.
Ph3
1479-0032
Beamion LUNG-3
Ph3
1479-0032
Beamion LUNG-3
LPI
Nov 2029
Key results
Oct 2030
We are here
Enrollment status : 4 pt enrolled globally

## Slide 13: Global Recruitment Status
Description | Count
Molecular screened | 16
Screened | 9
Screen-Failed | 1
Randomized | 4
Ongoing | 4
Long-term FU | -
Chart: Beamion LUNG-3 Global Recruitment Projections
| 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692 | 46722 | 46753 | 46784 | 46813 | 46844 | 46874 | 46905 | 46935 | 46966 | 46997 | 47027 | 47058 | 47088 | 47119 | 47150 | 47178 | 47209 | 47239 | 47270 | 47300 | 47331 | 47362 | 47392 | 47423
Recruitment - planned | 0.36 | 0 | 1 | 3 | 8.355 | 14.475 | 21.36 | 28.83 | 36.88 | 45.62 | 54.636 | 63.928 | 73.312 | 82.696 | 92.08 | 101.464 | 110.848 | 120.232 | 129.616 | 139 | 148.384 | 157.768 | 167.152 | 176.536 | 185.92 | 195.304 | 204.688 | 214.072 | 223.456 | 232.84 | 242.224 | 251.608 | 260.992 | 270.376 | 279.76 | 289.144 | 298.528 | 307.912 | 317.296 | 326.68 | 336.064 | 345.448 | 354.832 | 364.216 | 373.6 | 382.984 | 392.368 | 401.752
Recruitment - actual | 0 | 1 | 1 | 2 | 3

## Slide 14: 1479-0032 Zongertinib Beamion LUNG-3 on 22Apr2026 (China recruitment status)
Clinical Development and Operations
Months | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28 | Jan-29 | Feb-29 | Mar-29 | Apr-29 | May-29 | Jun-29 | Jun-29 | Jul-29 | Aug-29 | Sep-29 | Oct-29 | Nov-29
Pts randomized (actual) | 1 | 1 | 1 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pts randomized (plan) | 1 | 2 | 3 | 4 | 6 | 7 | 9 | 10 | 12 | 13 | 15 | 16 | 17 | 18 | 20 | 21 | 23 | 24 | 26 | 27 | 28 | 30 | 31 | 33 | 34 | 36 | 37 | 39 | 40 | 41 | 43 | 44 | 46 | 47 | 48 | 49 | 51 | 53 | 54 | 56 | 57 | 59 | 60 | 62 | 63 | 65 | 67 | 69 | 70
Pts screened (actual) | 1 | 1 | 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pts screened (planl) | 1 | 2 | 3 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94
Description | Global | China
Molecular screened | 16 | 3
Screened | 9 | 3
Screen-Failed | 1 | -
Randomized | 4 | 3
Ongoing | 4 | 3
Long-term FU | - | 
Chart: Patient Enrollment Status
| 46052 | 46081 | 46110 | 46139 | 46168 | 46197 | 46226 | 46255 | 46284 | 46313 | 46342 | 46371 | 46400 | 46429 | 46458 | 46487 | 46516 | 46545 | 46574 | 46603 | 46632 | 46661 | 46690 | 46719 | 46748 | 46777 | 46806 | 46835 | 46864 | 46893 | 46922 | 46951 | 46980 | 47009 | 47038 | 47067 | 47096 | 47125 | 47154 | 47183 | 47212 | 47241 | 47270 | 47299 | 47328 | 47357 | 47386 | 47415 | 47444
Patients Enrolled/Randomized (Actual) | 1 | 1 | 1 | 2
Patients Enrolled/Randomized (orginial plan) | 1 | 2 | 3 | 4 | 6 | 7 | 9 | 10 | 12 | 13 | 15 | 16 | 17 | 18 | 20 | 21 | 23 | 24 | 26 | 27 | 28 | 30 | 31 | 33 | 34 | 36 | 37 | 39 | 40 | 41 | 43 | 44 | 46 | 47 | 48 | 49 | 51 | 53 | 54 | 56 | 57 | 59 | 60 | 62 | 63 | 65 | 67 | 69 | 70
Patient Screened(Actual) | 1 | 1 | 1 | 3
Patient Screened(Planned) | 1 | 2 | 3 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 56 | 58 | 60 | 62 | 64 | 66 | 68 | 70 | 72 | 74 | 76 | 78 | 80 | 82 | 84 | 86 | 88 | 90 | 92 | 94

## Slide 15: Zongertinib (HERNEXEOS®) – 1L NSCLC Combo
*
15
2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
FPI
May 2026
Ph2, N=60
LPI
2028
Key results
Ph2, N=8
Jun 2026
CTA Review + EC + HGRAC + 1st SIV
Jan 2026 *
1st SIV
CTA Sub
Ph2
1479-0044
Beamion 44
LPI
Aug 2027
Further development plan
Aug 2027
2028
Key results
CTA approved on Mar 20, 2026, in ahead of schedule
HGRAC submission on 16Apr2026.
SIV expected in Jun 2026 (CoC of SoC not released yet.)
We are here
Ph2
1479-0044
Beamion 44

## Slide 16: Zongertinib (BI 1810631, HER2 TKI)
P2- Non-Lung

## Slide 17: General update
  New TPP(Early stage breast cancer) proposal : Early Stage Breast Cancer development plans, draft TPPs, prelimnary study designs are progressing , this new TPP proposal will submit to HPBUPC for endorsement in May​.
  1L CRC development : Beamion CRC-1 (1479-0050) TDO kicked off.
  2L BC strategy revision ongoing & alignment with Jazz​
  BCGC-01 amendment to be frontloaded (Cohort P : Zongertinib + Zanidatamab + Taxane , 2L mBC)

## Slide 18: Zongertinib (HERNEXEOS®) – Pan-tumor Development Plan (Accelerate Approval)
18
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2
1479-0009
Beamion Pan tumor-1
FPI
Oct 2024
Ph2, N=430
LPI
Key results
NDA sub HER2 amplified
and mutant cohorts
Aug 2028
NDA app. AA – HER2 amplified and mutant cohorts
CTPv4.0 was finalized and CTP v4 will be implemented after health authority’s approval.
Health authority interaction(CDE、PMDA, etc) of Beamion Pantumor-1 is ongoing.
Totally 18 subjects were enrolled; Totally 11 Chinese sites will be selected under CTP V4.
Health authority interaction was submitted to CDE on Apr-10, 2026, expect written feedback received by Jul-07, 2026.
Dec 2027
SIV
Oct 2024
Ph2, N=40
LPI
Sep 2027
Key results
NDA sub HER2 amplified
and mutant cohorts
Mar 2029
NDA app. AA – HER2 amplified and mutant cohorts
Dec 2027
CTA Review + EC + HGRAC + 1st SIV
May 2024
CTA Sub
Ph2
1479-0009
Beamion Pan tumor-1
We are here
Apr 2028
Sep 2027
May 2028

## Slide 19: Global Recruitment Status (as of 17-Apr-2026)
Clinical Development and Operations
Chart: 1479-0009 Global Recruitment Plan
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Plan Screened | 4 | 17 | 33 | 47 | 60 | 74 | 89 | 104 | 119 | 131 | 141 | 153 | 163 | 176 | 185 | 195 | 207 | 225 | 242 | 260
Actual Screened | 4 | 31 | 57 | 89 | 108 | 115 | 127 | 137 | 152 | 170 | 181 | 192 | 198 | 222 | 268 | 304 | 331 | 359 | 371
Planned Randomized | 0 | 5 | 15 | 26 | 36 | 48 | 60 | 71 | 85 | 97 | 107 | 116 | 126 | 136 | 146 | 153 | 163 | 174 | 187 | 200
Actual Randomized | 2 | 15 | 35 | 54 | 75 | 87 | 91 | 98 | 108 | 120 | 131 | 139 | 144 | 157 | 181 | 215 | 240 | 264 | 273

## Slide 20: China Recruitment Status (as of 17-Apr-2026)
Clinical Development and Operations
Chart: 1479-0009 China Recruitment Plan
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631
Plan Screened | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11 | 19 | 21 | 25 | 27 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 45 | 46 | 48 | 49 | 50 | 51 | 52 | 53 | 54
Actual Screened | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 7 | 8 | 8 | 10 | 11 | 11 | 19 | 19 | 22 | 23 | 23 | 23
Planned Randomized | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 15 | 16 | 17 | 18 | 19 | 21 | 23 | 25 | 27 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Actual Randomized | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 6 | 8 | 9 | 9 | 12 | 15 | 17 | 18 | 18 | 18

## Slide 21: Zongertinib (HERNEXEOS®) – Breast Cancer & Gastric Cancer (BC&GC)
21
2024 |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1
Ph Ib/2-
1479-0012
Beamion BCGC-1
FPI
July 2024
Ph1b/2, N=768
CTA Review + EC + HGRAC + 1st SIV
Jan 2024
CTA Sub
LPI
Apr 2028
Ph1b/2-
1479-0012
Beamion BCGC-1
NDA sub.
Jun 2029
NDA app.
BC 3L+ AA
2L BC strategy revision is ongoing with an new cohort (Zongertinib + Zanidatamab + Taxane)
Phase II recruitment (Cohorts D,E,F,I,J) opened.
Oct 2028
SIV
July 2024
Ph1b/2, N=72
LPI
Apr 2028
Key results
Jan 2030
NDA app.
BC 3L+ AA
Oct 2028
15 Chinese subjects were randomized.
CTA (CTP v5.0) was appoved by CDE on Apr 20, 2026.
We are here
Feb 2029
Key results
NDA sub.
Mar 2029

## Slide 22: Zongertinib (HERNEXEOS®)– Colorectal Cancer 1L
2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2029 |  | 2030 |  | 2031 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Phase 3
1479-0050
FPI
Apr 2027
Ph 3, Colorectal Cancer 1L
CTA Review + EC + HGRAC + 1st SIV
CTA Sub
NDA app.
CRC 1L FA
LPI
Jan 2031
NDA sub.
Jul 2031
Phase 3
1479-0050
SIV
2026 Q4
Pre-IND Submission
Sep 2026
Jun 2027
Ph 3, Colorectal Cancer 1L
May 2029
NDA app.
CRC 1L FA
LPI
Feb 2031
NDA sub.
Dec 2031
Beamion CRC-1 TDO was kicked off on Mar 26th, 2026.
Site feedback re HER2 testing : HER2 overexpression (IHC3+) was regularly performed, the middle pathway for patient screening will be feasible.
The feedback of Beamion CRC-1 synopsis was submitted to global team on Mar 20, 2026.
We are here
FDA interaction
May 2029

## Slide 23: Obrixtamig (BI 764532, DLL3/CD3 TcE)

## Slide 24: Obrixtamig (DLL3/CD3 TcE) – 2L epNEC (single arm study)
Jan 2028
NDA sub.
May 2027
NDA sub.
24
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2-
1438-0005
Dareon-5
Ph2, N=50
Ph2, N=5
Aug 2025
CTA Review + EC + HGRAC + 1st SIV
Feb 2025
1st SIV
CTA Sub
Ph2-
1438-0005
Dareon-5
SIV
Apr 2025
LPI
Jul 2026
Key results
Jan 2027
LPI
Jul 2026
Key results
Jan 2027
Feb 2028
NDA sub.
Futility analysis happened in Apr 2026. Key result will be shared in May 2026.
NDA timeline has shifted from May 2027 to Jan 2028. Part3 30 patients will be involved into primary analysis.
Detailed timeline will be shared in May.
On 7Apr 2026, CDE endorsed CTP amendment for adding part3 30 pts.
Team is waiting for global update on detail timeline and CTP.
HA interaction /BTD plan after interim futility analysis will be re-evaluated in early May according to the data.
Feb 2029
NDA app.
Jul 2028
NDA app.
Futility analysis
Futility analysis
H2 2026
HA interaction
We are here

## Slide 27: 1438-0005 DLL3/CD3 epNEC dated on 16Apr 2026 (Global recruitment status)
Chart: Patient Enrollment Status
| 45741 | 45772 | 45802 | 45833 | 45863 | 45894 | 45925 | 45955 | 45986 | 46016 | 46048 | 46079 | 46107 | 46138 | 46168 | 46199 | 46229 | 46260
Patients Enrolled (Actual) | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 11 | 13 | 15 | 20 | 27 | 30 | 33
Patients Enrolled (Planned) | 0 | 2 | 3 | 5 | 7 | 9 | 11 | 15 | 18 | 22 | 25 | 29 | 33 | 37 | 41 | 44 | 48 | 50
Patient Screened(Actual) | 0 | 0 | 1 | 2 | 12 | 22 | 50 | 77 | 108 | 143 | 162 | 214 | 237 | 243
Patient Screened(Planned) | 1 | 4 | 8 | 12 | 16 | 22 | 28 | 36 | 44 | 53 | 62 | 71 | 81 | 90 | 99 | 108 | 118 | 125
Patients Enrolled/Randomized (updated plan)
Clinical Development and Operations
Months | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26
Patients Enrolled (Planned) | 0 | 2 | 3 | 5 | 7 | 9 | 11 | 15 | 18 | 22 | 25 | 29 | 33 | 37 | 41 | 44 | 48 | 50
Patients Enrolled (Actual) | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 11 | 13 | 15 | 20 | 27 | 30 | 33 |  |  |  | 
Patient Screened(Planned) | 1 | 4 | 8 | 12 | 16 | 22 | 28 | 36 | 44 | 53 | 62 | 71 | 81 | 90 | 99 | 108 | 118 | 125
Patient Screened(Actual) | 0 | 0 | 1 | 2 | 12 | 22 | 50 | 77 | 108 | 143 | 162 | 214 | 237 | 243 |  |  |  | 
Cut-off date：16Apr 2026 Total Screened：243
Total Enrolled：33
Total Screen Failure：161
In Screening 01：47
In Screening 02： 2
Screen failure rate：82.99%
Total Screened Planned = 125
Total Randomized Planned = 50
Part 2

## Slide 28: 1438-0005 DLL3/CD3 epNEC dated on 16Apr 2026 (Asia recruitment status)
Chart: Asia Recruitment Status
| 46138
China Screen(Actual) | 13
China Recruitment(Actual) | 5
Japan Screen(Actual) | 40
Japan Recruitment(Actual) | 4
Korea Screen(Actual) | 5
Korea Recruitment(Actual) | 0
Asia Screen(Actual) | 58
Asia Recruitment(Actual) | 9
Clinical Development and Operations
Part 2
Asia Recruitment Plan:
CHN: 5 pts ( completed)
JPN: 6 pts
KOR: 4 pts
Asia Recruitment Status:
Cut-off date：16Apr 2026 Total Screened：58
Total Enrolled：5(CHN)+4(JPN)
Total Screen Failure：39
In Screening 01：10(JPN)
In Screening 02: 0
Screen failure rate：81.25%
Months | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26
China Screen(Actual) | 13 | 13 | 13 | 13 |  |  | 
China Recruitment(Actual) | 5 | 5 | 5 | 5 |  |  | 
Japan Screen(Actual) | 19 | 28 | 39 | 40 |  |  | 
Japan Recruitment(Actual) | 0 | 1 | 2 | 4 |  |  | 
Korea Screen(Actual) | 5 | 5 | 5 | 5 |  |  | 
Korea Recruitment(Actual) | 0 | 0 | 0 | 0 |  |  | 
Asia Screen(Actual) | 37 | 46 | 57 | 58 |  |  | 
Asia Recruitment(Actual) | 5 | 6 | 7 | 9 |  |  | 
China
Japan
Korea
Asia

## Slide 29: Obrixtamig (DLL3/CD3 TcE) – 1L SCLC (obrix+atezo+EP vs. atezo+EP)
29
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1
Ph3-
1438-0012
Dareon-Lung-1
SIV
Mar 2026
Ph3, N=670
Ph3, N=116 (Inc.TW20+HK2)
May 2026
CTA Review + EC + HGRAC + 1st SIV
1st SIV
Nov 2025
CTA Sub
LPI
Jun 2027
LPI
Jun 2027
Jan 2029
NDA sub.
May 2029
NDA app.
Feb 2029
NDA sub.
Japan screened first patient on 13Apr 2026.
First site(宁波大学附一) was initiated on 17Apr 2026. 上海胸科 was the second one initiated on 20Apr 2026. Up to date, 4 sites initiated.
Investigator meeting was scheduled on 25 Apr 2026 in Shanghai.
Dec 2029
NDA app.
Ph3-
1438-0012
Dareon-Lung-1
Aug 2025
PreIND Sub
Key results
Q4 2028
Key results
Q4 2028
15 Sep 2025
FDA interaction
We are here

## Slide 30: Obrixtamig (DLL3/CD3 TcE) – 1L epNEC (obrix+EP vs. EP)
Jan 2029
NDA sub.
30
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph3-
1438-0011
Dareon-Nec-1
SIV
Jun 2026
Ph3, N=390
Ph3, N=~60
Jul 2026
CTA Review + EC + HGRAC + 1st SIV
1st SIV
Jan 2026
CTA Sub
LPI
Jan 2028
LPI
Jan 2028
Global updated the trial timeline due to the recruitment rate increased.
NDA submission date shifted from Jun 2029 to Jan 2029.
We received CTA approval on 14Apr 2026. Only general comments left at CTN.
14 sites completed GCP submission, 6 sites completed EC submission and 3 EC approval obtained
IM meeting was planned in June. Details will be checked with Prof.Shen after Labor Day.
Jul 2029
NDA app.
Ph3-
1438-0011
Dareon-Nec-1
CTA preparation
Aug 2025
Kick-off
21 Nov 2025
FDA interaction
Key results
Sep 2028
Key results
Sep 2028
We are here
Feb 2029
NDA sub.
Dec 2029
NDA app.
Jun 2029
NDA sub.

## Slide 31: Obrixtamig (DLL3/CD3 TcE) – 1L/2L SCLC(obrix+BNT327+chemo)
31
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph Ib/II-
1438-0035
BOND
SIV
Jun 2026
Ph Ib/II, N≈60
Ph Ib/II, N=5
CTA Review + EC + HGRAC + 1st SIV
May 2026
CTA Sub
LPI
Sep 2027
Oct 2026
1st SIV
The contract between BioNtech and BI has been signed on 27 Mar.
Submitted US IND on 3 Apr 2026.
CTA will be submitted in mid-late May 2026, TBD by BioNtech.
Prof.Lu agreed to be national leading PI.
CTA Prep.
Jan 2026
Frontloading
preparation
20 Jan 2026
FDA interaction
We are here
Ph Ib/II-
1438-0035
BOND
LPI
Sep 2027
17 Mar 2026
CTP final

## Slide 32: Obrixtamig (DLL3/CD3 TcE) – 1L/2L SCLC(obrix+DLL3-ADC+chemo)
32
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph Ib/II-
1438-0036
Zorro
SIV
Sep 2026
Ph Ib/II, N≈60
Ph Ib/II, N=4
CTA Review + EC + HGRAC + 1st SIV
May 2026
CTA Sub
LPI
Dec 2027
Nov 2026
1st SIV
The contract between BI and ZaiLab has been signed in early Mar 2026.
Submitted US IND on 8Apr 2026.
CTA documents are under preparation and being reviewed by global team.
Target to submit CTA on 15May.
Prof.Lu agreed to be national leading PI.
CTA Prep.
Mar 2026
Kick-off
6 Apr 2026
CTA
We are here
Ph Ib/II-
1438-0036
Zorro
LPI
Dec 2027
24 Mar 2026
CTP final

## Slide 33: Brigimadlin (BI 907828, MDM2/p53)

## Slide 34: Brigimadlin (MDM2/p53 antago.) – Rollover study Development Plan
34
2024 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | … |  | 2034 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2-
1403-0032
Ph2
Ph2, N=2
Oct 2025
CTA Review + EC + HGRAC + 1st SIV
Apr 2025
1st SIV
CTA Sub
Ph2/3-
1403-0032
SIV
Dec 2024
LPC
Dec 2034
CTA was approved on 27 Aug 2025.
We are here

## Slide 35: Early Assets
CD137/FAP (BI 765179)
STING Agonist (BI 1703880)
LY6K-HLA/CD3 (BI 3822971)

## Slide 36: CD137/FAP (BI 765179)

## Slide 37
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | 
Ph1-1463.1b
HNSCC
CD137/FAP – HNSCC/NSCLC Development Plan
Global
China
Lean PoCP
(Jun 2024)
FPI
Mar 2025
Phase 1b N=60
Phase 1b N=7
Feb 2025
CTA Review + EC + HGRAC + 1st SIV
Aug 2024
1st SIV
CTA Sub
LPI
Jan 2026
Feb 2026
PoC
(Jul 2026)
Ph2/3
1L R/M HNSCC
Futility analysis
Aug 2025
Primary analysis
Ph1-1463.1b
NSCLC
Ph1b/2 1463-0002
in 1L NSCLC
Feb 2032
NDA FA
Ph1-1463.1b
HNSCC
Primary analysis is planned for PoC release in July 2026.
GO/No GO criteria is updated with ORR from 40% to 36% based on the ORR of Pembro+chemo in 1L HNSCC with CPS* ≥1
1L NSCLC development is under planning.
LPI
24Nov2025
Ph 3 pivotal (combi pembro) 1L R/M HNSCC
Ph 3 pivotal (combi pembro) for 1L NSCLC
7 Chinese patients were enrolled (1CR, 2 PRs, 2 SDs and 2PDs).
We are here
*CPS: Combined positive score

## Slide 38: CD137xFAP Clinical Development in 1L NSCLC PD-L1 positive
2024
Today
Jan 13 - Oct 23
May 11 - Aug 4
Jun 24 - Jul 21
Oct 5
Nov 24
Feb 9
Jul 11
Dec 19
Feb 19
Mar 17
Sep 2
 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033/2034
1L NSCLC TPS ≥ 50% 1L NSCLC TPS 1-49% |  |  |  |  |  |  |  | 
Seamless Ph II/III combo PD-1xVEGF BsAb
Stage 1: Safety run-in (N = 12-18)
Stage 2: Randomised Phase II (PFS)
Stage 3: Randomised Phase III (OS)
FA US
Ph III combo Pembro (PFS/OS) N = TBD
G
N
PA OS
IA PFS
PoC
Randomised Ph II combo Pembro vs Pembro (PFS) N = 145
Ph I triple combo Pembro + chemo
Safety run-in (RP2D) + dose expansion (ORR/DOR) N = 30
RoFD
G
N
GO
PFS HR <0.75
Ivonescimab mono: TPS ≥50%: ORR 60%; PFS: 11.1 mon. TPS 1-49%: ORR 43%; PFS: 8.0 mon. TPS ≥1%: ORR 50%; PFS: 11.1 mon. DoR: NR.
Ivonescimab+CT: TPS ≥1%: ORR 72%; PFS: 11.1 mon. DoR 12.5 m
Pembro mono: TPS ≥50% (KN-024): non-sq: ORR 46%, mPFS 7.7m. Sq: ORR 46%, mPFS 8.3m; TPS 1-49%: ORR 31%; PFS: 5.4 mon
Pembro+CT: TPS ≥50%: non-sq (KN-189)​ : ORR 62%, mPFS 11.3m ; Sq (KN-407)​ : ORR 64%, mPFS 8.3m.
TPS 1-49%: non-sq : ORR 50%, mPFS 9.4m ; Sq: ORR 54%, mPFS 8.2m. TPS ≥1%: mPFS 5.6m; ORR 37.3%; DOR 26.5m​
Other FAP+ tumors |  |  |  |  |  |  |  | 
Ph Ib/II combi SOC
G
N
Ph III Combi SOC
G
N
G
N
If Ivo is new SOC
FA US
Combo PD-1xVEGF Ab preclinical evidence
Ph II/III triple combo Pembro + chemo
Stage 1: Randomised Phase II (PFS)
Stage 2: Randomised Phase III (OS)
Notes: Benchmark in TPS ≥50%
Pembro mono : non-sq mOS 26.3m, mPFS 7.7.m, ORR 46%. Squamous: mOS 19.9m; mPFS 8.3m
Future benchmark: Ivonescimab (HARMONI-7, PCD: 4/2028). Approved in China (HARMONi-2) PFS 11.1m vs 5.8m, HR 0.51
Benchmark in TPS <50%:
Pembro + chemo: non-sq : mOS 19-22m ; mPFS 8-9m ; ORR 44-56%. squamous: mOS 18m; mPFS 8.2m
Future benchmark Ivonescimab+Chemo (global HARMONI-3, PCD: 4/2028). Approved in China (HARMONI-6 all comers, PFS 11.1m vs 6.9m HR 0.6) and in TPS ≥1%.
TPS ≥50%: mOS 26.3m; mPFS 7.7m; ORR 45%; DOR 29m (Keynote-024)​
TPS ≥1%: mOS 16.4m; mPFS 5.6m; ORR 37.3%; DOR 26.5m (Keynote-042)​
KN-042: Pembro mono in TPS >=50%: ORR 39%, mPFS 6.5 mo, mOS 20 mo
KN-407: Pembro chemo in TPS >=50%: ORR 60%, mPFS 8.3 mo, mOS 23.3 mo
KN-189: Pembro chemo in TPS >=50%: ORR 62%, mPFS 12.8 mo, mOS 29.6 mo

## Slide 39: Go NoGo Scenarios for initiation of a Ph. 2 study in 1L NSCLC based on ORR in 1L HNSCC
  No Go:
  <40% (<12 PRs of 30 pts) <36% (<11 PRs of 30 pts)
  Go:
  40 36-49% (12 11-14 PRs of 30 pts)  must justify resource investment
  Super Go:
  ≥50% (≥15 PRs of 30)  accelerate Ph2 in 1L NSCLC TPS high/Low
PoC:
ORR ≥36%
Planned July 2026

## Slide 40: 1L HNSCC CPS ≥1: SOC and future SOC
 | Population | ORR | PFS (mo) | OS (mo)
Pembro + chemo | CPS ≥1 | 36% | 4.9 | 13.6 vs 11
 | CPS ≥20 | 44% | 6 | 14.7 vs 11
Pembro mono | CPS ≥1 | 19% | 3.2 | 12.3
 | CPS ≥20 | 23.3% | 3.4 | 14.9
Potential future SOC:
Petosemtamab (anti EGFR/LGR5, Merus/Genmab) + Pembro: estim. launch date 01/27
combi with pembro in CPS ≥1 (mainly HPV-) 1L HNSCC pts in a Ph 1/2 trial (n=43) showed
cORR 63%
mPFS 9.0m
12-mOS rate 79%
PoC:
ORR ≥36%
Notes: Ficerafusp alfa (EGFR x TGFb, Bicara Ther.) + Pembro may launch in Q1 2028 for HPV- disease; Ph 1 trial data (n=28) ORR 54%, mPFS 9.9m and mOS 21.3m.
Amivantamab (EGFR x c-MET, Janssen) Ph1/2 data in 2L HNSCC (ORR 45% with DOR of 7.2m and mPFS 6.8m); a Ph 3 trial in combination with Pembro and carboplatin planned, estim. launch Q4/2029.
POC: 36% = 11 OR /30pts
Extreme regimen cetux/platin/5FU: ORR 36% PFS 5.1mo OS 10.7mo
LGR5, or Leucine-rich repeat-containing G-protein coupled receptor 5, is a transmembrane receptor that plays a significant role in regulating stem cell function and is a marker for adult stem cells in various tissues, particularly in the intestinal epithelium. It is involved in the Wnt signaling pathway, which is essential for maintaining stemness and controlling cell fate.

## Slide 41: Timelines for 1463-0002 Start-Up and FPI Milestones
BUPC
Resource Requests

## Slide 42: STING Agonist (BI 1703880)

## Slide 43: Systemic STING ago. FR – NSCLC Development Plan
43
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 20230 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2-
1480-0002
SIV
Nov 2026
Ph2, N=80
Ph2, N=12
Feb 2027
CTA Review + EC + HGRAC + 1st SIV
Aug 2026
1st SIV
CTA Sub
LPI
TBD
LPI
TBD
Ph2-
1480-0002
Final CTP: 27-May-26
CTA submission: Aug 2026 (30days pilot?)
We are here
Dose escalation is still ongoing.
The key priority is ensuring robust decision-making with available data in June.
Target remains July for submission of updated 1480.2 protocol.

## Slide 44: LY6K-HLA/CD3 (BI 3822971)

## Slide 45: LY6K-HLA/CD3 FiH Ph1 Timeline
45
2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Ph1 FiH
2015-0001
Ph 1a mono DE (N = 89 / 137, 12 sites)
FSS
Sep 2026  Nov
LPI
Oct 2029
We are here
Ph 1b mono expansion
FSS
Apr 2030
LPI
Sep 2031
CTA Sub
30Apr2026
FDA pre-IND WRO
06Mar 2026
sqNSCLC
N = 30 / 60
CTA Review + EC + HGRAC + 1st SIV
CTA Sub
SIV
Aug 2026
Pre-IND
Pre-IND Sub
May 2026
Feb 2027
Ph 1a mono DE (N = 89 / 137, 12 sites)
LPI
Oct 2029
Ph 1b mono expansion
FSS
Apr 2030
LPI
Sep 2031
PoC
Feb2032
Steering committee meeting on 24Apr2026
China assessment is completed.
Note: Pre-IND submission plan based on assumption that package is ready now.

## Slide 46
01
Regulatory and Legal feasibility
02
Clinical and Operational Feasibility
03
Patient Selection Feasibility
04
Biomarker and Sampling Handling
05
CMC and IMP Supply
06
CPS

## Slide 47: China Feasibility Assessment CMC - Summary
Potential Gap | Mitigation Actions | Criticality No / Low / Medium / Significant / High

## Slide 48: PMS & RWE Studies

## Slide 49: Study Status
TA ONCO Portfolio Summary - PMS Studies
1438- Obrixtamig
1479- Zongertinib
1200- Afatinib
Notes: ECR
No alt text provided
pivotTable
No alt text provided
image
No alt text provided
textbox
No alt text provided
textbox
No alt text provided
card
No alt text provided
IIS
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
BI-ONISed
No alt text provided
BI-ONISnd
No alt text provided
EAP
No alt text provided
BI-Clinical trial
No alt text provided
image
No alt text provided

## Slide 50: Mature Product/PMS Overview - ONCO
Product/Study | Indication | Study type (Study no.: FPI-LPO,CTR) | Current Status | Next Mile-stone | Key Updates | 
Zongertinib (Epidemiology and Real-world Treatment Patterns of Advanced NSCLC Patients with HER2 Mutation in China) PEK University, Prof. ZHAN Siyan | NSCLC | ECR(1479-0042) Dec2025-Apr 2026, Mar 2027 | Data collection ends （Mar 2026） | Data analysis （May 2026） | CEC endorsed in Dec 2024. Global released was completed on 24 Mar 2025.Kick off meeting was held on 24Apr. Protocol was approved in Aug. The contract was signed on 17Sep. Data collection started on 26Nov 2025. Data analysis is ongoing. | 
Zongertinib (The SEQUENTIAL-HER2 Study: A Prospective, Multicenter Study Evaluating First-line Zongertinib followed by ADCs in Patients with HER2 TKD-mutated Advanced NSCLC ) CTONG/Guangdong General Hospital, Prof. WU Yilong | NSCLC | IIS(1479-0079) Dec2026-May 2030, Oct 2030 | Global Release (25Mar 2026) | Protocol submitted to Lectrona （Apr 2026） | Got global release on 25Mar 2026. The contract template is under CTONG reviewing. The protocol is under development. | 
Obrixtamig (Epidemiology of Neuroendocrine Carcinomas (NECs) in China) PEK University, Prof. WANG shengfeng | NEC&SCLC | ECR（1438-0032） Jan 2026- Dec 2026, Oct 2027 or Mar 2026-May 2027, Mar 2028 | Data collection starts （26Jan 2026） | Data collection ends （Dec 2026） | Local CEC endorsed in Oct 2024. 1st round hybrid review was completed on 5Nov, and the final decision is "Eligible for Re-Submission. The kickoff meeting was held on 2Sep. The contract was signed on 21Sep. The protocol was approved on 6Nov 2025. Got EC approval letter on 25Nov 2025. Data collection started on 26Jan 2026. | 
Afatinib (Neoadjuvant afatinib therapy for resectable stage IIIA, IIIB-N2 EGFR mutation-positive lung adenocarcinoma) SHA Pulmonary hospital, Prof. Zhang Peng | Non-SqCC NSCLC Neoadjuvant | IIS (1200-0328): Jul.2020 - May.2022(stage 1), Apr.2026 (stage 2), Sep.2026 | Follow up (Apr 2026) | LPO (Apr 2026) | Enrollment completion on 9Feb2022 ,total 47 patients enrolled primary endpoint (stage 1) results has reached: Abstract has oral presented at 59th STS done in Jan 2023，Report accepted by Nature communications on 26July2023. DIM report submitted successfully in Aug2023 The investigator requested to extend study period from 30Sep 2025 to 30Sep 2026 and got CEC endorsement. Stage 2 follow-up is on track. | 
Afatinib (Neoadjuvant afatinib therapy for resectable stage IIIA, IIIB-N2 EGFR mutation-positive lung adenocarcinoma) Huashan hospital, Prof. Zhao Yao | Chordoma | IIS (1200-0329): Oct.2022 – Jan.2026, July2026 | LPO (30Jan 2026) | DBL (Apr 2026) | Clinical trail agreement fully signed, SIV:30Sep2022（sample size: 20) Actual recruit/ Planned recruit: 15/15 (by 31Jan 2025)​ FPI: 26Oct2022, LPI: 31Jan 2025 Follow-up was completed on 30Jan 2026 | 

## Slide 51
Thank You!