## Slide 1: Report for RDPAC CO Timeline Survey
CO Timeline Survey 2023
April, 2024

## Slide 2: AGENDA
1
Summary of RDPAC Survey
2
Benchmark of the Industry and Boehringer
3
Potential Hurdles of Startup and Closeout
Confidential for restricted internal use only

## Slide 3: Executive Summary
Confidential for restricted internal use only
Even continuous shorten, there is still the time lag between Global and China (20.9wks /4.9M vs 44wks /10.3M in 2023) from protocol finalization to related FPFV compared with last year (19.6wks /4.6M vs 46wks /10.7M in 2022)
In clinical operation stage, it takes 22.1wks /5.2M in 2023 from CTA-Approval (CTA-A) to FPFV (29.4wks/6.7M in 2022) and the overall initiation time of clinical trials in China continuously shorten
Both paralleled EC review and earlier contract negotiation saved about 6-7wks (1.4-1.6M) from CTA-A to FPFV
  Around 3wks saved that EC approval of 74% leading site is earlier than CTA-A in 2023 (-0.1wks in 2023 vs 2.6wks in 2022)
  Around 3wks saved that it takes 0.3wks in 2023 (3wks in 2022) from HGR approval to contract sign-off as contract negotiation is happened earlier than CTA-A with internal efforts
Below actions needs both internal and external efforts to improve the clinical trial efficiency
  Modified HGR administration including delinked with contract sign-off, more clear patent requirement, etc.
  Potentially, investigator products (IP) supply will be attended with custom clearance
  IP/Lab preparation and others can be considered with internal efforts to catch up global standards
Notes: 1.PF to FPFV
1.1In general, the China timeline from PF to FPFV is continuously shorten, from 10.7M in 2022 to 10.3M in 2023.
1.2.But compared with global, there is still room to improve, as this number is 4.9M for global, while 10.3M for China.
(1.3 backup data only, won’t share unless asked, for BI, from the collected trials that China joined, this comparison is 6.1M for global, 7.9M for China)
2.CTA to FPFV, it shortens from 6.7M to 5.2M in China industry.
3.Paralleled EC review and earlier contract negotiation shortens the timeline with 1.4-1.6M, which means the careful selection of leading sites is crucial for startup phase.
4.HGR, IP, lab and others are the potential areas that the industry can keep working on to improve the clinical trial efficiency.

## Slide 4: Sample profile
Totally, 199 samples of start-up trials are collected from 28 member companies.
The qualified samples include trials which China site’s FPFV happened from 1Jan 2023 until 31Dec 2023.
Tab.1 Start-up sample distribution |  |  | 
 |  |  | Number of CTs
Total |  |  | 199
---By Operation model |  |  | 
 | All in-house time(permanent HC) |  | 105
 | Full out-source to CRO and oversight by pharm |  | 36
 | Hybrid model |  | 58
---By TA |  |  | 
 | Oncology |  | 61
 | Non-oncology |  | 138
---By Trial Phase |  |  | 
 | Phase I |  | 37
 | Phase II |  | 38
 | Phase III |  | 123
 | Vaccine trial (Phase III) |  | 1
---By Trial type |  |  | 
 | China only registration study (LRT, local registration trial) |  | 49
 | Global trial + China Extension |  | 5
 | Global trial |  | 143
 | IMCT/ China dominated regional trial |  | 2
Confidential for restricted internal use only
Notes: Next a quick update on sample profile,
The executive summary just shared was derived from 199 samples of start-up trials collected from 28 companies.
With different operation models, Therapeutic areas, trial phases and trial types.

## Slide 5: Study Startup Timeline 2023 (median, weeks)
*Notes:
“HGR-A”: From HGR online submission to HGR approval
The numbers above are median, so an overall value might be unequal to the sum of its parts, because parameter value distribution is different from stage to stage.
Preparation
protocol finalization
CTA submission
CTA
approval
leading site
EC Approval
1st site contract
sign off
leading site HGR approval
1st site FPFV
CTA-A
From CTA-A to FPFV
12.1wks
22.1wks
5.2M
EC-A
HGR
Contract
sign off
FPFV
GCP filing +
leading EC review
1.4+5.4 wks
HGR-A*
8.3wks
Contract sign off
10.7wks
1st site activation
Site
activation
IP ready in China depot
14.7wks
1st site activation
IP
IP
ready
7.1 wks
-0.1 wks
11.0wks
0.3 wks
2.1
wks
1.3
wks
17.4wks
Confidential for restricted internal use only
6.0 wks
35.0 wks
Notes: Now we can take a closer look at the industry median startup timelines
1.Let’s start by reviewing the general timeline from CTA submission to FPFV, this takes around 8 months
2.Then if we change the starting point to CTA approval, to achieve 1st site activation, it takes around 3 months, and 5 months for FPFV

## Slide 6: Benchmark with Boehringer China
Chart: CTA-A to 1ST activated site FPFV
Month
Chart: CTA-A to 1ST activated site FPFV
| Industry Median
Month | 5.1567
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25%
Month | 5.1567 | 3.43
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median
Month | 5.1567 | 3.43 | 3.3
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25%
Month | 5.1567 | 3.43 | 3.3 | 2.3
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25% | Boehringer China Best
Month | 5.1567 | 3.43 | 3.3 | 2.3 | 1.7

## Slide 7: Benchmark with Boehringer China
Chart: CTA-A to 1ST activated site FPFV
Month
Chart: CTA-A to 1ST activated site FPFV
| Industry Median
Month | 5.1567
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25%
Month | 5.1567 | 3.43
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median
Month | 5.1567 | 3.43 | 3.3
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25%
Month | 5.1567 | 3.43 | 3.3 | 2.3
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25% | Boehringer China Best
Month | 5.1567 | 3.43 | 3.3 | 2.3 | 1.7
Chart: CTA-A to 75% Site Activation
| Industry Median
Month | 7
Chart: CTA-A to 75% Site Activation
| Industry Median | Industry 25%
Month | 7 | 5.3667
Chart: CTA-A to 75% Site Activation
| Industry Median | Industry 25% | Boehringer China Median
Month | 7 | 5.3667 | 4.4
Chart: CTA-A to 75% Site Activation
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25%
Month | 7 | 5.3667 | 4.4 | 3.6
Chart: CTA-A to 75% Site Activation
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25% | Boehringer China Best
Month | 7 | 5.3667 | 4.4 | 3.6 | 2.8

## Slide 8: Benchmark with Boehringer China
Chart: CTA-A to 1ST activated site FPFV
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25% | Boehringer China Best
Month | 5.1567 | 3.43 | 3.3 | 2.3 | 1.7
Chart: CTA-A to 75% Site Activation
| Industry Median | Industry 25% | Boehringer China Median | Boehringer China 25% | Boehringer China Best
Month | 7 | 5.3667 | 4.4 | 3.6 | 2.8
Boehringer China Median
CTA-A to
100% sites activation
4.9

## Slide 9
Last hurdles just before China FPFV
For example:
Expiration date of IP,
Production capacity,
Too many types of IP
Chart: 
| IP Supply (batch for FPFV) | Kits/Lab Supply | Limited patient pool | The status for process/system setting up | 遗传办/审批法规政策变化 | E-pro设备汉化/清关/供应/运输等问题 | COVID-19 pandemic | 无受制因素 | Others | No answers due to information availability
SQ31选项 | 0.27638 | 0.1206 | 0.070352 | 0.065327 | 0.060302 | 0.055276 | 0.045226 | 0.035176 | 0.1608 | 0.18593
IP Supply (batch for FPFV)
Kits/Lab Supply
Limited patient pool
The status for process/system setting up
HGR regulatory changes
E-pro Chinesization/customs clearance/delivery
COVID-19 pandemic
No last hurdle
Others
No answers due to information availability
Including Lab setup
Confidential for restricted internal use only
Notes: Lastly we would like to share the survey results of some hurdles, both in startup phase and closeout phase.
The top 3 are …

## Slide 10: 3rd party QC for site close-out
Chart: Is 3rd party QC required for site close-out? (based on CTs)
| Yes | No
CQ13有多少家要求做第三方质控 | 0.46875 | 0.53125
Base=64
Chart: Is 3rd party QC required for site close-out ? (based on sites)
| Yes | No
CQ13之和/CQ5.2之和,手动算 | 0.1424 | 0.8576
Base=1250
Chart: Whether any DBL delay or Database lock broken occurred after 3rd party QC ?
| Yes | No
Q14 | 0 | 1
Base=30
Yes
Number of sites surveyed : Total=1250 Mean=19.5
 | Number of sites
DBL delay after 3rd party QC | 0
DBL broken occurred after 3rd party QC | 0
Confidential for restricted internal use only
Notes: This is my last slide, there are still quite a number of sites requiring 3rd party QC before DBL but there is no delay caused by this.

## Slide 11: THANK YOU!