## Slide 1: Portfolio Executive Committee (PEC) Review Meeting Portfolio Overview Update - CREA
  Sarah Liang, Jiaqi Lu | 25th Apr, 2024 | 15 min

## Slide 2: Ongoing: Iclepertin GlyT1 — Cognitive Impairment associated with Schizophrenia (CIAS)
Ph3-
1346.11, 12, 13
Nov‘24
Mar’24
2021 |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 | 2027 | 2028 | 2029 | 2030
H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 
Ph3-
1346.14
FPI
Open-label safety extension; treatment duration 12m
FPI
Feb’25
LPO
LPI
Feb‘26
CONNEX-2 (N=586)
CONNEX-1 (N=586)
Ph3-
1346.11
CTA + EC + HGRAC + SIV
05Jul
CTA-s
1st SIV
Recruitment window: 29m; N=96
China
Ph3-
1346.14
06Jan’21
1st SIV
wo/PR
NDA-a:
Sep’26
CTA Review + EC +
HGRAC + SIV
Open-label safety extension; treatment duration 12m
CTA-s
01Jun
FPI
NDA-s
Jun’25 (best)
13Apr’22
today
Global
RoFD
Dec’20
LPO
Jan’26
Jan’25
LPI
FPI
LPO
LPI
DBL
NDA-s
16May’25
NDA-a
Jan’26
HA consultation for CMC is planned around June 2024. The internal kick-off meeting on 12th Mar 2024
CN PK will be tested locally for CONNEX-1,3 &X to meet timeline. Method transfer is expected to completed at the end of July 2024
TW final randomized 58pts, 1pts gap for non-CPP requirement. Current strategy: submit Non-CPP NDA and response during the review if any
Nomination Chinese investigator for CONNEX manuscript
  Prof. Hongyan Zhang (CONNEX-1)
  Prof. Gang Wang (CONNEX-3, Pooled CONNEX)
FPI
CONNEX-3 (N=586)
LPO
LPI
CONNEX-1 TLR is expected on Nov.18th 2024
NDA-s potentially 2 weeks earlier (final timeline will be released after June HPSC)
w/PR
NDA-a
Jun’26
LPI
Oct‘24
LPO
TLR
18Nov24
April‘24
July’24
April‘24
Jan’25
Nov‘24
Ph3-
1346.13
FPI
CTA + EC + HGRAC + SIV
05Jul
CTA-s
1st SIV
Recruitment window: 29m; N=178: 120+58 (TW)
06Jan’21
FPI
8Nov24
Mar’24
DBL
LPI
Oct‘24
LPO
TLR
22Nov24
8Nov’24
FPI
DBL
TLR
Feb’25
Dec’24
LPO
LPI
July’24
April‘24
Jan’25
Nov‘24
DBL
Dec’24
DBL
Dec’24
Notes: 【As of 06Jan2023】
Global 1346.11: FPI on 21Oct2021@US
Global 1346.12: FPI on 28Sep2021@US
Global 1346.13: FPI on 08Sep2021@Korea
Global 1346.14: FPI on 21Mar2022
China 1346.11: FPI on 22Dec2021
China 1346.13: FPI on 20Oct2021
China 1346.14: FPI on 10May2022
【As of 3Apr2023】
Global adjusted CONNEX timeline by additional 9m.

## Slide 3: CONNEX recruitment status as of 17Apr 2024
 | CONNEX 1 |  | CONNEX 2 | CONNEX 3 |  | 
 | Global | China | Global | Global | China | Taiwan*
Total Screened [N] | 853 | 134 | 840 | 845 | 164 | 70
In Screening [N] | 0 | 0 | 0 | 83 | 0 | 0
Screen Failed [N (%)] | 199(24%) | 32(25%) | 229(27%) | 217(26%) | 32(21%) | 12(17%)
Randomised (actual VS. initial plan) | 620(a) VS. 586(p) | 96(a) VS. 88(p) | 611(a) VS. 586(p) | 545(a)VS. 586(p) | 120(a) VS. 62(p) | 58(a) VS. 40(p)
Discontinued [N (%)] | 76(12%) | 9(9%) | 61(10%) | 63(12%) | 8(7%) | 3(6%)
Completed [N] | 363 | 71 | 351 | 322 | 99 | 38
Estimated Percentage (%)/Global randomization | / | 15.5% | / | / | 20% | 10%
* updated by 24Apr2024

## Slide 4: 1346-0014 rollover study China and Taiwan recruitment summary _cutoff date 17Apr2024
 | China | Taiwan
Rolled over(p) | 175 | 50
Rolled over(a) | 126 patients rolled over (rollover rate 126/170=74%) | 35 patients rolled over
Discontinued Treatment Early | 10 (8%) | 3 (8.6%)
Completed Treatment | 49 | 15

## Slide 5: CONNEX Global & Local CIAS Publication Plan
1346-0011 Ph III CONNEX 2
Q1
Q2
Q3
Q4
Q4
Q1
Q2
Q3
Q1
Q2
Q3
Q4
2024
2025
Manuscripts
1346-0011 Ph III CONNEX 1
Ps
CIAS review in Chinese SCZ
1346-0013 Ph III CONNEX 3
1346-0014 Ph III CONNEX X
Ps
Ps
Ps
Ph III CONNEX Pooled Efficacy
Ph III CONNEX Pooled Safety
US LAUNCH
Q1 2026
2026
Ps
Ps
1346-0011 Ph III CONNEX 1 Post Hoc Analysis
Ps
1346-0012 Ph III CONNEX 2 Post Hoc Analysis
Ps
1346-0013 Ph III CONNEX 3 Post Hoc Analysis
Ps
1346-0014 Ph III CONNEX X Post Hoc Analysis
Ps
CHINA
Early phase data encores [CSP 2024]
Ph III CONNEX Asian/Chinese (Efficacy + Safety)
CONNEX TLR [CSP 2025]
Congress abstract
Manuscripts
Other local ECRs and IIS publications
1
3
Nomination Chinese investigator for CONNEX manuscript
Category | Status | Publication | Name | Institution | Note
 | Proposed to Global on April 19th | CONNEX-1 | Hongyan Zhang | Sixth Hospital of Peking University | CONNEX-1 Leading PI
 |  | CONNEX-3 | Gang Wang | Beijing Anding Hospital | National coordinator CONNEX-3 Leading PI CONNEX-X Leading PI
 |  | Pooled CONNEX | Gang Wang |  | 
1
Will further evaluate nominations internally and communicate with Prof. Wang prior to proposed to global
2
Will ask global support that CN to lead these publications (CN first author)

## Slide 6: One Page Summary ━ CREA (CNS)
On track
Timeline: > 3 months delay
Strategic issue: project to be terminated, China integration/development undermined;
Operational issue: major enrollment delay, significant poor compliance;
Regulatory issue: negative comment from authority, major concerns due to regulation change;
Not meeting primary end point;
Quality: ≥ 1 critical and/or ≥ 4 major site audit observations; inspection readiness with critical issues; critical NC report
Timeline: 1-3 months delay or potential delay;
Strategic issue: global strategy uncertain; China integration/development at risk, insufficient China sample size;
Operational issue: slow enrollment, compliance rate lower than plan;
Regulatory issue: technical and/or dossier issues and/or deficiency letter with potential impact to approval and/or approval timeline;
Quality: 3 major site audit observations, inspection readiness with significant issues; major NC report
TA | Ongoing |  | Endorsed | Under evaluation | Next wave
CREA | Iclepertin (GlyT1) CIAS – Ph3 |  | BI 1358894 (TRPC4/5) PTSD – Ph3 | CT-155 (DTx) Negative symptom of Schizophrenia | BIBF 1120 (Nintedanib IVT (TKi) / wAMD
 | Metalyse (TNK) AIS – Ph3 |  | BI 1358894 (TRPC4/5) MDD – Ph3 Ph2 TLR: Efficacy - failed to separate from placebo on MADRS change from baseline at Week 6 AT to propose Asset Termination in Apr’s HPSC | BI 1815368 (PKKi) wAMD prevention - CN: Ph2 | BI 3031185 (mGluR4 NAM) / Impulsivity
 | BI 1569912 (NR2B NAM) MDD adjunct– Ph2 (FOT) |  | BI 764524 (anti-SEMA 3A) DR – CN: Ph3 | BI 1584862 (PAFR antagonist) GA – CN: Ph2. | Iclepertin (GlyT1) / LAI for CIAS PMO
 |  |  |  | BI 771716 (anti-C3) GA– CN: Ph2/Ph3 | BI 3776528 (SSTR4 ago.) / CI PSD (Cognitive Impairment in Psychosis Spectrum Disorders)
 |  |  |  | BI 1356225 (GOATi) Impulsivity in Substance Use Disorder | CT-156 (DTx) / Schizophrenia (functioning)
 |  |  |  |  | BI 3793898 (mGluR3 PAM) / CIAS
Notes: Predefined PoCP criterion for aNrp-1 not met​
Deep analysis of the data did not reveal any treatment impact on Retinal Non-Perfusion​
Further activities for aNrp-1 in DR are not recommended​
aNrp-1 did not show preclinically neuroprotective activity: no alternative development scenario in RH​

## Slide 7: Ongoing: BI 1569912 (NR2B NAM) — Major Depressive Disorder (MDD) adjunct
Ph1b-1447.3
Ph1 MRD
1447.2
Ph1-1447.4
Ph2-1447.5
Ph2-1447.5
Ph2 (N=16)
MutaMouse study positive to lift clinical hold
US NDA-a:
Mar 2030
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  | 2025 |  | 2026 |  | 2027 | 2027 | 2028 | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 |  | 
Global
China
CTP/ICF
Dec’23
Nov’22
Aug’23
PoCP trial (N=66)
FPI
LPO
MRD in HV (N=60)
FPI
Oct’22
LPO
Sep’23
JP Ph1 (SRD)
FPI
Sep
LPO
Feb
today
MD (20mg)
FPI
Sep
LPO
Nov
Ph2 trial (N=204)
Mar’24
FPI
LPI
Sep’25
TLR
Jan’24
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA-s
Q2/3 ’24
20Dec’23
PoCP
Feb’24
wo/pre-IND
US FPI on 27Mar2024
It’s obtained the EC approval from leading site on 23rd Apr 2024.
China submitted the CTA as the 1st submission in global on 20th Dec 2023, and received the formal CTA approval on 11th Mar 2024.
China has been allocated for 16 patients with 10 sites.
China Leading PI is Prof. Li Huafang from 上海市精神卫生中心.
CH NDA-a:
Nov 2030
FOT: IQVIA
FOT: IQVIA
LPI
Sep’25

## Slide 8: NR2B NAM PoCP Study Design
Optional 6-w lead-in phase
with SSRI/SNRI
S
R
20 mg n= 20 single admin.
5 mg n= 20 single admin.
Placebo n= 19 single admin.
Screening
in-patient
Day 1
Day 2
Day 4
Day 6
Day 8
Day 15
out-patient (follow-up)
Day 11
Study design
Study schematic
MDD patients with inadequate response to ≥1 antidepressant in current episode
Single administration of BI 1569912 (20 mg or 5 mg), or placebo; adjunct to ongoing SSRI / SNRI therapy
Primary endpoint is safety and tolerability; max decrease in MADRS within 7 days
Dissociation assessed by CADSS, B-VAS, SMWQ
PoCP criteria: Improvement in MADRS total score compared to placebo ≥3 at one time point and ≥2 at a neighboring time point in either dose

## Slide 9: Safety and tolerability on treatment and follow up
Percentages are calculated using total number of subjects per treatment as the denominator. MedDRA version used for reporting: 26.1
1 Primary safety endpoint
System organ class/Preferred term | Placebo |  | BI 1569912 5 mg |  | BI 1569912 20 mg | 
Preferred term | N | % | N | % | N | %
Number of patients | 19 | 100.0 | 20 | 100.0 | 20 | 100.0
Patients with any AE | 6 | 31.6 | 7 | 35.0 | 3 | 15.0
Patients with severe AEs | 0 | 0.0 | 0 | 0.0 | 0 | 0.0
Patients with AEs of special interest | 0 | 0.0 | 0 | 0.0 | 0 | 0.0
Patients with serious AEs | 0 | 0.0 | 0 | 0.0 | 0 | 0.0
Patients with investigator defined drug-related AEs:1 | 1 | 5.3 | 3 | 15.0 | 1 | 5.0
Gastrointestinal disorders | 0 | 0.0 | 2 | 10.0 | 0 | 0.0
Investigations (increased blood pressure) | 0 | 0.0 | 1 | 5.0 | 0 | 0.0
Metabolism and nutrition disorders | 1 | 5.3 | 0 | 0.0 | 1 | 5.0
Nervous system disorders | 1 | 5.3 | 1 | 5.0 | 0 | 0.0
Psychiatric disorders | 1 | 5.3 | 0 | 0.0 | 0 | 0.0
Skin and subcutaneous tissue disorders | 0 | 0.0 | 0 | 0.0 | 1 | 5.0
BI 1569912 was safe and well-tolerated, with a comparable amounts of adverse events compared to placebo. No clinically relevant changes on group level for blood pressure and for notable findings in the ECG were observed.

## Slide 10: BI 1569912 20 mg demonstrated rapid onset, sustained for five days post-administration
Between 3.4 and 4.9 point improvement from Day 2-Day 6 after single administration (PoCP criteria was ≥3 points at one time point and ≥2 points at a neighboring time point in either dose)

## Slide 11
MDD adjunct PoCC key study assumptions and timelines
Key assumptions | 
Screened | 469
Randomized | 204
Screen Failure Rate | 55% (average)
Crude recruitment rate (FSS-EoS) | 0.17
Net recruitment rate | 0.30
Enrollment Duration | 16 months
Drop Out Rate | 15%
Total Countries/Sites | 7/63
Key milestones | 
First Subject Screened | 20-Mar-2024
75% site activation | 27-Sept-2024
Last Subject Randomized | 5-Sep-2025
Last Subject Completed (End of study) | 31-Oct-2025
Database Lock | 12-Dec-2025
Topline Results | 16-Jan-2026
We are assuming an ambitious 0.3 nRR and 75% site activation within six months. For reference, TRPC4/5 MDD averaged ~0.17 nRR post-COVID
Lead indication: Aspiration & development strategy
From HPSC

## Slide 12: NR2B asset maximization scenarios
 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039
Explore now |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Depression now, expand later |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Focus on MDD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Note: Timelines shown are illustrative pending further diligence; submissions may have to be delayed pending prior submission approval; Long term studies not shown for clarity
New indication SODs
Key considerations
Assess full potential of asset ASAP – can decide to pivot to high unmet need indications if desired
PTSD and OCD studies are derisked with seamless phase 2a / 2b design e.g., ~10M EUR at risk for each
Assess potential in depression ASAP where we have highest confidence
Derisk expansion investment in PTSD and OCD with PoCC in MDD adj e.g., ~10M EUR at risk for each
MDD adj
MDD mono + adj
NDA
US approval
BD
BD
NDA
US approval
PoCC achieved in MDD adjunct
IRA pricing in effect
PTSD
NDA
US approval
OCD
NDA
US approval
PIND
PTSD
OCD
PIND
MDD adj
BD
BD
NDA
US approval
PTSD
NDA
US approval
OCD
NDA
US approval
PIND
PTSD
OCD
PIND
NiSOD
NiSOD
MDD adj
Proposed scenario
Ph2b dose-range finding study
Ph3 studies
Ph2a signal-finding study
NiSOD
NiSOD
NiSOD
NiSOD
Focus on highest value opportunity: MDD
Initiate development for other indications once MDD pivotal studies are kicked off – as to not distract team during intense period of Ph2-Ph3 transition for MDD
BD
BD
NDA
US approval
PTSD
NDA
US approval
OCD
US approval
PTSD
OCD
PIND
NiSOD
NiSOD
NiSOD
MDD mono + adj
NDA
US approval
MDD mono + adj
NDA
US approval
MDD mono
MDD mono
MDD mono
1
2
3

## Slide 13: NR2B NAM high level program timeline
2024
2032
Today
Aug 16
262 days
Apr 24 - Apr 24
138 days
Jul 22 - Jan 29
496 days
Mar 8 - Jan 30
126 days
May 13 - Nov 4
344 days
Oct 15 - Feb 8
570 days
Oct 25 - Dec 31
570 days
Oct 25 - Dec 31
233 days
Sep 19 - Aug 11
116 days
Oct 25 - Apr 5
116 days
Oct 25 - Apr 5
131 days
262 days
Apr 24 - Apr 24
1043 days
Dec 31 - Dec 28
707 days
Oct 25 - Jul 10
Dec 18 - Jun 18
953 days
Oct 25 - Jun 19
570 days
Oct 25 - Dec 31
485 days
Feb 28 - Jan 7
May 1
Nov 30
569 days
Dec 7 - Feb 11
Feb 20
Feb 20
370 days
Sep 1 - Jan 30
May 11
Jan 31
Jan 31
Jun 11
Jan 8
Dec 1
Mar 1
Jul 28
Indication
NDS
Clinical supporting studies
MDD
mono + adj
CMC
BD Depr.
PoCC
2024
2025
2026
2027
2028
2029
2030
HPSC RoFD
Development iCF solid oral
1447-0006: DDI victim of CYP2J2 inhibition
1447-0005; Ph II DRF; MDD adj.
1447-0007: DDI induction potential of CYP2B6 & CYP3A4
Longterm tox (26w/39w) rat/dog
Short term efficacy - adjunct
Short term efficacy - mono
1447-0010; Human ADME/Absolute BA
Hepatic impairment
Renal impairment
non-clinical abuse potential studies
Process development & scale-up
Carcinogenicity Studies
Long-term open label extension
Randomized withdrawal study – 26 weeks
Short-term efficacy – vs vortioxetine (DBL to week 6 for US, JPN; OL to week 26 for G-BA)
1447-0014 - Ph II DRF
NDA
Appr. US
2031
Ph III program
PoCP
niSoD
Ph II DRF; MDD mono
Approval US
PoCC
NDA
2032
PoCC
MAA
Appr. EU
Appr. JP
Jul 28
JNDA/SNDA
Jan 23
Appr. CN
FSS
Key Results
today

## Slide 14: Summary of Leading PIs on PTSD & MDD in China
Study – planned | PI proposal | Site
TRPC 4/5 MDD Ph3 *3 studies (single dose* vs placebo) | 王刚 | 北京大学第六医院
 | 李华芳 | 上海市精神卫生中心
 | 张鸿燕 | 北京大学第六医院
TRPC 4/5 PTSD ph3 *2 studies (single dose vs placebo/ 2 doses vs placebo) | 王刚 | 北京大学第六医院
 | 王振 | 上海市精神卫生中心
 | 于欣 | 北京大学第六医院
 | 李凌江 | 中南大学湘雅第二医院
TRPC 4/5 PTSD ph1 | 李华芳 | 上海市精神卫生中心
NR2B MDD Ph2 | 李华芳 | 上海市精神卫生中心
Study - ongoing | PI | Site
CONNEX-1 1346.11 | 张鸿燕 | 北京大学第六医院
CONNEX-1 1346.13 | 王刚 | 首都医科大学附属北京安定医院
CONNEX-1 1346.14 | 王刚 | 首都医科大学附属北京安定医院

## Slide 15: Under evaluation: CT-155 Digital Therapeutics — Negative Symptom of Schizophrenia
Clinical learning studies
US Sub*
Oct’24
Aug’25
US Appr
Apr’25
Jan’26
CLS 3
Pivotal trial
CLS 1
CLS 2
TLR
Jul’24
Mar’25
RCT in US (Convoke trial)
31Mar’23
FPI
Global
China
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 |  | 
today
Device testing (3m)
NDA-s
Mar’26
NDA-a
H1’28
NDA-s
H1’27
NDA-a
Mar’27
Localization (6m, tbc)
CTA+EC+HGRAC+1st SIV (6M)
CTA-s
Q3’25
FPI
Q2‘26
RCT in China
RCT in China
- Not preferred
2
Device testing
Scenarios
NMPA
consultation
Due to the RCT recruitment challenges, the project timeline was re-based in Feb’s HPSC.
w/o China RCT*
- Preferred
1
* Overseas data + ethnic difference analysis + RWE
RoFD
27Jan’23
Localization (6m, tbc)
Pre-IND
All regions have NO any centric activities planned before TLR released by Mar 2025.
Notes: Type III App myPKFiT (Takeda) via Priority Review:
  NDA-s: before 15 Mar 2019
  NDA-a: 17 Nov 2020

## Slide 16: CT-156 Study planning: focusing on functional impairment - including medication adherence – in people living with Schizophrenia
CLS2 FPI May 6, LPO Dec 9
TLR
CLS1 completed
RCT FPI Apr 2025
US Appr
Aug 2028
CLS1 (Clinical Learning Study) TLR: enhances confidence that the CT-156 approach effectively engages participants
CLS2: Under preparation
RCT FPI projected for Apr 2025

## Slide 17: One Page Summary ━ CREA (Retinal Health)
On track
Timeline: > 3 months delay
Strategic issue: project to be terminated, China integration/development undermined;
Operational issue: major enrollment delay, significant poor compliance;
Regulatory issue: negative comment from authority, major concerns due to regulation change;
Not meeting primary end point;
Quality: ≥ 1 critical and/or ≥ 4 major site audit observations; inspection readiness with critical issues; critical NC report
Timeline: 1-3 months delay or potential delay;
Strategic issue: global strategy uncertain; China integration/development at risk, insufficient China sample size;
Operational issue: slow enrollment, compliance rate lower than plan;
Regulatory issue: technical and/or dossier issues and/or deficiency letter with potential impact to approval and/or approval timeline;
Quality: 3 major site audit observations, inspection readiness with significant issues; major NC report
TA | Ongoing |  | Endorsed | Under evaluation | Next wave
CREA | Iclepertin (GlyT1) CIAS – Ph3 |  | BI 1358894 (TRPC4/5) PTSD – Ph3 | CT-155 (DTx) Negative symptom of Schizophrenia | BIBF 1120 (Nintedanib IVT (TKi) / wAMD
 | Metalyse (TNK) AIS – Ph3 |  | BI 1358894 (TRPC4/5) MDD – Ph3 Ph2 TLR: Efficacy - failed to separate from placebo on MADRS change from baseline at Week 6 AT to propose Asset Termination in Apr’s HPSC | BI 1815368 (PKKi) wAMD prevention - CN: Ph2 | BI 3031185 (mGluR4 NAM) / Impulsivity
 | BI 1569912 (NR2B NAM) MDD adjunct– Ph2 (FOT) |  | BI 764524 (anti-SEMA 3A) DR – CN: Ph3 | BI 1584862 (PAFR antagonist) GA – CN: Ph2. TALC endorsed that the Ph2 PoCP/PoCC study will be only run in US for the budget saving focus. | Iclepertin (GlyT1) / LAI for CIAS PMO
 |  |  |  | BI 771716 (anti-C3) GA– CN: Ph2/Ph3 The Asian strategy is under discussion, but Ph2 will be only run in US as same as PAFR. | BI 3776528 (SSTR4 ago.) / CI PSD (Cognitive Impairment in Psychosis Spectrum Disorders)
 |  |  |  | BI 1356225 (GOATi) Impulsivity in Substance Use Disorder | CT-156 (DTx) / Schizophrenia (functioning)
 |  |  |  |  | BI 3793898 (mGluR3 PAM) / CIAS
Notes: Predefined PoCP criterion for aNrp-1 not met​
Deep analysis of the data did not reveal any treatment impact on Retinal Non-Perfusion​
Further activities for aNrp-1 in DR are not recommended​
aNrp-1 did not show preclinically neuroprotective activity: no alternative development scenario in RH​

## Slide 18
China GA ECR
PART A：Cross-sectional
N=100~150
Data of the first visit
Objective:
Description of BCVA and GA lesion involvement of fovea
Multimodal imaging features and phenotypes
PART B：Prospective cohort
N=50
Observation period: 2 years
Objective：
The change of GA lesion size and progression rate of lesion after 2 years
The change of BCVA and GA lesion involvement of fovea after 2 years
* Partner with Prof Chen Youxin from Peking Union hospital leading 6 centers
Fill the data gap of disease phenotypes, progression rate and potential predictor biomarkers in China, thus enlighten the GA development strategy in China and Asia

## Slide 19: China Evidence Generation Strategy for GA Disease Area
Anti-C3 Ph II in US Feb 2025-Jan 2027
Anti-C3 Ph III Apr 2027- Apr 2030
2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
PAFR PhII in US Q1 2025-Q1 2027
POCP
PAFR PhIII Q1 2028- 2031
POCP
ECR protocol finalization + IRB approval July 2024
Data collection and analysis
Dec 2026
CTR
Feb 2027
20-25%€
70-80%€
100%€
Interim analysis
Jan 2026
Provide progression rate and phenotype data to support China Ph3
Anti-C3 pan-Asian Ph1 (TBD)
(Acceleration Scenario)

## Slide 20
2022 |  | 2023 |  |  |  | 2024 |  | 2025 |  | 2025 |  |  |  | 2026 |  |  |  | 2027 | 2028 | 2029 | 2030 | 2031
H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 
Endorsed:
BI 764524 (aSema3A)– Non-Perfusion Diabetic Retinopathy (NPDR)
China
Ph2b (N=120~150), recruitment window (12 m); trt (52 wk); off-trt (26 wk)
Mar’24
FPI
Jul’26
LPO
Global
Launch
2030
Post-PoCP trials
today
aSema3A
Post-PoCP trials
Eye-EMI, N=650
1436.2: non-interventional
Jun’22
LPI
PoCP
mid-Jul’23
LPI
Mar’25
1436.1 Ph1/Ph2a
26Apr’23
LPO
25Nov’22
LPI
29Sep’20
FPI
1436.2: non-interventional
LPI extended
15Jul’22
Eye-EMI, N=650
Jun
LPI
Phase 3
IA
FOT: ORA
China integration into Ph2b was NOT supported by the Asset Team. To keep the variability and complexity (and cost) low, Ph2b will focus on limited countries. It was suggested by the Asset Team to look into ECR opportunities and pave the way for Ph3.
PMDA mtg
Jul’23
Japan
Phase 3
Ph1/2a completed for both aSema3A & aNRP1
Data analysis ongoing, TLR of anti-SEMA 3A available at end of Jun’23
TDO for Phase IIb close to finalization
PMDA agreed the SRI strategy before Ph2b. FDA disagreed to use Sham in Ph3 and not recommend for Ph2.

## Slide 21
Ph2: 1485.6
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  | 2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 | 2029 | 2030 | 2031 | 2032
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 
NDA-a
Oct‘31
today
China
Ph1: 1485.1 & 2
SRD & MRD
Under evaluation:
BI 1815368 FR (PKKi) — wAMD prevention
Phase IIa & IIb (to be updated)
2027
LSC
Jan’25
FSS
Phase III * 2
2030
LSC
Q3’27
FSS
Ph2: 1485.4
SRD
17Jun
4Nov’22
Ph3: 1485.7 & 8
Phase III
2030
LSC
Q3‘27
FSS
NDA-a
Nov‘31
Ph3: 1485.7/8
Japan Ph1: 1485.5
Sep’24
Dec’24
MRD
05Jan’24
19Jun
PoCP
Q3 2024
J-Ph1
FSI
LSC
DBL
Dec’24
wo/pre-IND scenario:
Phase IIa & IIb (to be updated)
CTA + EC + HGRAC + 1st SIV (6m)
May’25
1st SIV
2027
LSC
mid-Nov‘24
CTA-s
CTN-s
Apr’24
FOT: ORA
JP Ph1 dependent on PoCP
FSS
LSC
TLR
Mar’24
JP Ph1 postponed to Jun 2024 (originally Mar’24) due to the delay of Ph2 by 3m. TLR expected in Sep’24. But JP team plans to submit CTN in Jan’24 to keep the opportunity for early initiation of JP Ph1.
Feedback post ARVO about DME: CSFT would be a reasonable PoCC endpoint, and 3 months is seen a reasonable timeframe to get CSFT responses. Interaction w/ FDA was recommended to take place once ph2 data is available. TPP change to DME without VA impairment and compare to observation was recommended (in line with ARVO feedback).

## Slide 22
Thank You !

## Slide 23: Ongoing: BI 1358894 (TRPC4/5) — Post Traumatic Stress Disorder (PTSD)
2022 | 2022 | 2023 |  |  |  | 2024 |  |  |  | 2025 |  | 2025 |  | 2026 |  | 2027 | 2027 | 2028 |  | 2029 |  | 2030 | 2031
H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 |  | 
Ph3-1402.31/32/33
Ph2-1402.30
Global
China
Ph3-1402.32
N=266
02Feb’22
Oct
Jul
FPI
Ph3 short-term pivotal trials, N=TBD
Oct’24
TBD
IA
Mar’23
US NDA-s
May 2028
TBD
LPO
TBD
US NDA-a
Mar2029
Ph3 long-term pivotal trial, N=TBD
EOPII MR-s
Mar’24
LPI
LPO
FPI
LPO
FPI
Recruitment window TBD
Pre-IND MR-s
Mar‘24
Recruitment Window: TBD
To try join Ph3 directly in pre-IND (low PoS). If CDE disagrees, then:
CTA Review + EC + HGRAC + 1st SIV (6M)
Jul’24
today
Jan’25
CTA-s
FPI
NDA-s
Jun 2028
NDA-a
Dec 2029
FDA mtg
May’24
Ph3 CTP
Jun-Jul’24
Ph3-
1402.31/32/33
CN PK-
1402.XX
RoFD
Jun’24
TLR
04Dec’23
To give more insights from TRPC4/5 PTSD PoCC study in Feb 2024’s HPSC as below summary：
- There is insufficient consistent strong evidence from 1402-0030 to generate high confidence in a clinically relevant impact of the compound at this dose and with this posology in patients with PTSD