Christina Lian / Ansu Li

Head of PPM / MT

Boehringer Ingelheim China

Agenda

Portfolio Executive Committee (PEC)

Review Meeting

_____________________________________________

Thursday, 25th Apr, 2024

08:30 – 11:50

Meeting room: Microsoft Teams Meeting/C6

* Participation by TA & Topics, no full meeting participation needed, unless marked

* Meeting language: English

Shareroom link: PEC shareroom

Agenda by TA

| TA | Meeting time |
| --- | --- |
| Common session | 35 min |
| INFL | 40 min |
| CRM | 40 min |
| ONCO | 30 min |
| CREA | 30 min |

Agenda by Topic

|  |  | Topic | Speaker | Pre-reads | Time | Duration | Follow up actions/PEC decision/suggestion | Responsible person | Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (I) | Opening | Wei Zhang | N | 8:30 | 5 min |  |  |  |
|  | (I) | Last PEC meeting action points following up | RILs | Y | 8:35 | 10 min |  |  |  |
|  | (I) | RDPAC CO timeline survey | Kim Xue | Y | 8:45 | 15 min |  |  |  |
|  | (A) | Cross-function evaluation on FOT/HOM painpoints and solutions | Alex Zhang / Ansu Li | Y | 9:00 | 10 min |  |  |  |
|  | (I) | INFL Pipeline Overview | Yuting Li / Ying Chen | Y | 9:10 | 25 min |  |  |  |
|  | (E) | Feasibility results of ECR-EPI study of PG and HS | Yijun Zhou | Y | 9:35 | 15 min | - Proposal endorsed to include HS draining tunnel in key outcome analysis and not to add NS in the study - Proceed with current proposal, and in-parallel to evaluate the possibility of adding GPP into the study scope, i.e. impact on timeline and budget. | Yijun Zhou/Guoze Feng | May 2024 |
|  |  | Break |  |  | 9:50 | 20 min |  |  |  |
|  | (I) | CRM Pipeline Overview | Leo Bao/ Yinan Zhu / Lian Zheng / Yu Zhou/ Hongzi Liang | Y | 10:10 | 40 min | SYNCHRONIZE- CN - To recruit remaining patients from 7 MRI sites with prioritization of T2DM patients - To closely monitor the recruitment status of global trials and adjust the recruitment window of this trial as needed to ensure simultaneous NDA submission | Yinan Zhu& Amy Li | Jun 2024 |
|  | (I) | Oncology Pipeline Overview | Donglei Zhu / Nick Xue / Meiruo Liu | Y | 10:50 | 20 min | Beamion LUNG-1 - To closely monitor global BTD application strategy and further evaluate local strategy accordingly | Juno Hu & Lijie Yu | May 2024 |
|  | (I) | DDLPS RWE results update and publication plan | Sherry Fu | Y | 11:10 | 10min |  |  |  |
|  | (I) | CREA Pipleline Overview | Sarah Liang / Jiaqi Lu | Y | 11:20 | 15 min | GA ECR: - Endorsed. |  |  |
|  | (I) | Metalyse & Actilyse Overview | Jiaqi Lu/ Leo Bao | Y | 11:35 | 15 min | Actilyse: - To explore the opportunities of re-submission timeline acceleration. | Leo Bao |  |
|  |  | Close |  |  | 11:50 |  |  |  |  |

*Purpose of the presentation: Information sharing (I), Advice collection (A), and Content Endorsement (E)

| Standing members & Standing invitation & Guests |  |
| --- | --- |
| Standing members (Full meeting participation): - Chair: Wei Zhang - Function Heads: - Head of RA: Kuncy Xia - Head of CD&O: Jessie Song - Head of BDS: Hongjie Deng - Head of Epidemiology: Qiang Li - Head of PSPV: Helen Tao Guests: - Head of RA CMC: Ellen Wang - Head of PMS: Liqun Tian - Head of CMC Experts China: Haixia Ren | Standing invitation: - Head of QM: Ling Xu - Head of HK Medicine: Coriue Cheong - Head of TW Medicine: Carol Yang - Head of HAMA: Carol Liu - Head of Trial Management, CD&O: Alex Zhang - Head of Development China: Jun Lu - Head of TMCP: Shaonan Wang |
| Members per TA (Oncology) |  |
| - TAH/TAL in each medical function: - TAH: Sally Chen - Early Asset Lead: Meiruo Liu - Brigimadlin Evidence Lead: Donglei Zhu - RA: Lijie Yu - CD&O: Catherine Zhang - BDS: Eric Song - PV: Yanjie Shen, Ruoyi Gu |  |
| Members per TA (Inflammation) |  |
| - TAH/TAL in each medical function: - TAH: Helen Tao - RIL: Yuting Li - Spesolimab Evidence Lead: Ying Chen - RA: Michael Chen - CD&O: Ying Zhang - BDS: Hui Wang - PV: Hui Huang/Yongfei Guo |  |
| Members per TA (CRM) |  |
| - TAH/TAL in each medical function: - TAH: Julia Zhu - Early Asset Lead: Hongzi Liang - Survodutide Evidence Lead: Yinan Zhu, Lian Zheng - RA: Doris Han - CD&O: Angela Xiao - BDS: Harry Hua - PV: Maggie Dai / Cynthia Shi |  |
| Members per TA (CREA) |  |
| - TAH/TAL in each medical function: - TAH: Christina Lian - Associated TAH: Gloria Sun - Early Asset Lead: Jiaqi Lu - Iclpertin Evidence Lead: Sarah Liang - RA: Lincy Liu - CD&O: Alex Zhang - BDS: Hongjie Deng (acting) - PV: Maggie Dai, Cynthia Shi |  |