Meeting minutes

Portfolio Executive Committee (PEC)

Review Meeting

_____________________________________________

Monday, 15Dec2025

12:30-15:25

Meeting room: Microsoft Teams Meeting/30F B9

Agenda by TA

| TA | Meeting time |
| --- | --- |
| Common session | 10 min |
| ONCO | 20 min |
| CRM | 85 min |
| INFL | 40 min |
| MHEH | 10 min |

|  | Topic | Speaker | Decisions/Follow up actions/Advice | Responsible person | Timeline |
| --- | --- | --- | --- | --- | --- |
|  | Opening | Wei Zhang |  |  |  |
|  | Follow-up actions from the last PEC -Cross-TA topics | Action owners | NDA submissions in Hong Kong: to update the Neradominast HK NDA approvals’ timelines in IPF & PPF indications. | Kuncy Xia & Karen Yuen | Next PEC |
|  | TA Oncology |  |  |  |  |
|  | Updates-Oncology | Jiaqi Lu, Juno Hu, Donglei Zhu, Nick Xue | Zongertinib-1L NSCLC: to revisit the NDA approval timeline after CFDI inspection around mid of Feb 2026. Afatinib-Chordoma IIS​: to provide the study details to Dr. Zhang. | Lijie Yu Jiaqi Lu | Feb 2026’s PEC Next PEC |
|  | TA CRM |  |  |  |  |
|  | Follow-up actions from the last PEC-CRM | Action owners |  |  |  |
|  | Updates-CRM | Hongzi Liang, Yinan Zhu, Lian Zheng, Leo Bao, Julia Zhu |  |  |  |
|  | (E) Metalyse Late Time Window HA interaction strategy | Leo Bao | ☐For information sharing (I) ☐For advice collection (A) ☑For content endorsement (E) Endorsed PEC comments: - PEC endorsed the China health authority communication plan. - PEC suggested team to fully align with global team for China HA interaction plan and let global team understand the uncertainty for NDA approval if China directly submits the CTA without the pre-IND consultation to confirm with CDE on the NDA requirements. | Leo Bao | Next PEC |
|  | (E) Asian phase 1 trial on FAP/TRAILR2 in MASH cirrhosis patients | Julia Zhu | ☐For information sharing (I) ☐For advice collection (A) ☑For content endorsement (E) Not Endorsed PEC comments: - PEC suggested team to evaluate the value by enrollment of limited Chinese patients, and the invested resource and operational complexity increased under scenario 2 (CDE not request, but PMDA request Asian data) - PEC suggested team to clearly clarify the two questions for consultation, and if an intensive PK could be waived through this Asian phase 1. - An ad hoc PEC meeting will be planned for further endorsement. | Julia Zhu | Next PEC |
|  | # (E) Two RWE studies for VicaEMPA | Chloe Wang, Wenjing Tan | ☐For information sharing (I) ☐For advice collection (A) ☑For content endorsement (E) Endorsed PEC comments: - PEC highly recognized the value of the two RWE studies, especially the business value and endorsed the study proposals without any comments. |  |  |
|  | TA INFL |  |  |  |  |
|  | Updates-INFL | Saskia Kind, Ying Chen, Bo Wang, Yayun Zhu, Helen Tao |  |  |  |
|  | (I/A) China development strategy for Nerandomilast SSc indication | Bo Wang | ☑For information sharing (I) ☑For advice collection (A) ☐For content endorsement (E) PEC comments: - PEC suggested team to formally communicate with the global team regarding the potential risks associated with obtaining approval for the SSc/SSc-ILD indication in China and maintain a written record of the communication. | Bo Wang | Next PEC |
|  | TA MHEH Update |  |  |  |  |
|  | Updates-MHEH | Meiruo Liu, Freya Zhu, Jingbo Xiao |  |  |  |
|  | Close |  |  |  |  |

*Purpose of the presentation: Information sharing (I), Advice collection (A), and Content Endorsement (E)

| Standing members & Standing invitation & Guests |  |
| --- | --- |
| Standing members (Full meeting participation): Chair: - Head of Medicine: Wei Zhang Function Heads: - Head of TA CRM Medicine: Emma Xie - Head of TA INFL Medicine: Helen Tao - Head of TA MHEH Medicine and Early Asset Lead: Meiruo Liu - Head of TA Oncology Medicine: Sally Chen - Head of RA: Kuncy Xia - Head of CDO: Jessie Song - Head of BDS: Hongjie Deng - Head of RWE: Qiang Li - Head of PSPV and QM: Ling Xu - Head of X-TA Excellence: Grace Wang - Head of Development CMC China: Yanling Wang - Medicine Insights and PMO: Harry Hua Guests: - HR: Michelle Zhou | Standing invitation: - Head of HK Medicine: Karen Yuen - Head of TW Medicine: Carol Yang |
| Members per TA (Oncology) |  |
| - aTAH: Elaine Yu - eAL: Jiaqi Lu - RA: Lijie Yu - CDO: Catherine Zhang - BDS: Eric Song - PSPV: Ruoyi Gu - RWE: Jill Zhang - QM: May Yu |  |
| Members per TA (Inflammation) |  |
| - aTAH: Lindsay Xu - eAL: Saskia Kind - RA: Michael Chen - CDO: Ying Zhang - BDS: Hui Wang - PSPV: Hui Huang - RWE: Guoze Feng - QM: Vera Zhang |  |
| Members per TA (CRM) |  |
| - aTAH: Jenny Yang - eAL: Hongzi Liang - RA: Doris Han, Lincy Liu - CDO: Angela Xiao - BDS: Fei Ji - PSPV: Yanjie Shen - RWE: Wenjing Tan - QM:Liuqiong Wu |  |
| Members per TA (MHEH) |  |
| - RA: Lincy Liu - CDO: Alex Zhang - BDS: Harry Hua - PSPV: Yingxia Zhang - RWE: Raven Zheng - QM: Simon Shi |  |