## Slide 1: Portfolio Executive Committee (PEC) Review Meeting TA ONCOLOGY
  Jiaqi Lu, Juno Hu, Donglei Zhu, Nick Xue | 20251215 | 20 mins
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Part I: Portfolio Update

## Slide 3: 2025 ONC Key Milestone Overview
PoPP for VSV-GP OV (it, iv, all comers)
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
RoFD for Zongertinib in Adjuvant NSCLC
Termination
Study start/ read-out
Milestone
Termination
SoD/PoPP/PoCP/RoFD
TLR
Pre-IND/CTA/SIV
BTD/NDA
Global milestones
China milestones
Beamion Lung-1 Cohort 2 TLR
Zongertinib – 1L NSCLC
NDA Sub. for Zongertinib in 2L NSCLC
Dareon-5 Type II Meeting Sub.
Obrixtamig – NEC
Ph1b 1st SIV
CD137/FAP – 1L HNSCC
RoFD for Obrixtamig in 1L SCLC
NDA Approval for Zongertinib in 2L NSCLC (26th Aug)
BTD Sub. for
Zongertinib – 1L NSCLC
Dareon-Lung-1 pre-IND Sub.
Obrixtamig – 1L SCLC
US launch for Zongertinib in 2L NSCLC
(8th Aug)
PhIII CTA Sub.
Zongertinib – Adjuvant NSCLC
US NDA Sub. for Zongertinib in 1L NSCLC
30th Sep
RoFD for Obrixtamig in 1L epNEC
NDA Sub. for Zongertinib in 1L NSCLC
(29th Oct)
SoD for HPK1 Degrader
RCC, NSCLC, HNSCC
SoD for KRAS G12D inh. (BU)
CRC
SoD for TAG72 ADC
GC; NSCLC; OC
SoD for LY6K-HLA/CD3
NSCLC, HNSCC
nSOD/RoFD for Zongertinib
Pan-tumor HER2+
Pan-tumor HER2m
nSOD: CRC
We are here
Dareon-Lung-1 CTA Sub.
Obrixtamig – 1L SCLC

## Slide 4: Part II: Project Update

## Slide 5: Zongertinib (BI 1810631, HER2 TKI)
P1-Lung

## Slide 6: Patients Enrollment for Beamion LUNG-1 Cohort 9 27 pts were enrolled by Dec 12th, 2025, 4.5 months ahead of plan
Accelerated Plan- Updated
Chart: Patient Enrollment Status
| 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113
Patients Enrolled/Randomized (Actual) | 7 | 11 | 22 | 27
Patients Enrolled/Randomized (orginial plan) | 1 | 5 | 8 | 14 | 19 | 20 | 23 | 25
Patient Screened(Actual) | 9 | 17 | 25 | 28
Patient Screened(Planned) | 1 | 6 | 9 | 16 | 20 | 25 | 27 | 30
Patients Enrolled/Randomized (updated plan) | 7 | 11 | 23 | 27

## Slide 7: Zongertinib (HERNEXEOS®) – 1L NSCLC Development Plan_AA
AA: Accelerated approval; CNPV: Commissioner’s National Priority Voucher
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph Ia/b
1479-0001
Beamion LUNG-1
Ph Ia/b
1479-0001
Beamion LUNG-1
May/Aug 2026
NDA app.*
Aug 2025
BTD granted
Ph Ib cohort 2
N=74
May 2025
TLR
Dec 2025
/Jan 2026
Jul 2025
BTD sub.
30 Sep
2025
NDA sub.
NDA app.
LPI
Jun 2024
FPI
Sep 2025
Ph Ib cohort 2
N=18
May 2025
TLR
29 Oct 2025
NDA sub.
LPI
Jun 2024
FPI
Sep 2025
*CN: With PR granted as assumption, the best case approval date based on 7-month review period without deficiency letter, the base case approval date based on 10-month review period with deficiency letter.
12-month updated data with DCO Aug will submit to CDE around Jan 2026 as rolling submission.
Inspection notification received on Dec 5. CFDI inspection is expected during end of Jan to early Feb, 2025. Inspection preparation is ongoing.
Aug 2025
Pre-NDA sub.
Selected for FDA CNPV Pilot Program on Nov 6 2025, approval expected in mid of Dec 2025(best case) or mid of Jan 2026 (base case)
STRICTLY CONFIDENTIAL
We are here

## Slide 8: Zongertinib (HERNEXEOS®) – 1L NSCLC Development Plan_ Full Approval
8
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph3
1479-0008
Beamion LUNG-2
Ph 3 N=416
Ph3, N=88
TLR
Dec 2026
FPI
Jan 2024
LPI
Apr 2026
Mar 2024
1st SIV
Apr 2027
NDA sub.
Aug 2027
NDA app.
May 2028
NDA app.
94% of recruitment target achieved in Nov 2025
Final enrolled number is 88, around 21% of total sample size.
* 1L NDA based on 12-month review period
Ph3
1479-0008
Beamion LUNG-2
LPI
Apr 2026
TLR
Dec 2026
May 2027
NDA sub.
We are here

## Slide 9: Beamion LUNG-2 zongertinib 1L NSCLC Recruitment 23 pts were enrolled as of 5th Dec 2025
New Enrolment Curve
China Mainland | New Allocation | Total Allocation
Target | 25 | 90
Actual | 23 | 88
China is still ranking as global 1st enrolling country.

## Slide 10: Zongertinib (HERNEXEOS®) – Adjunctive NSCLC Development Plan
MRD: minimal residual disease
10
2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
FPI
Nov 2025
Ph3, N=400
LPI
Nov 2028
Key results
Oct 2030
Feb
2031
NDA
sub.
Jun
2031
NDA
app.
Ph3, N=70
13 Feb 2026
CTA Review + EC + HGRAC + 1st SIV
Aug 2025
1st SIV
CTA Sub
IM is planned on Jan 24 2026
CTA approved on Nov13 2025
HGRAC with MRD tissue exportation was submitted on 19Nov and meeting result is expected this week. .
Mar
2031
NDA sub.
Jan
2032
NDA app.
Ph3
1479-0032
Beamion LUNG-3
Ph3
1479-0032
Beamion LUNG-3
LPI
Nov 2028
Key results
Oct 2030
We are here

## Slide 11: Zongertinib (HERNEXEOS®) – 1L NSCLC Combo
11
2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
FPI
May 2026
Ph2, N=60
LPI
2028
Key results
Ph2, N=8
Jul 2026
CTA Review + EC + HGRAC + 1st SIV
Jan 2026
1st SIV
CTA Sub
CTA finalized in Nov 6, 2025
Ph2
1479-0044
Ph2
1479-0044
LPI
Aug 2027
Further development plan
Aug 2027
2028
Key results
Prepare for CTA sub.
We are here

## Slide 12: Zongertinib (BI 1810631, HER2 TKI)
P2- Non-Lung

## Slide 13: Zongertinib P2 indications expansion: Zanidatamab combination in 2L BC, capture newly identified opportunities in pan-tumor, and CRC space new development
Status: Ph1
Combination: T-DM1 or cape/T or zani/cape
1st Launch: 2032
Mono or Combi Trastuzumab
1st Launch: 2029
Status: Ph1
Combination: wT-DXd
1st Launch: 2031
Status: Ph1b
Combination: wT-DXd
1st Launch: 2031
Indications:
HPSC approved
Dec 2024
2L HER2+ mGC
Indications:
New recommendation
Oct
2025
2L HER2+ mBC
2L HER2+ mGC
3L+ HER2+ mBC
Opportunity to add zani combination
Timeline after FDA feedback on track
DDI study for all indications with higher dose needed
Status: Ph1b
Combination: wTDM-1 or Cape/T
1st Launch: 2032
2L HER2+ mBC
Mono or Combi Trastuzumab
1st Launch: 2028
3L+ HER2+ mBC
Status: Ph2
Combination: mono
1st Launch: 2028
HER2+ pan-tum.
New opportunity
(ROFD)
Status: Ph2
Combination: mono
1st Launch: 2029
HER2m pan-tum.
New opportunity
(ROFD)
Status: 2L part pf pan-tumor strategy
Combination FOLFOX
1st Launch: 2032
1L HER2+ mCRC
New opportunity
(niSOD)
On track

## Slide 14: Zongertinib P2 project global update
HP BUEC endorsed the accelerated plans for CRC development and HER2m Pantumor with the assumptions/risks
Early Breast Cancer high level development plans were presented to Clinical Advisory Meeting with no objections
Zongertinib P2 indication team will be spilt to two indication team -- Breast Cancer indication team , Pantumor & Beyond indication team to strengthen indications focus.

## Slide 15: Zongertinib (HERNEXEOS®) – Pan-tumor Development Plan (Accelerate Approval)
15
2024 |  |  |  | 2025 |  | 2026 |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2
1479-0009
Beamion Pan tumor-1
FPI
Oct 2024
Ph2, N=430
LPI
Sep 2027
Key results 1
& NDA sub. 1
HER2 amplified cohorts
Q3 2028
NDA app.
(AA – HER2
Amplified Cohorts)
Q4 2027
SIV
Oct 2024
Ph2, N=40
LPI
Sep 2027
Key results 1
& NDA sub. 1
Q1 2029
NDA app. (AA – HER2
Amplification Cohorts)
Q1 2028
Q3 2029
NDA app.
(AA – HER2
mutant Cohorts)
Key results 2
& NDA sub. 2
HER2 mutant cohorts
Q4 2028
Q4 2029
NDA app.
(AA – HER2
Mutant Cohorts)
Key results 2
& NDA sub. 2
HER2 mutant cohorts
Q4 2028
CTA Review + EC + HGRAC + 1st SIV
May 2024
CTA Sub
Ph2
1479-0009
Beamion Pan tumor-1
We are here
Beamion Pantumor-1 was endorsed as a ‘registration-capable’ trial to support tumor agnostic approval in HER2 amplified and mutant population.
Preparations for the Type C package regarding pantumor development and dose strategy are in progress, FDA meeting is expected in Feb 2026.
CDO Update: 14 subjects were randomized and the additional 5 sites will be finalized by the end of Dec 2026.
China Health Authority Interaction to discuss pantumor development will be planned in parallel with the FDA type C meeting in Q1 2026.

## Slide 16: Zongertinib (HERNEXEOS®) – Pan-tumor Development Plan (Accelerate Approval) – New Timeline
16
2024 |  |  |  | 2025 |  | 2026 |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2
1479-0009
Beamion Pan tumor-1
FPI
Oct 2024
Ph2, N=430
LPI
Sep 2027
Key results 1
& NDA sub. 1
HER2 amplified cohorts
Q3 2028
NDA app.
(AA – HER2
Amplified Cohorts)
Beamion Pantumor-1 was endorsed as a ‘registration-capable’ trial to support tumor agnostic approval in HER2 amplified and mutant population.
Preparations for the Type C package regarding pantumor development and dose strategy are in progress, FDA meeting is expected in Feb 2026.
CDO Update: 14 subjects were randomized and the additional 5 sites will be finalized by the end of Dec 2026.
China Health Authority Interaction to discuss pantumor development will be planned in parallel with the FDA type C meeting in Q1 2026.
Q4 2027
SIV
Oct 2024
Ph2, N=40
LPI
Sep 2027
Key results 1
& NDA sub. 1
Q1 2029
NDA app. (AA – HER2
Amplification Cohorts)
Q1 2028
NDA app.
(AA – HER2
mutant Cohorts)
Key results 2
& NDA sub. 2
HER2 mutant cohorts
NDA app.
(AA – HER2
Mutant Cohorts)
Key results 2
& NDA sub. 2
HER2 mutant cohorts
CTA Review + EC + HGRAC + 1st SIV
May 2024
CTA Sub
Ph2
1479-0009
Beamion Pan tumor-1
We are here
Accelerated Timeline for HER2 mutant indication
Accelerated Timeline for HER2 mutant indication

## Slide 17: Global Recruitment Status (as of 12-Dec-2025)
Clinical Development and Operations
Chart: 1479-0009 Global Recruitment Plan
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143
Plan Screened | 4 | 17 | 33 | 47 | 60 | 74 | 89 | 104 | 119 | 131 | 141 | 153 | 163 | 176 | 185 | 195 | 207 | 225 | 242 | 260
Actual Screened | 4 | 31 | 57 | 89 | 108 | 115 | 127 | 137 | 152 | 170 | 181 | 192 | 198 | 222 | 226
Planned Randomized | 0 | 5 | 15 | 26 | 36 | 48 | 60 | 71 | 85 | 97 | 107 | 116 | 126 | 136 | 146 | 153 | 163 | 174 | 187 | 200
Actual Randomized | 2 | 15 | 35 | 54 | 75 | 87 | 91 | 98 | 108 | 120 | 131 | 139 | 144 | 157 | 163

## Slide 18: China Recruitment Status (as of 03-DEC-2025)
Clinical Development and Operations
Chart: 1479-0009 China Recruitment Status
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204
Plan Screened | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Actual Screened | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 7 | 8 | 8 | 10 | 11 | 11 | 19 | 19
Planned Randomized | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10
Actual Randomized | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 6 | 6 | 8 | 9 | 9 | 12 | 14

## Slide 19: Zongertinib (HERNEXEOS®) – Breast Cancer & Gastric Cancer (BC&GC)
19
2024 |  | 2025 | 2026 | 2027 |  | 2028 |  |  |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
H1 | H2 | Y | Y | H1 | H2 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Ph Ib/2-
1479-0012
Beamion BCGC-1
FPI
July 2024
Ph1b/2, N=594
CTA Review + EC + HGRAC + 1st SIV
Jan 2024
CTA Sub
LPI
Apr 2028
Ph1b/2-
1479-0012
Beamion BCGC-1
Key results &
NDA sub.
Q2 2029
NDA app.
BC 3L+ AA
New Protocol version 5.0 (new cohorts of CRC and BC were added) first submission (FDA) is planned in second week of Dec.
Q3 2028
FPI
July 2024
Ph1b/2, N=TBD
LPI
Apr 2028
Key results &
NDA sub.
Q3 2029
NDA app.
BC 3L+ AA
Q3 2028
Totally 13 subjects were enrolled.
1479-0012 CTP v5 (new cohorts of CRC and BC were added) CTA submission will target Jan 20th per CTP&ICF finalization timeline.
We are here

## Slide 20: Zongertinib (HERNEXEOS®)– Gastric Cancer 2L
2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Phase 3
1479-0013
Beamion Gastric-1
FPI
Q1 2027
Ph 3, Gastric Cancer 2L
CTA Review + EC + HGRAC + 1st SIV
CTA Sub
Q2 2030
NDA app. BC 2L FA
LPI
Q3 2030
NDA sub.
Q2 2031
Phase 3
1479-0013
Beamion Gastric-1
SIV
Aug 2026
Pre-IND Submission
Apr 2026
Jan 2027
Ph 3, Gastric Cancer 2L
Q2 2030
NDA app. BC 2L FA
LPI
Q4 2030
NDA sub.
Q3 2031

## Slide 21: Zongertinib (HERNEXEOS®)-- Breast Cancer 3L+
2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Phase 3
1479-0016
Beamion Breast-1
FPI
Jul 2027
Ph 3, Breast Cancar 3L+
CTA Review + EC + HGRAC + 1st SIV
CTA Sub
Q1 2030
NDA app. BC 3L+ FA
LPI
Q2 2030
NDA sub.
Q1 2031
Phase 3
1479-0016
Beamion Breast-1
SIV
Jul 2027
Ph 3, Breast Cancar 3L+
Q2 2030
NDA app. BC 3L+ FA
LPI
Q3 2030
NDA sub.
Q2 2031
Jan 2027
Pre-IND Submission
Aug 2026

## Slide 22: Zongertinib (HERNEXEOS®)-- Breast Cancer 2L
2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Phase 3
1479-0017
Beamion Breast-2
FPI
Q3 2027
Ph 3, Breast Cancar 2L
CTA Review + EC + HGRAC + 1st SIV
CTA Sub
Q4 2030
NDA app. BC 2L FA
LPI
Q3 2031
NDA sub.
Q2 2032
Phase 3
1479-0017
Beamion Breast-2
SIV
Q3 2027
Ph 3, Breast Cancar 2L
Q4 2030
NDA app. BC 32 FA
LPI
Q4 2031
NDA sub.
Q3 2032
Mar 2027
Pre-IND Submission
Nov 2026

## Slide 23: Obrixtamig (BI 764532, DLL3/CD3 TcE)

## Slide 24: Obrixtamig (DLL3/CD3 TcE) – 2L epNEC (single arm study)
24
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph2-
1438-0005
Dareon-5
Ph2, N=50
Ph2, N=5
Aug 2025
CTA Review + EC + HGRAC + 1st SIV
Feb 2025
1st SIV
CTA Sub
Ph2-
1438-0005
Dareon-5
SIV
Apr 2025
LPI
Jul 2026
Key results
Jan 2027
LPI
Jul 2026
Key results
Jan 2027
May 2027
NDA sub.
Jun 2027
NDA sub.
Total sample size will increase from 50 to 80. New protocol was released in end of Nov 2025.
The primary analysis is based on 50 pts.
Among the 50 pts, EA proportion is 30% which is JP12%, CN10%, KR8%.
China has recruited 4 patients. One responder was observed.
CMC HA interaction planned in Dec 2025.
HA interaction planned in early 2026 after interim futility analysis.
Jun 2028
NDA app.
Sep 2027
NDA app.
Futility analysis
Q1 2025
Futility analysis
Q1 2025
Q1-Q2 2026
HA interaction
We are here

## Slide 25: 1438-0005 DLL3/CD3 epNEC dated on 12Dec 2025 (Global recruitment status)
Chart: Patient Enrollment Status
| 45741 | 45772 | 45802 | 45833 | 45863 | 45894 | 45925 | 45955 | 45986 | 46016 | 46048 | 46079 | 46107 | 46138 | 46168 | 46199 | 46229 | 46260
Patients Enrolled (Actual) | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 11 | 13 | 14
Patients Enrolled (Planned) | 0 | 2 | 3 | 5 | 7 | 9 | 11 | 15 | 18 | 22 | 25 | 29 | 33 | 37 | 41 | 44 | 48 | 50
Patient Screened(Actual) | 0 | 0 | 1 | 2 | 12 | 22 | 50 | 77 | 108 | 118
Patient Screened(Planned) | 1 | 4 | 8 | 12 | 16 | 22 | 28 | 36 | 44 | 53 | 62 | 71 | 81 | 90 | 99 | 108 | 118 | 125
Patients Enrolled/Randomized (updated plan)
Clinical Development and Operations
Months | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26
Patients Enrolled (Planned) | 0 | 2 | 3 | 5 | 7 | 9 | 11 | 15 | 18 | 22 | 25 | 29 | 33 | 37 | 41 | 44 | 48 | 50
Patients Enrolled (Actual) | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 11 | 13 | 14 |  |  |  |  |  |  |  | 
Patient Screened(Planned) | 1 | 4 | 8 | 12 | 16 | 22 | 28 | 36 | 44 | 53 | 62 | 71 | 81 | 90 | 99 | 108 | 118 | 125
Patient Screened(Actual) | 0 | 0 | 1 | 2 | 12 | 22 | 50 | 77 | 108 | 118 |  |  |  |  |  |  |  | 
Cut-off date：12Dec2025 Total Screened：118
Total Enrolled：14
Total Screen Failure：53
In Screening 01：49
In Screening 02： 2
Screen failure rate：79%
Total Screened Planned = 125
Total Randomized Planned = 50

## Slide 26: 1438-0005 DLL3/CD3 epNEC dated on 12Dec 2025 (China recruitment status)
Chart: Patient Enrollment Status
| 45863 | 45894 | 45925 | 45955 | 45986 | 46016 | 46048 | 46079 | 46107 | 46138 | 46168 | 46199 | 46229 | 46260
Patients Enrolled (Actual) | 1 | 1 | 2 | 4 | 4 | 4
Patients Enrolled (Planned) | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5
Patient Screened(Actual) | 3 | 4 | 9 | 11 | 13 | 13
Patient Screened(Planned) | 1 | 2 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 13
Patients Enrolled/Randomized (updated plan)
Clinical Development and Operations
Months | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26
Patients Enrolled (Planned) | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5
Patients Enrolled/Randomized (Actual) | 1 | 1 | 2 | 4 | 4 | 4 |  |  |  |  |  |  |  | 
Patient Screened(Planned) | 1 | 2 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 13
Patient Screened(Actual) | 3 | 4 | 9 | 11 | 13 | 13 |  |  |  |  |  |  |  | 
Cut-off date：12Dec 2025 Total Screened：13
Total Enrolled：4
Total Screen Failure：8
In Screening 01：1
In Screening 02: 0
Screen failure rate：66.7%
Total Screened Planned = 13
Total Randomized Planned = 5

## Slide 27
Obrixtamig (DLL3/CD3 TcE) – 2L epNEC (Epi study)
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
27
Ph2, N=5
Aug 2025
CTA Review + EC + HGRAC + 1st SIV
Feb 2025
1st SIV
CTA Sub
Ph2-
1438-0005
Dareon-5
LPI
Jul 2026
Key results
Jan 2027
Jun 2027
NDA sub.
Jun 2028
NDA app.
Futility analysis
Q1 2025
Q1-Q2 2026
HA interaction
Analysis
Data collection
Dec 2025
Protocol + EC approval + Contract
Epi-Study
1438-0032
Key results
Jan 2027
Jun 2027
Report
Ph2, N=5
Aug 2025
CTA Review + EC + HGRAC + 1st SIV
Feb 2025
1st SIV
CTA Sub
Ph2-
1438-0005
Dareon-5
LPI
Jul 2026
Key results
Jan 2027
Jun 2027
NDA sub.
Jun 2028
NDA app.
Futility analysis
Q1 2026
Oct 2027
Publication
The contract was signed on 21Sep 2025.
The protocol was approved on 6Nov 2025.
We are here

## Slide 28: Obrixtamig (DLL3/CD3 TcE) – 1L SCLC (obrix+atezo+EP vs. atezo+EP)
28
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1
Ph3-
1438-0012
Dareon-Lung-1
SIV
Feb 2026
Ph3, N=670
Ph3, N=116 (Inc.TW20+HK2)
May 2025
CTA Review + EC + HGRAC + 1st SIV
1st SIV
Nov 2025
CTA Sub
LPI
Jun 2027
LPI
Jun 2027
Jan 2029
NDA sub.
May 2029
NDA app.
Feb 2029
NDA sub.
CTP was released on 7 Nov 2025 which was 2 weeks delayed than schedule .
Target to initiate SIV on 27 Feb 2026.
CTA was submitted on 28 Nov 2025. CTA approval is expected in early Mar 2026.
GCP submission to leading site completed on 3Dec2025.
This project does prospective testing and use the DLL3 as a stratification factor. FPI needs to wait clinical performance study(CPS) approval. Local Roche handles CPS submission.
Dec 2029
NDA app.
Ph3-
1438-0012
Dareon-Lung-1
Aug 2025
PreIND Sub
Key results
Q4 2028
Key results
Q4 2028
15 Sep 2025
FDA interaction
We are here

## Slide 29: Obrixtamig (DLL3/CD3 TcE) – 1L epNEC (obrix+EP vs. EP)
29
2025 |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph3-
1438-0011
Dareon-Nec-1
SIV
Jun 2026
Ph3, N=390
Ph3, N=~60
Jul 2026
CTA Review + EC + HGRAC + 1st SIV
1st SIV
Jan 2026
CTA Sub
LPI
Jul 2028
LPI
Jul 2028
Jun 2029
NDA sub.
Jul 2029
NDA sub.
Global team had a FDA meeting on 21 Nov 2025. No major concern was raised.
CTP was finalized on 11 Dec 2025.
CTA is under preparation. Global review was completed last week.
Team planned to submit CTA in mid of Jan 2026.
May 2030
NDA app.
Dec 2029
NDA app.
Ph3-
1438-0011
Dareon-Nec-1
CTA preparation
Aug 2025
Kick-off
21 Nov 2025
FDA interaction
Key results
Q1 2029
Key results
Q1 2029
We are here

## Slide 30: Brigimadlin (BI 907828, MDM2/p53)

## Slide 31: Brigimadlin (MDM2/p53 antago.) – Rollover study Development Plan
31
2024 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | … |  | 2034 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2-
1403-0032
Ph2
Ph2, N=2
Oct 2025
CTA Review + EC + HGRAC + 1st SIV
Apr 2025
1st SIV
CTA Sub
Ph2/3-
1403-0032
SIV
Dec 2024
LPC
Dec 2034
CTA was approved on 27 Aug 2025.
We are here

## Slide 32: Early Assets
CD137/FAP (BI 765179)
KRAS G12D inhibitor (BI 4015092)

## Slide 33: CD137/FAP (BI 765179)

## Slide 34
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | 
Ph1-1463.1b
HNSCC
CD137/FAP – HNSCC/NSCLC Development Plan
Global
China
Lean PoCP
(Jun 2024)
FPI
Mar 2025
Phase 1b N=60
Phase 1b N=6
Feb 2025
CTA Review + EC + HGRAC + 1st SIV
Aug 2024
1st SIV
CTA Sub
LPI
Jan 2026
May 2026
PoC
(Nov 2026)
Ph2/3
1L R/M HNSCC
Futility analysis
Aug 2025
Primary analysis
Ph1-1463.1b
NSCLC
Ph1b Expansion Cohort in 1L NSCLC
Sep 2030
NDA FA
Ph1-1463.1b
HNSCC
There will be a 5-6 months ahead per current re-baseline plan.
Futility Analysis is in preparation, which will be completed in Jan 2026.
NSCLC will be selected as the lead indication, and NSCLC development plan is in preparation .
LPI
May 2026
Ph 3 pivotal (combi pembro) 1L R/M HNSCC
Ph 3 pivotal (combi pembro) for 1L NSCLC
As of 8th Dec, total 7 allocated CN patients were all enrolled.
We are here

## Slide 35: 1463-0001 CD137/FAP 1L HNSCC dated on 2Dec 2025 (Global recruitment status)
Chart: Patient Enrollment Status
| 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326
Patients Enrolled (Actual) | 1 | 3 | 9 | 11 | 14 | 19 | 28 | 34 | 43
Patients Enrolled (orginial plan)
Patient Screened(Actual) | 4 | 6 | 12 | 15 | 20 | 31 | 44 | 53 | 60
Patient Screened(Planned) | 5 | 12 | 22 | 30 | 38 | 45 | 53 | 60 | 66 | 70 | 73 | 76 | 78 | 80 | 81 | 82 | 83 | 84 | 85 | 85
Patients Enrolled (Planed) | 1 | 3 | 6 | 9 | 10 | 11 | 15 | 19 | 23 | 25 | 29 | 33 | 37 | 41 | 45 | 49 | 50 | 51 | 55 | 60
Clinical Development and Operations
Months | Mar- 25 | Apr- 25 | May- 25 | Jun- 25 | Jul- 25 | Aug- 25 | Sep- 25 | Oct- 25 | Nov- 25 | Dec- 25 | Jan- 26 | Feb- 26 | Mar- 26 | Apr- 26 | May- 26 | Jun- 26 | Jul- 26 | Aug- 26 | Sep- 26 | Oct- 26
Screening (planned) | 5 | 12 | 22 | 30 | 38 | 45 | 53 | 60 | 66 | 70 | 73 | 76 | 78 | 80 | 81 | 82 | 83 | 84 | 85 | 85
Screening (Actual) | 4 | 6 | 12 | 15 | 20 | 31 | 44 | 53 | 60 |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 1 | 3 | 6 | 9 | 10 | 11 | 15 | 19 | 23 | 25 | 29 | 33 | 37 | 41 | 45 | 49 | 50 | 51 | 55 | 60
Randomized (Actual) | 1 | 3 | 9 | 11 | 14 | 19 | 28 | 34 | 43 |  |  |  |  |  |  |  |  |  |  | 
Total Screened Planned = 85
Total Randomized Planned = 60
Cut-off date：2Dec 2025
Total Screened：60
Total Enrolled：43
Total Screen Failed：14
In screening：3
Screen failure rate：24.6%
Acc. LPI

## Slide 36: 1463-0001 CD137/FAP 1L HNSCC dated on 2Dec 2025 (China recruitment status)
Chart: Patient Enrollment Status
| 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326
Patients Enrolled (Actual) | 2 | 3 | 3 | 3 | 5 | 5 | 7
Patients Enrolled (orginial plan)
Patient Screened(Actual) | 4 | 5 | 5 | 8 | 9 | 10 | 11
Patient Screened(Planned) | 1 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10 | 10 | 10
Patients Enrolled (Planed) | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6
Months | Apr- 25 | May- 25 | Jun- 25 | Jul- 25 | Aug- 25 | Sep- 25 | Oct- 25 | Nov- 25 | Dec- 25 | Jan- 26 | Feb- 26 | Mar- 26 | Apr- 26 | May- 26 | Jun- 26 | Jul- 26 | Aug- 26 | Sep- 26 | Oct- 26
Screening (planned) | 0 | 1 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 10 | 10 | 10
Screening (Actual) | 1 | 4 | 5 | 5 | 8 | 9 | 10 | 11 |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6
Randomized (Actual) | 0 | 2 | 3 | 3 | 3 | 5 | 5 | 7 |  |  |  |  |  |  |  |  |  |  | 
Total Screened Planned = 13
Total Randomized Planned = 6
Cut-off date：2Dec 2025
Total Screened：11
Total Enrolled：7
Total Screen Failed：4
In screening：0
Screen failure rate：36.4%
Announcement: we have successfully reached the planned recruitment target allocation for the 1463-0001 trial in China (Total planned enrollment: 6 subjects) by 4Nov 2025. And we strive to enroll more patients in China.

## Slide 37: STING Agonist (BI 1703880)

## Slide 38: Systemic STING ago. FR – NSCLC Development Plan
38
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 20230 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2-
1480-0002
SIV
Q2/3 2026
Ph2, N=80
Ph2, N=12, TBD
Aug 2026
CTA Review + EC + HGRAC + 1st SIV
Feb 2026
1st SIV
CTA Sub
LPI
H1 2028
LPI
H1 2028
Ph2-
1480-0002
Final CTP: 26th Jan 2026
CTA submission: Feb 2026, to try the “CTA 30 days” pathway.
We are here

## Slide 39: KRAS G12D inhibitor (BI 4015092)

## Slide 40: BI 4015092: eTPPs to Support Best-in-Class Potential in 1L mCRC
Indication & target patient population
Assumed standard of care at launch
In combo w/ cetuximab for therapy of pts with KRAS G12Dmut mCRC progressive on/after ≥1L prior systemic therapy, who have no effective SoC treatment option
  Very low life expectancy and QoL for patients with KRASmut mCRC
  No effective SoC treatment option in target population
Chemo + targeted drugs
Lonsurf + BEV, Fruquintinib, Lonsurf, Regorafenib
Pan(K)RAS inhibitors: tbd
Unmet need and value proposition
  Primary endpoint:
  mOS improved, HR≤ 0.7 vs. SoC
  Secondary endpoints:
  mPFS (≥6 m)
  DoR (≥8 m)
  ORR (≥ 45%) QoL
Efficacy
Chemo + targeted drugs:
Bevacizumab + FOLFIRINOX or FOLFOX
Pan(K)RAS inhibitors
In combo w/ 1L SoC (FOLFOX+beva) + cetux for the therapy of patients with mCRC with KRAS G12D mut, as determined by an FDA approved test
  Very low life expectancy and QoL for patients with KRASmut mCRC and need for a targeted oral therapy
  Primary endpoint:
  mOS Improved, HR≤ 0.7 vs. SoC
  mPFS(≥12m)
  Secondary endpoints:
  ORR (>65-70%) QoL
Benchmark
Efficacy
L± B (2-3L)
mOS - 10.8.m
mPFS - 5.6m
ORR – 6.1%
Fruquintinib
(3L+) mono:
mOS – 7.4m
mPFS – 3.7m
ORR: 4.7%
Lonsurf (3L+)
mOS – 7.2 m
mPFS – 2.4 m
ORR – 1.2%
TRIBE 1 Study FOLFIRI + BEV (1L)
mOS – 23.9m
mPFS – 9.5 m
ORR – 55%
TRIBE 2 Study mFOLFOX6 + BEV (1L)
mOS – 22.5m
mPFS – 9.8 m
ORR – 50%
CAIRO 5 Study FOLFOX + BEV (1L)
mOS – n/a
mPFS – 9 m
ORR – 33%
G12Ci sotorasib
(2L+ CRC combi) :
ORR: 26%
mPFS – 5.6m
G12Ci Adagrasib
(2L+ CRC combi) :
ORR: 34%
mPFS – 6.9m
mOS 15.9

## Slide 41: G12D Competitors _ focus on CRC + anti-EGFR | BI 4015092 will be a Late Follower
2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
ph1/1b mono /+daraxonrasib n=444
ph1/2 +cmab ±CT /+ 1L SoC PaC/CRC, n=1130
zoldonrasib +/- daraxonrasib,
+ all SOC combos, in 28 US sites
AA: accelerated approval ; FA: full approval; cmab: cetuximab; CRC: colorectal cancer; CT: chemotherapy; mono: monotherapy; NSCLC: non-small cell lung cancer; ORR: objective response rate; PDAC: pancreatic ductal adenocarcinoma; ww: worldwide clinical sites
ph1 mono / +cmab / +undiscl. n=410 in 27 sites ww
ph1 mono / +cmab / 1L+ SOC QW in 47 ww
ph1 mono / +cmab n=430 in 43 sites ww
ph1 mono / +cmab / + SOC n=466, 32 US/EU
Ph1/1b 2L+ mono / +CT/ + cmab n=570 in 52 US/EU
Other G12Di with only monotherapy trial (mostly CN only):
G12D degrader: ARV-806, ASP-4396, PT-0253 (PAQ Ther.)
DN022150, RNK08954, Jiangsu Hansoh HS-10529
Tyligand TSN1611, data at ASCO25, ORR 25%
Quilu Pharma QLC1101 and Hengrui’s HRS-4642: other combos
ph1 mono / +cmab / + SOC, n=308
ph1 mono / +cmab n=250 in 14 US
ph1 mono / +cmab n=240 in 5 US
ph1/2 mono / +cmab n=130 in 5 US
Boehringer Ingelheim BI 4015092
Revolution Medicines Zoldonrasib RMC-9805
AstraZeneca AZD022
Verastem VS-7375
Genentech GDC-7035
Astellas ASP3082
Incyte INCB161734 INCB186748
Eli Lilly LY3962673
Quanta QTX3034 QTX3046
today
no strong preclinical CRC data
AA (2L)
FA (1L)
FiH
FA (1L GI)
AA (2L)
AA (2L)
AA (2L)
potential AA if primary endpoint ORR (team assumptions)
1L Focus anticipated
no strong early (n=7) CRC data
closed 9/25 recruitment w 30 of 308 planned pts
closed 7/25 recruitment – no info
Fierce competition in the development of G12D specific KRAS inhibitors
Several competitors are at least two years ahead
Learning from G12C: swift move to early lines and combinations to increase efficacy
Differentiation / BIC profile is needed to succeed
Notes: RevMed FIH 5/22 > FA 2L PDAC 5/27 => 5y later with ph3 starting Oct24 = 2.5y after ph1 start
                FA 1L PDAC 2029 => 7y later
                start NSCLC and GI combo w G12Di – assuming standard timelines with ph3 starting after PCD of prior trial
                1H2024 -> FA 2032 => 8y later
                if assumed ph3 starting 2,5y after ph1/2 start -> ph3 start 2H26, 4,5y later FA => 1H2031
                BI FIH 2027 => FA 1L 6y later

## Slide 42: De-risking Clinical Development Investments | Proposed Inflection Points
1L: First line; 2L+: second line and above; AA: accelerated approval; Bev: bevacizumab; CRC: colorectal cancer; DE: dose escalation; FA: full approval; FiH: first in human; RDO: Randomized Dose Optimization; rPh3: randomized phase 3.
Preclinical data
⑤
①
③
②
④
Clinical data
Competitor data
Part of 1st CTP
Added via amendment
Separate trial
2026
2027
2030
2032
2031
2033
2034
DE solid tumors
DE 2L+ CRC
Pivotal Ph2 2L+ CRC
Single arm n = 90
Combination w/ cetuximab
DE 1L CRC
RDO 1L CRC
2 dose levels, n = 25 each
rPh3 1L CRC
vs. FOLFOX +/- Bev*
Pre-FiH IP
End of DE
Futility 1
PoC
2028
Futility 2
2029
backfill cohorts 2L+ CRC 2 dose levels, n = 20 each
RDO 2L+ CRC
2 dose levels, n = 25 each
Mono
Combo 2L+
Combo 1L
Combination w/ cetuximab + FOLFOX
AA (US)
FA (US)
zoldonrasib + daraxonrasib
FA: combo w/1L Soc CRC/PDAC
Q2/2032
*Risk: if any competitor receives FA in 1L CRC and becomes SoC before start of the BI 4015092 Ph3, head-to-head comparison may be required

## Slide 43: Timeline assessment for China integration plan
Ph I mono Dose Escalation
FiH
IP End of DE
2025
2026
2027
2028
2029/30
2031/32
Ph I 2L CRC combi + Cetuximab
IP Combo
Futility
PoC
AA (US)
We are here
Ph I mono Dose Escalation
Q1 2027
CTA Review + EC + HGRAC + 1st SIV
Q2/3 2026
1st SIV
CTA Sub
Global CTP + 1M
Ph I 2L CRC combi + Cetuximab
Pre-IND (TBD)
Q2 2026
Pre-IND
Sub
Global TDO + 1M
Two pending discussion topics:
Biomarker strategy
IMP shelf life

## Slide 44: PMS & RWE Studies

## Slide 45: Oncology TA Overview - IIS & ECR
Product | Indication | Study type (Study no.: FPI-LPO,CTR) | China Dev. Strat. | Current Status | Next Mile-stone | Key Updates | 
Afatinib 30mg & 40mg | Non-SqCC NSCLC Neoadjuvant | IIS (1200-0328): Jul.2020 - May.2022(stage 1), Apr.2025 (stage 2), Sep.2025 | China alone | Follow up (Apr 2026) | LPO (Apr 2026) | Enrollment completion on 9Feb2022 ,total 47 patients enrolled primary endpoint (stage 1) results has reached: Abstract has oral presented at 59th STS done in Jan 2023，Report accepted by Nature communications on 26July2023. DIM report submitted successfully in Aug2023 The investigator requested to extend study period from 30Sep 2025 to 30Sep 2026 and got CEC endorsement. Stage 2 follow-up is on track. | 
Afatinib 40mg | Chordoma | IIS (1200-0329): Oct.2022 – Dec.2025, Mar2026 | China alone | LPI (Jan 2025) | LPO (Dec 2025) | Study agreement fully signed, SIV:30Sep2022（sample size: 20) Actual recruit/ Planned recruit: 15/20 (by 31Jan 2025)​ FPI: 26Oct2022, LPI: 31Jan 2025 Follow-up is on track | 
Obrixtamig | NEC&SCLC | ECR（1438-0032） Jan 2026- Dec 2026, Oct 2027 or Mar 2026-May 2027, Mar 2028 | China alone | EC approval (12Nov 2025) | Data collection starts (Dec 2025) | Local CEC endorsed in Oct 2024. 1st round hybrid review was completed on 5Nov, and the final decision is "Eligible for Re-Submission. The kickoff meeting was held on 2Sep. The contract was signed on 21Sep. Got EC approval letter on 25Nov 2025. | 
Zongertinib | NSCLC | ECR(1479-0042) Dec2025-Apr 2026, Mar 2027 | China alone | Data collection starts (26Nov 2025) | Data collection ends (Feb 2026) | CEC endorsed in Dec 2024. Global released was completed on 24 Mar 2025.Kick off meeting was held on 24Apr. Protocol was approved in Aug. The contract was signed on 17Sep. Got EC approval letter on 26Nov 2025 | 
Zongertinib | NSCLC | IIS | China alone | CEC approval (Nov 2025) | PEC approval (Dec 2025) | CEC endorsed in Nov 2025. | 

## Slide 46: Zongertinib ECR Study timeline Acceleration Aim to has CTR ready by Jul 30, 2026
Milestones | Base case | Acc. case | Actual
Local CEC endorsement |  |  | 24 Dec
Proposal submitted to Lectrona | Mar 2025 | / | Jan 2025
Hybrid review and budget release | Jun 2025 | / | Mar 2025
Protocol submitted to Lectrona | Jul 2025 | / | June 2025
Protocol review & approval | Aug 2025 | Aug 2025 | 26Aug 2025
IRB/IEC approval | Sep 2025 | Sep 2025 | 24Nov 2025.
Contract | Nov 2025 | Nov (Oct) 2025 | 17Sep 2025
Data collection starts | Dec 2025 | Nov 2025 | 26Nov 2025
Data collection ends | Apr 2026 | Dec 2025 | 
Data analysis | Jun 2026 | Feb 2026 | 
Study report review & approval | Oct 2026 | 30July 2026 | 
Journal publication | Mar 2027 | / | 
Key results will be used to support NRDL submission aimed at June 2026

## Slide 47
Thank You!