## Slide 1: Portfolio Executive Committee (PEC) Review Meeting TA CRM
  CRM Team | 15-Dec-2025 | 20 min
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Part I: Follow-up Actions from the Previous PEC
PEC action log

## Slide 4: Part II: Update

## Slide 5
Dec 2024
Dec 2025
No change since last meeting

## Slide 6
CRM TA Achievements in 2025
1 BLA approval
1 BTD submission and approval (Global First!)
5 Pre-IND/EoPh II submission
6 CTA submission (1 global first CTA submission, 1 global first EC approval)
More HA interactions for strategy consultation and protocol amendment etc.
4 first site initiation
6 first subject screening
1 last subject completion
9 Investigator Meetings (face-to-face and online)

## Slide 7
CRM TA Milestones in 2026
CTA submission
    Avenciguat Ph III in GN (1366-0015)
    BI 3034701 (GGY2Ra.) Ph II in obesity (1507-0002)
    TRPC6i Ph II in DMD (1434-0019)
    BI 7703711 (SIRPa ant.) Ph IIb in MASH
Other HA interaction submission
    Survodutide in obesity for pediatric obesity, CMC pre-NDA, drug-device combination attribution definition
    Survodutide in MASH for NIT
    Survodutide in ALD
    BI 3802876 (FAP/TRAILR2) in MASH for PK backloading
First Site Initiation
    TENACITY (Metalyse in AIS >4.5h, 1123-0060)
    TRPC6i Ph III in pFSGS (1434-0017)
    TRPC6i Ph II in podocytopathies (1434-0027)
    TRPC6i Ph II in DMD (1434-0019)
    Avenciguat Ph III in GN (1366-0015)
    BI 3034701 (GGY2Ra.) Ph II in obesity (1507-0002)
    BI 7703711 (SIRPa ant.) Ph IIb in MASH
Last Subject Completion and Key results
    SYNCHRONIZE I, II, CVOT and CN

## Slide 8: TA CRM Portfolio Summary - PMS Studies
No change since last meeting

## Slide 9: TA Review Meeting Mature Product Overview Metabolism
Product | ·Indication | Study type/Global Status (Study no.: FPI-LPO, CTR) | China Dev. Strat. | Current status | Next Mile-stone | Key Updates | 
Jardiance (Empagliflozin) | HFrEF | China local NISed (1245.0291:Nov 2021-Dec 2030) | China alone | IEC approval | Feasibility analysis 1 (2026 Jan) | Current database enrolment delay: due to VBP, and drug switch situation HAI was sent on Jan 20th, feedback on May 14th Monthly meeting with PI to go through: latest database enrolment, issues etc. Total 1450 as of Nov2025. Plan to make an onsite visit to communicate the CDE submission file, feasibility analysis and latest database enrolment | 
Jardiance (Empagliflozin) | HFpEF | China local NISed (1245.0313:Q4 2022-Dec 2030) | China alone | IEC approval | Feasibility analysis 1 (2026 Jan) | Current database enrolment delay: due to VBP, and drug switch situation HAI was sent on Jan 20th, feedback on May 14th Monthly meeting with PI to go through: latest database enrolment, issues etc. Total 1450 as of Nov2025. Plan to make an onsite visit to communicate the CDE submission file, feasibility analysis and latest database enrolment | 

## Slide 10: Challenges and next step
Issues |  | Follow up action | Timeline
Study progress report to CDE | Lack of latest data | Urge PI to provide the data and review the content of CDE file Check the database on-site | Continuously communicate with PI Completed and found some issues
Current status of data | Available patients: 1,790 in the database; Unclear diagnosis record of HFrEF/HFpEF; Unstructured data including drug prescription and lab test ; Lack of follow-up data | Communicate with PI to improve database quality: Improve diagnosis record of HFrEF and HFpEF Need further data curation for unstructured data Improve follow-up visit record | Next on-site visit (expected within this week)
PI challenge | Negative collaboration | Further engagement with PI | Continuously

## Slide 11: Metalyse

## Slide 12: Metalyse Development Plan (TENACITY - Late time window indication)
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Jan 10
China
EU
Mar 27
Ph3, 30 sites, N=~339
Feb 2026
CTA Review + EC + HGRAC + 1st SIV
8 Aug 2025
1st SIV
CTA Sub
LPI
May 2028
NDA sub.
May 2029
NDA app.
Pre - IND
Jan 13
Ph3, N=1325
Feb 2026
CTA Review + 1st SIV
4 Nov 2025
1st SIV
CTA Sub
LPI
Jul 2027
CSR
Apr 2028
NDA sub.
Apr 2029
NDA app.
Pre - IND
May 28
today
Jul 2027
Nov 2027
DBL
(Key results +1W)
Jan 2028
CSR
Nov 2027
DBL
(Key results +1W)
Jan 2028

## Slide 13: Metalyse development plan
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
*
Global
TENACITY
Previous timeline
(~5m acceleration, TBC by global)
Ph3, N=1325 (China ~ 340pts), 18M
CTA Review + 1st SIV
1st SIV
Feb 2026
CTA-s
4 Nov 2025
LPI
Jul 2027
CSR
Jan 2028
EU NDA sub.
Apr 2028
EU NDA app.
Apr 2029
DBL
Nov 2027
Dec 2025
HAI（15+60WD)
TDO
IMP readiness for site shipment: Metalyse + Antiplatelet (Placebo) ~16 M
Dec 2025
Jan 2026
N=200 (9 M)
CTA Review
Apr 2026
Placebo IMPD Prep**
SIV
May 2027
CSR
Aug 2028
DBL
Jun 2028
NDA sub.*
Oct 2028
NDA app.
Oct 2029
LPI
Feb 2028
China
Join TENACITY as original plan and conduct a China blinding sister trial in parallel
EC -approval
CTA-s
Nov 2026
* China NDA submissions must include results from the TENACITY trial and sister trial.
**Placebo IMPD preparation timeline will be further evaluated once placebo candidate is selected.
*** Under evaluation by Global team
Base case
Apr 2027
EC-s
Feb 2027
Global Study Team requests China to achieve 25% enrollment in TENACITY (base/best cases)
HAI（15+60WD)
TDO
IMP readiness for site shipment: Metalyse + Antiplatelet (Placebo) ~12 M***
Dec 2025
Jan 2026
N=200 (9 M)
CTA Review
Apr 2026
Placebo IMPD Prep**
SIV
Jan 2027
CSR
Apr 2028
DBL
Feb 2028
NDA sub.*
Jun 2028
NDA app.
Jun 2029
LPI
Oct 202
EC -approval
CTA-s
Jul 2026
Best case
Dec 2026
EC-s
Oct 2026

## Slide 14: Key Update on Metalyse China Late Time Window (LTW) Indication Development
The decision from BUPC (11 Dec 2025)
Approval for the acceleration (by 5 months) of global Tenacity trial and the China sister trial involving 200 patients remains contingent upon the completion of a 30% cost reduction assessment – Based on informal communications, the global team will prioritize the budget for the China sister trial
Global recommends submitting the CTA directly, without pre-IND. (concerns: CDE may not give clear feedback; even mandate a full-power trial). The regulatory strategy for the China sister trial is pending CN RA agreement.

## Slide 15: Survodutide

## Slide 16
16
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2025 |  | 2028 |  |  |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2
Ph3-1404.44
FOS trial
Ph3-1404.44
FOS trial
FSS
19 Oct 2024
Mar2032
DBL
Accelerated sub/appr (F2/3): Oct 2027/Mar 2028
China
Global
Ph3-1404.64
FOS trial
Ph3-1404.64
FOS trial
Mar2024
EoP2 sub
May 2027
Interim analysis
FSS
19 Oct 2024
Jul 2029
DBL
MASH F2/3
Full sub/appr (F2-4): Sep2029/Feb 2030
Survodutide/MASH Development Plan
We are here
6 Aug
CTA s
18 Oct
CTA a
Mar
EoP2 s
FSS
17 Jan
2024
FSS
27 Jan
2024
LSR
Jan 2028
LSR
Dec 2027
Accelerated sub/appr (F2/3): Nov 2027/Aug 2028 (best&base)
Full sub/appr (F2-4): Oct 2029/Jul 2030 (best) Dec 2030 (base
Full sub/appr (F2-3): Nov 2032/Sept 2033 (best) Feb 2034 (base
By 1st Dec, LIEVERAGE had 168 (+27) pts screened, 8 (+4) randomized, 56 in screening; LIVERAGE-Cirrhosis had 60 (+9) pts screened, 21 (+2) randomized, 15 in screening.
Virtual NCI Lead Call was held on 3rd Dec.
Global submitted HAI on NIT related questions to FDA, meeting is planned on 9th Jan, 2026. Local kick-off is planned in late Dec.
Notes: CTA+EC+HGRAC+1st SIV=4.5m

## Slide 17: Projects/Studies with Red-Light – China Mainland
By 1 Dec, Totally 85 site engagement visits completed by BI China team. 18 sites planned to have engagement visit.
Under discussion on the collaborate site engagement visit between BI and PXL COLs upon tiers.
National Coordinate Investigator (NCI) lead call and NCIs call with Julian done on 3 Dec 2025
FTF IM planned in Mar-Apr 2026, under discussion for Study Recruitment Award
Global NCIs Call planned in Mid Dec 2025.
Site Engagement Plan
2 Recruitment Vendors to be involved for Liverage Cirrhosis in Mid Dec 2025 (Potential contribution to Liverage)
Finalized the narratives for NIT competitive study and plan to distribute to local BI & PXL team.
Global approved the CN Investigator Fee (IF)s increase and pt stipends increase, currently under implementation by PXL, expected to complete by end of Jan 2026.
Monthly BI CN-global exchanging meeting with Global team to discuss hurdles.
Global Pathologist and Vendor for biopsy review/collection training on 17Dec2025 for investigators and local pathologists to decrease the biopsy SF rate
Strengthen collaboration between local pathologists and investigators to minimize biopsy screen failures
Additional 10 sites for feasibility and selection, currently 1 new site selected.
Discussed potential sites for closure (current 7 sites) based on site performance and global guidance.
Other Mitigation Actions
Enrolment period of part one is announced to extend to Jul 2026 in late Oct 2025.
Recruitment is behind the plan in LIVERAGETM in China
By 1 Dec, CN has screened 168 (+27), randomized 8 (+4) [17 as planned for Nov], screen failed 105, in screening 56;
Main challenges for China including intensive competition, high SF rate, site performance low (no scr. >5 weeks since activation)
Status Update
Project/study
Survodutide, GCGR/GLP-1R dual agonist,
in MASH/1404-0044, PhIII
Red-light starts from
Aug 2025
Notes: Total Screened = 60
Total Randomized = 21
Total SF= 24
SFR= 53.33%

## Slide 18: LIVERAGE Medical Head Exchange meeting - Follow up action updates
Date: 21 Nov. 2025, 9:00-10:00 Topics: Status and key asks of LIVERAGE trial, 45min
 | Follow-up actions | Responsible person | Timeline | Status
1 | Need immediate action for formal release and detailed plan of EAP/Drug Voucher (e.g. the duration of drug compensation) from global | Elena | By the middle of Dec 2025 | EC endorsed the drug vouchers proposal, to provide Survo for 1 year in feasible countries. Next to discuss with global trial team on ICF wording and timeline.
2 | Solid global plan to support the Patients who progress to liver outcome events | Not discussed in the meeting, which need comments from Elena and Luiza by the end of Dec 2025. |  | Topic set in next Global-CN Catch-up (13 Jan, 2026)
3 | A centralized pathological training to be implemented ASAP | David and Katarina Vajdova | By the end of Dec 2025 | The training is planned on 17 Dec
4 | A direct case-by-case scientific discussion platform between local and central pathologists on biopsy cases with discrepancy for educational purpose only | Luiza | By Dec 2nd, 2025 | After the centralized pathological training completion, Luiza will follow-up with the central pathologists.
5 | Push Parexel(PXL) team to have the draft contract delivered to the sites of the increased CN Investigator Fee (IF)s and pt stipends | David | By the end of Nov 2025 | Verbal communication has been done by PXL team.
6 | Push Parexel(PXL) team to have the site contract implementation of the increased CN Investigator Fee (IF)s and pt stipends | David | By the end of Jan 2026 | Ongoing
7 | Global narrative on differentiation of Lilly SYNERGY-Outcome trial from the patient perspective | Luiza | By the middle of Dec 2025 | Narrative developed by study physician and commented by China team.
8 | Visit Prof. Vincent Wong of Prince of Wales Hospital to explore any experience could be implemented in China Mainland | Wei/Emma | By end of Dec 2025* | Visit was done on 3 Dec, visit summary was shared to both China and global teams.

## Slide 19: Projects/Studies with Red-Light - Taiwan
Recruitment is behind the plan in LIVERAGETM for both global and Taiwan;
Main challenges in Taiwan including high SF rate (Biopsy result failed), half sites not proactive enough with low performance (screen 1 patient per month), 2-3 sites have strict prescreen, PXL local team communication frequency and efficiency with sites are not satisfactory, etc.
Key issues
10 site booster visits have been conducted from Aug 2025 until now. Overall performance has increased which can be reflected in screening activities, however not reflected in enrollment, there is 1 potential subject might have high possibility to be enrolled in Dec 2025 or Jan 2026.
National Coordinator will be starting to connect sites for recruitment.
Have 1 additional sites proposed for feasibility and selection.
Discussion in increasing site staff fee for prescreening and retention activities.
Discussion in possibility of study information/materials posted in public area or shared to district hospital.
Discussion in possibility to held a local investigator meeting in Jan 2026, but may extend to Mar 2026 due to year end and upcoming Lunar New Year.
Mitigation actions
By 8 Dec, TW has screened 52(+32 since end of Aug, +10 since end of Nov), randomized 1 (+1 since end of Aug) [should enrolled 2 as planned], screen failed 31, in screening 20;
By 8 Dec, Totally 10 site engagement visits completed by BI Taiwan team. 1 site (TWN1) unavailable by Dec 2025 so planned to have further engagement in the near future.
PXL TWN Boost Recruitment Visit Plan submitted for Global PXL team approval.
Status update
Project/study
Survodutide, GCGR/GLP-1R dual agonist,
in MASH/1404-0044, PhIII
Red-light starts from
Aug 2025
Notes: Financial: 研究者费，提升，逐步审批中；患者补贴，已提交 (Biopsy proposed to Global； MRII, 内窥镜补贴提交global for review) ；患者关怀礼物，已提交，待审批；
Study design: will be discussed with global team
Site engagement
Pt screen number vendor onboard后变化
8 sites are Tier-1 (13); 13 sites are Tier-2 (19)
12 sites are Tier-3 (18); 4 sites are Tier-4 (4)
1 site is Only for Liverage Cirrhosis

## Slide 20: Projects/Studies with Yellow-Light – Hong Kong
Main challenges in Hong Kong including low performance of site for recruitment (screen 1 patient per month), high SF rate, etc.
Key issues
The booster recruitment visit for both sites were planned. HKG1 with the accompany of Dr. Zhang, Emma, Karen, Dave was conducted on 3 Dec 2025. HKG 2 planned in Q4 2025.
Pre-screening activities initiated at both sites, leading to the increase of recruitment (+2) in both of the studies.
Planned virtual site engagement meeting on 18Dec2025.
Plan to discuss the enrolment target increase for HKG1.
Plan to invite Hong Kong sites for FTF IM in Mar-Apr 2026.
Mitigation actions
By 01 Dec, HK has screened 11 (+2), randomized 1 [2 as planned], screen failed 5, in screening 5;
Status update
Project/study
Survodutide, GCGR/GLP-1R dual agonist,
in MASH/1404-0044, PhIII
Red-light starts from
Aug 2025
Notes: High SF Ratio: Currently no trends for SF ratio. 1 biopsy results, 1 patient decision, 2 others (using prohibited CM, and 1 upon investigator’s decision)

## Slide 21: 1404-0044 LiverageTM dated on 01Dec2025 (Global recruitment status)
Chart: Patient Enrollment Status(Global)
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508
Patients Enrolled/Randomized (Actual) | 0 | 1 | 1 | 1 | 3 | 8 | 18 | 35 | 52 | 78 | 108 | 143 | 194 | 226
Patients Enrolled/Randomized (Planned) | 0 | 1 | 1 | 1 | 3 | 7 | 17 | 31 | 50 | 77 | 106 | 135 | 180 | 232 | 290 | 347 | 401 | 463 | 520 | 580 | 639 | 700 | 811 | 925 | 1041 | 1152 | 1267 | 1382 | 1488 | 1603 | 1712 | 1800
Patient Screened(Actual) | 33 | 42 | 55 | 129 | 266 | 534 | 808 | 1145 | 1550 | 1986 | 2402 | 2800 | 3209 | 3629
Patient Screened(Planned) | 26 | 41 | 55 | 97 | 246 | 482 | 779 | 1110 | 1491 | 1977 | 2417 | 3028 | 3271 | 3530 | 3788 | 4076 | 4302 | 4584 | 4853 | 5180 | 5666 | 6191 | 6696 | 7235 | 7752 | 8255 | 8795 | 9314 | 9762 | 10135 | 10165 | 10165
Clinical Development and Operations
Months | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05
Screening (planned) | 26 | 41 | 55 | 97 | 246 | 482 | 779 | 1110 | 1491 | 1977 | 2417 | 3028 | 3271 | 3530 | 3788 | 4076 | 4302 | 4584 | 4853 | 5180 | 5666 | 6191 | 6696 | 7235 | 7752 | 8255 | 8795 | 9314 | 9762 | 10135 | 10165 | 10165
Screening (Actual) | 33 | 42 | 55 | 129 | 266 | 534 | 808 | 1145 | 1550 | 1986 | 2402 | 2800 | 3209 | 3629 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 1 | 1 | 1 | 3 | 7 | 17 | 31 | 50 | 77 | 106 | 135 | 180 | 232 | 290 | 347 | 401 | 463 | 520 | 580 | 639 | 700 | 811 | 925 | 1041 | 1152 | 1267 | 1382 | 1488 | 1603 | 1712 | 1800
Randomized (Actual) | 0 | 1 | 1 | 1 | 3 | 8 | 18 | 35 | 52 | 78 | 108 | 143 | 194 | 226 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 3629
Total Randomized = 226
Total SF=2690
SFR=92.25%
Total sample size for part 1 is 700, TCM sample size 12% of 700, ~84
Notes: SF Reason: Biopsy (22%), FAST/VCTE/Fibro (11%), AST (9%)

## Slide 22: 1404-0044 LiverageTM dated on 01Dec2025 (China recruitment status)
Chart: Patient Enrollment Status (China mainland)
| 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 8
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 11 | 17 | 24 | 30 | 36 | 43 | 50 | 57 | 64 | 70 | 79 | 89 | 98 | 107 | 117 | 126 | 134 | 144 | 153 | 159
Patient Screened(Actual) | 0 | 1 | 1 | 3 | 12 | 19 | 37 | 61 | 83 | 109 | 141 | 168
Patient Screened(Planned) | 0 | 0 | 1 | 3 | 9 | 17 | 33 | 60 | 81 | 186 | 226 | 273 | 319 | 366 | 405 | 452 | 492 | 538 | 598 | 658 | 717 | 784 | 843 | 903 | 969 | 1029 | 1089 | 1136 | 1136 | 1136
Clinical Development and Operations
Total sample size for part 1 is 700, TCM sample size 12% of 700, ~84
Months | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05
Screening (planned) | 0 | 0 | 0 | 0 | 1 | 3 | 9 | 17 | 33 | 60 | 81 | 186 | 226 | 273 | 319 | 366 | 405 | 452 | 492 | 538 | 598 | 658 | 717 | 784 | 843 | 903 | 969 | 1029 | 1089 | 1136 | 1136 | 1136
Screening (Actual) | 0 | 0 | 0 | 1 | 1 | 3 | 12 | 19 | 37 | 61 | 83 | 109 | 141 | 168 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 11 | 17 | 24 | 30 | 36 | 43 | 50 | 57 | 64 | 70 | 79 | 89 | 98 | 107 | 117 | 126 | 134 | 144 | 153 | 159
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 168
Total Randomized = 8
Total SF=105
SFR=92.92%
Notes: SF Reason: Biopsy results 44%, Fibroscan data 20%, Lab results 16%

## Slide 23: 1404-0044 LiverageTM dated on 1Dec2025 (Taiwan recruitment status)
Chart: Patient Enrollment Status (Taiwan)
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 12 | 15 | 18 | 22 | 25 | 29 | 32 | 35 | 38 | 41
Patient Screened(Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 8 | 13 | 20 | 34 | 40 | 40 | 50
Patient Screened(Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 13 | 20 | 39 | 46 | 52 | 52 | 59 | 66 | 72 | 72 | 92 | 112 | 139 | 159 | 185 | 205 | 225 | 252 | 272 | 293 | 293 | 293 | 293
Clinical Development and Operations
Months | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05
Screening (planned) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 13 | 20 | 39 | 46 | 52 | 52 | 59 | 66 | 72 | 72 | 92 | 112 | 139 | 159 | 185 | 205 | 225 | 252 | 272 | 293 | 293 | 293 | 293
Screening (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 8 | 13 | 20 | 34 | 40 | 50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 12 | 15 | 18 | 22 | 25 | 29 | 32 | 35 | 38 | 41
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 50
Total Randomized = 1
Total SF=24
SFR=96%

## Slide 24: 1404-0044 LiverageTM dated on 1Dec2025 (Hong Kong recruitment status)
Chart: Patient Enrollment Status (Hong Kong)
| 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 8 | 10 | 11 | 13 | 15 | 16 | 18 | 20 | 21
Patient Screened(Actual) | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 5 | 5 | 6 | 9
Patient Screened(Planned) | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 5 | 5 | 12 | 12 | 12 | 19 | 19 | 26 | 26 | 26 | 33 | 48 | 55 | 70 | 84 | 91 | 106 | 120 | 128 | 142 | 150 | 150
Clinical Development and Operations
Months | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05
Screening (planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 5 | 5 | 12 | 12 | 12 | 19 | 19 | 26 | 26 | 26 | 33 | 48 | 55 | 70 | 84 | 91 | 106 | 120 | 128 | 142 | 150 | 150
Screening (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 5 | 5 | 6 | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 8 | 10 | 11 | 13 | 15 | 16 | 18 | 20 | 21
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 11
Total Randomized = 1
Total SF=5
SFR=83.33%
Notes: 1 biopsy results, 1 Fibroscan, 1 patient decision, 2 others (using prohibited CM, and 1 upon investigator’s decision)

## Slide 25: 1404-0064 LiverageTM - Cirrhosis dated on 1Dec2025 (Global recruitment status)
Chart: Patient Enrollment Status (Global)
| 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692 | 46722 | 46753 | 46784 | 46813
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 25 | 57 | 106 | 148 | 215 | 281 | 322
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 1 | 2 | 6 | 14 | 26 | 43 | 71 | 112 | 156 | 206 | 259 | 310 | 364 | 424 | 478 | 541 | 605 | 660 | 723 | 787 | 848 | 903 | 968 | 1036 | 1090 | 1155 | 1212 | 1282 | 1340 | 1402 | 1463 | 1525 | 1587 | 1590 | 1638 | 1691 | 1740 | 1793
Patient Screened(Actual) | 0 | 1 | 2 | 5 | 21 | 52 | 128 | 265 | 447 | 591 | 740 | 899 | 1077 | 1252
Patient Screened(Planned) | 0 | 0 | 0 | 4 | 12 | 26 | 48 | 82 | 132 | 208 | 294 | 398 | 496 | 598 | 714 | 830 | 940 | 1066 | 1184 | 1298 | 1428 | 1556 | 1676 | 1794 | 1916 | 2050 | 2174 | 2294 | 2406 | 2540 | 2652 | 2782 | 2906 | 3030 | 3156 | 3180 | 3180 | 3180 | 3180 | 3180 | 3180 | 3180
Clinical Development and Operations
Months | 2024-10 | 2024-11 | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11 | 2027-12 | 2028-01 | 2028-02 | 2028-03
Screening (planned) | 0 | 0 | 0 | 4 | 12 | 26 | 48 | 82 | 132 | 208 | 294 | 398 | 496 | 598 | 714 | 830 | 940 | 1066 | 1184 | 1298 | 1428 | 1556 | 1676 | 1794 | 1916 | 2050 | 2174 | 2294 | 2406 | 2540 | 2652 | 2782 | 2906 | 3030 | 3156 | 3180 | 3180 | 3180 | 3180 | 3180 | 3180 | 3180
Screening (Actual) | 0 | 1 | 2 | 5 | 21 | 52 | 128 | 265 | 447 | 591 | 740 | 899 | 1077 | 1252 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 1 | 2 | 6 | 14 | 26 | 43 | 71 | 112 | 156 | 206 | 259 | 310 | 364 | 424 | 478 | 541 | 605 | 660 | 723 | 787 | 848 | 903 | 968 | 1036 | 1090 | 1155 | 1212 | 1282 | 1340 | 1402 | 1463 | 1525 | 1587 | 1590 | 1638 | 1691 | 1740 | 1793
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 25 | 57 | 106 | 148 | 215 | 281 | 322 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 1252
Total Randomized = 322
Total SF= 581
SFR= 64.34%

## Slide 26: 1404-0064 LiverageTM - Cirrhosis dated on 01Dec2025 (China recruitment status)
Chart: Patient Enrollment Status (China mainland)
| 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 10 | 13 | 18 | 19 | 21
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 10 | 13 | 18 | 19 | 21 | 26 | 30 | 35 | 39 | 44 | 48 | 53 | 58 | 62 | 67 | 71 | 76 | 80 | 85 | 89 | 94 | 99 | 103 | 108 | 112 | 117 | 121 | 126 | 131
Patient Screened(Actual) | 0 | 0 | 0 | 1 | 7 | 11 | 23 | 32 | 36 | 40 | 50 | 60
Patient Screened(Planned) | 0 | 0 | 0 | 1 | 7 | 11 | 24 | 33 | 37 | 41 | 51 | 61 | 70 | 79 | 90 | 101 | 111 | 121 | 131 | 141 | 151 | 161 | 171 | 180 | 190 | 200 | 207 | 215 | 225 | 235 | 243 | 253 | 261 | 271 | 273 | 273
Clinical Development and Operations
Months | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11
Screening (planned) | 0 | 0 | 0 | 1 | 7 | 11 | 24 | 33 | 37 | 41 | 51 | 61 | 70 | 79 | 90 | 101 | 111 | 121 | 131 | 141 | 151 | 161 | 171 | 180 | 190 | 200 | 207 | 215 | 225 | 235 | 243 | 253 | 261 | 271 | 273 | 273
Screening (Actual) | 0 | 0 | 0 | 1 | 7 | 11 | 23 | 32 | 36 | 40 | 50 | 60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 10 | 13 | 18 | 19 | 21 | 26 | 30 | 35 | 39 | 44 | 48 | 53 | 58 | 62 | 67 | 71 | 76 | 80 | 85 | 89 | 94 | 99 | 103 | 108 | 112 | 117 | 121 | 126 | 131
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 10 | 13 | 18 | 19 | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 60
Total Randomized = 21
Total SF= 24
SFR= 53.33%

## Slide 27: 1404-0064 LiverageTM - Cirrhosis dated on 01Dec2025 (Taiwan recruitment status)
Chart: Patient Enrollment Status (Taiwan)
| 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 22 | 23 | 24 | 25 | 26 | 28 | 29 | 30 | 31 | 33
Patient Screened(Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 9 | 10 | 14 | 17
Patient Screened(Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 10 | 12 | 14 | 16 | 18 | 22 | 24 | 26 | 28 | 30 | 34 | 36 | 38 | 40 | 42 | 46 | 48 | 50 | 52 | 53 | 58 | 60 | 62 | 64 | 66 | 66
Clinical Development and Operations
Months | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11
Screening (planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 10 | 12 | 14 | 16 | 18 | 22 | 24 | 26 | 28 | 30 | 34 | 36 | 38 | 40 | 42 | 46 | 48 | 50 | 52 | 53 | 58 | 60 | 62 | 64 | 66
Screening (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 9 | 10 | 14 | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 22 | 23 | 24 | 25 | 26 | 28 | 29 | 30 | 31 | 33
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 17
Total Randomized = 2
Total SF= 9
SFR=81.81%

## Slide 28: 1404-0064 LiverageTM - Cirrhosis dated on 1Dec2025 (Hong Kong recruitment status)
Chart: Patient Enrollment Status (Hong Kong)
| 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 6 | 6 | 7 | 8 | 9 | 9 | 9 | 10 | 10 | 11 | 12 | 13 | 13 | 13 | 14 | 15 | 16 | 17
Patient Screened(Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 6 | 7 | 7
Patient Screened(Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 7 | 7 | 7 | 9 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 28 | 30 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 44 | 44
Clinical Development and Operations
Months | 2024-12 | 2025-01 | 2025-02 | 2025-03 | 2025-04 | 2025-05 | 2025-06 | 2025-07 | 2025-08 | 2025-09 | 2025-10 | 2025-11 | 2025-12 | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12 | 2027-01 | 2027-02 | 2027-03 | 2027-04 | 2027-05 | 2027-06 | 2027-07 | 2027-08 | 2027-09 | 2027-10 | 2027-11
Screening (planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 7 | 7 | 7 | 9 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 28 | 30 | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 44 | 44
Screening (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 6 | 7 | 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Randomized (Planned) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 6 | 6 | 6 | 7 | 8 | 9 | 9 | 9 | 10 | 10 | 11 | 12 | 13 | 13 | 13 | 14 | 15 | 16 | 17
Randomized (Actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total Screened = 7
Total Randomized = 5
Total SF= 0
SFR= 0%
1 ETD

## Slide 29
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
Global
China
Dec 2027
US approval
Dec 2026
NDA sub
SYNCHRONIZE-1
SYNCHRONIZE-2
SYNCHRONIZE-CVOT
Jun/LSR
Obesity w/o T2DM, N=726
Aug/LSR
30Apr/TLR
Obesity with CV risk, N=5534
25Nov/FSS
Obesity with T2DM, N=755
27 Mar2026/DBL
Jul 2028
CN NDA App
(base case)
Jan 2027
CN NDA sub
Jul/LSR
Aug/LSR
CTA + EC + HGRAC + 1st SIV (5M)
SYNCHRONIZE-1
SYNCHRONIZE-2
SYNCHRONIZE-CVOT
CTA Sub
25Aug
EoP2
29 Dec
2022
Obesity w/o T2DM, N=64/726
Obesity with CV risk, N=174+43 (incl TW&HK)/5534
31Jan/FSS
Obesity with T2DM, N=78/755
Mar/CDE feedback
25Apr/
EoP2 meeting
CTA Sub
15Sep
6Feb/FSS
Jul/LSS
Pre-IND
SYNCHRONIZE-CN
13 Mar/DBL
(79W)
31 May
Obesity, BMI 24/28 N=307 (56 for MRI-PDFF)
CN PK-1404.13
MRD study design
CTA Sub
18 Jan
Jul 2024
/SIV
Sept 2024/LSS
20 Jun 2025/DBL
Jan 2026
CTR
15 May2026/DBL
27Mar2026/DBL
30Nov
/CTA appr
30Nov/
CTA appr
Apr 2028
CN NDA App
(best case)
6Feb/FSS
17Jan/FSS
Survodutide/Obesity Development Plan
TA CEC Portfolio Update| ONLY FOR INTERNAL USE
CTA + EC +HGRAC + 1st SIV (6M)
N=30
We are here
15 May2026/DBL
Patient retention is still the focus
Communication plan are under development
Final feedback from CDE Clin-Pharm on new proposal of BE studies for supporting bridging PFS to Pen (whether conducting BE studies only on the highest and lowest strength is sufficient to support bridging for all strengths). BI Clin-Pharm evaluated as no problem considering dose proportional PK profile and same concentration ratio for all strength between PFS and PEN.

## Slide 30: CN Participant Discontinuation in SYNCHRONIZE trials (Cut off Date for CN: 4-Dec-2025)
 |  | N | Discontinued prematurely n (%) | PSD* n (%)
SYNCHRONIZE-1 | Global | 725 | 258 (35.6%) | 74(10.21%)
 | China | 64 | 14 (21.8%) | 0 (1 potential LFU)
SYNCHRONIZE-2 | Global | 752 | 248 (32.9%) | 38(5.05%)
 | China | 77 | 20 (26%) | 0
SYNCHRONIZE-CVOT | Global | 5510 | 2057 (37.4%) | 269 (4.9 %)
 | China | 174 | 53 (30%) | 0
SYNCHRONIZE-CN | China | 306 | 57 (18.6%) | 0
* follow-up lost + ICF withdraw;
LFU=lost follow-up

## Slide 31: VicaEmpa

## Slide 32: VicaEmpa/CKD Development Plan (both global and local)
 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2025 |  | 2029 |  | 2030 | 2027 | 2031 | 2032
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 |  | 
DBL: Sep, 2027
Approval: Aug, 2028
FSS: Aug, 2025
Approval: Jan, 2029
Approval(Base): Jul.2029
CTA-EC-HGRAC-1st SIV
(Hybrid-Oxford University)
Ph-III: 1378-0006
Trial duration on base case scenario
FSS: Jun, 2025
DBL: Jan, 2027
Ph-II: 1378-0023
CTA
FSS: Sep, 2025
CTA: Mar, 2025
DBL: Sep, 2027
DBL: Jan, 2027
22 patients randomised，26 sites initiated
12 patients randomized in China
CTP3.0 submitted on 24 Nov through HAI

## Slide 33: VicaEmpa/HF Development Plan (both global and local)
 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2025 |  | 2029 |  | 2030 | 2027 | 2030 | 2031
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 |  | 
FSS: Jul, 2025
DBL: Mar, 2029
Approval: Jan, 2030
Approval: Jun, 2030
CTA-EC-HGRAC-1st SIV
Ph-III: 1378-0018
Trial duration on base case scenario
CTA
(Hybrid-IQVIA)
CTA: Mar, 2025
FSS: Oct, 2025
DBL: Jul, 2028
Approval: Feb, 2029
Approval: Sep, 2029
Approval(Base): Mar, 2030
Ph-III: 1378-0020
(Hybrid-IQVIA)
DBL: Jul, 2028
Approval(Base):
Aug, 2030
339(vs. 197 planned) patients randomized in China, and similar momentum observed at global level (3,607 vs. 3,559 planned)
IM was held on 23rd Nov, 2025
11(vs. 1) patients randomised in China, and 268(vs. 117) patients randomized globally
DBL: Mar, 2029

## Slide 34: VicaEmpa/CVRR Development Plan (both global and local)
 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  | 2025 |  | 2029 |  | 2030 | 2027 | 2030 | 2031
 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 |  | 
CTA-EC-HGRAC-1st SIV
Trial duration on base case scenario
DBL: Jan, 2030
Approval: Mar, 2031
Approval: Apr, 2031
Ph-III: 1378-0041
EASi-PROTKT
CTA
CTA: 31 May,2025
FSS: Jul, 2025
28(vs. 12 planned) patients randomized in China, and similar momentum observed at global level (479 vs. 100 planned)
FSS: Sep ,2025
DBL: Jan, 2030
Approval(Base):
Jun, 2031

## Slide 35: Oxford’s feedback on site activation and patient screening
26 sites are open and a total of 40 are expected to open by their Spring festival (starts 17th Feb). The target is 60, with 57 sites selected already (and 56 with local submissions in process).
Month | Site Activations
Aug | 9
Sep | 3
Oct | 0
Nov | 12
Dec (until 12 Dec) | 2
Total | 26
Site activation status quo
Lower screening rate in cardio sites
Site activation status and prospects
 |  | Screening rate at sites since opening (Participants per week) | 
Clinic type | Number of sites | Mean ± SD | Median (Q1-Q3)
Cardiology | 7 | 0.7 ± 0.4 | 0.4 (0.4-1.0)
Nephrology/endocrinology | 10 | 1.4 ± 0.7 | 1.2 (0.9-1.8)
China is the first region to open cardiology sites at any scale, and the feedback is that finding patients is challenging for the cardiologists.
This is reportedly as many patients are ineligible as there is a desire to use MRAs (even in non-diabetic CKD). Screening is 2-3x faster are nephrology sites vs cardiology sites.

## Slide 36: Response to recruitment and site activation plan
No detailed recruitment plan was given;
The current plan by Oxford is to let recruitment continue until at least 1,100 patients are randomized.
According to Martina, it is expected the overall delay will be as long as 6 months, this also adds time for China for recruitment, plus their plan to allow China to get to at least 1,100 pts. in any case.

## Slide 37: 1378-0020: China Recruitment Progress
Randomization
Chart: Randomization: Actual vs. Projection
| Dec-24 | Jan-2025 | Feb-2025 | Mar-2025 | Apr-2025 | May-2025 | Jun-2025 | Jul-2025 | Aug-2025 | Sep-2025 | Oct-2025 | Nov-2025 | Dec-2025 | Jan-2026 | Feb-2026 | Mar-2026 | Apr-2026 | May-2026 | Jun-26
projection | 0 | 4 | 13 | 30 | 49 | 70 | 90 | 112 | 134 | 155 | 176 | 197 | 219 | 241 | 260 | 282 | 303 | 325 | 341
Actual | 1 | 11 | 28 | 72 | 118 | 153 | 191 | 229 | 254 | 284 | 304 | 339
actual by month | 1 | 10 | 17 | 44 | 46 | 35 | 38 | 38 | 25 | 30 | 20 | 35

## Slide 38: 1378-0020 global recruitment progress
Revised targets from Jun.2025 onwards
Chart: 
| Jun-2024 | Jul-2024 | Aug-2024 | Sep-2024 | Oct-2024 | Nov-2024 | Dec-2024 | Jan-2025 | Feb-2025 | Mar-2025 | Apr-2025 | May-2025 | Jun-2025 | Jul-2025 | Aug-2025 | Sep-2025 | Oct-2025 | Nov-2025 | Dec-2025 | Jan-2026 | Feb-2026 | Mar-2026 | Apr-2026 | May-2026 | Jun-2026
Projections | 1 | 2 | 15 | 35 | 69 | 131 | 252 | 430 | 639 | 908 | 1202 | 1533 | 1778 | 2121 | 2478 | 2831 | 3198 | 3559 | 3928 | 4296 | 4636 | 5004 | 5364 | 5731 | 6000
Actuals | 0 | 5 | 32 | 63 | 110 | 186 | 335 | 482 | 717 | 1029 | 1334 | 1636 | 1974 | 2277 | 2616 | 2925 | 3279 | 3607

## Slide 39: 1378-0018: China Recruitment Progress
Randomization
Chart: 
| Jun-2025 | Jul-2025 | Aug-2025 | Sep-2025 | Oct-2025 | Nov-2025 | Dec-2025 | Jan-2026 | Feb-2026 | Mar-2026 | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027 | Feb-2027 | Mar-2027 | Apr-2027 | May-2027 | Jun-2027 | Jul-2027 | Aug-2027 | Sep-2027 | Oct-2027 | Nov-2027 | Dec-2027 | Jan-2028
China Subjects Enrolled Targeted | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 17 | 29 | 44 | 59 | 75 | 90 | 106 | 122 | 137 | 153 | 168 | 183 | 199 | 213 | 229 | 244 | 260 | 275 | 291 | 306 | 321 | 337 | 352 | 368 | 373
China Subjects Enrolled Actual | 0 | 0 | 0 | 0 | 1 | 11

## Slide 40: 1378-0018 global recruitment progress
Chart: 
| Jun-2025 | Jul-2025 | Aug-2025 | Sep-2025 | Oct-2025 | Nov-2025 | Dec-2025 | Jan-2026 | Feb-2026 | Mar-2026 | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027 | Feb-2027 | Mar-2027 | Apr-2027 | May-2027 | Jun-2027 | Jul-2027 | Aug-2027 | Sep-2027 | Oct-2027 | Nov-2027 | Dec-2027 | Jan-2028
global projection randomization | 1 | 8 | 17 | 32 | 63 | 117 | 205 | 313 | 431 | 581 | 748 | 925 | 1091 | 1268 | 1441 | 1609 | 1785 | 1955 | 2128 | 2303 | 2462 | 2636 | 2808 | 2985 | 3149 | 3323 | 3501 | 3670 | 3846 | 4016 | 4192 | 4200
global actual randomization | 1 | 9 | 17 | 67 | 158 | 268

## Slide 43: Projects/Studies with Red-Light
Continuously delayed timeline, and shortened recruitment window left
Fewer subjects and endpoint events are expected, potentially impacting Chinese subgroup result and indication approval
Monthly regular catch-up with CTL is ongoing to monitor trial progress
Global Medical and global brand team have been fully informed, and aware of the current situation, and will also look into the delay issue.
FSS(First Subject Screen) took place on 24th Aug, 2025, while no subject was randomized yet. Overall delay is ~ 4 months vs. original timeline(30th Apr, 2025)
13 sites activated with 38 patients screened, while no patient randomized yet
LSR(Last Subject Randomised) was still scheduled on 30th Aug, 2026
A global delay also occurred, and except Taiwan(88), no East Asian countries has randomized patients yet
Project/study
VicaEmpa, ASi+SGLT-2i,
in CKD/EASi-KIDNEY, Ph-III
Red-light starts from
Apr 2025
Key issues
Mitigation actions
Status update

## Slide 44: Early Assets

## Slide 45: Projects/Studies with Red-Light
RoFD decision pending since Apr due to undetermined global development strategy
Key issues
Front-loading of certain trial start-up activities including CTP development, vendor setup and site selection to accelerate the trial initiation as soon as RoFD is released
Mitigation actions
RoFD is planned in Nov. TDO is final and site selection is ongoing.
Status update
Project/study
Avenciguat (sGCa.) in GN/1366-0015, PhIII
Red-light starts from
Jul. 2025

## Slide 46: Avenciguat (sGCa.), GN Development Plan
FSS: first subject screened; LSS: last subject screened; AA: accelerated approval; CA: conditional approval; fSIV: first site initiation
GN: glomerulonephritides; IgAN: IgA nephropathy; FSGS: focal segmental glomerulosclerosis; MN: membranous nephropathy;
sGCa.: soluble guanylate cyclase activator
2026
564 days
65 days
480 days
175 days
Today
260 days
2029
Global
1366-0015
Ph III
China
1366-0015
Ph III
2026
2027
2028
2029
1/5/26
final CTA package
4/9/26 - 6/7/28
global FSS to LSS
2/5/26 - 5/6/26
CTA sub - app
8/5/26 - 6/7/28
fSIV - LSS
futility analysis DBL
2/3/27
10/24/28 - 6/26/29
NDA sub. - app. for AA
interim analysis DBL
Jul 5
Nov 24 - Nov 24
NDA sub. - app. for CA (best)
RoFD still pending; avenciguat townhall meeting scheduled on 19 Dec for update on HPBU EC meeting
CTA under preparation with planned submission on 05-Feb-2026
Final patient allocation confirmed: China mainland 76, Taiwan 21, Hongkong 8
1000 GN patients
100 GN patients
300 IgAN patients
105 GN patients (76 mainland, 21 TW, 8 HK)

## Slide 47: Avenciguat (sGC act.) in GN Ph III (1366-0015) trial design
Primary Endpoint for accelerated approval:
Change in proteinuria (UPCR based on first morning void) from randomization to month 9
Primary Endpoint for full approval:
total annualized eGFR slope from baseline to end of treatment (at least 24 months)
Key Inclusion criteria
≥12 years and 40 kg
eGFR ≥20 ml/min/1.73m2
UPCR >750 mg/g
Biopsy proven GN
On optimized/maximally tolerated RAASi, SGLT2i, MRA and ERA for ≥8 weeks
oral immunosuppressives on stable dose for ≥3 months
Key Exclusion criteria
rapid progressive kidney disease as measured by eGFR loss ≥ 50% over a period of 3 months prior to Screening
History of kidney transplant or planned kidney transplant
Systolic blood pressure <100 mmHg
i.v. immunosuppressive treatment ≤6 months

## Slide 48: BI 764198 (TRPC6i), FSGS Development Plan
2025
65 days
2031
495 days
399 days
174 days
262 days
Global
1434-0017
Ph III
China
1434-0017
Ph III
Today
2025
2026
2027
2028
final CTA package
9/30/25
10/17/25 - 1/16/26
CTA sub-app
12/3/25 - 10/27/27
global FSS - LSS
4/16/26 - 10/27/27
fSIV - LSS
2029
2030
2031
key results
5/1/30
8/30/30 - 5/1/31
NDA sub - app
interima analysis
5/10/29
9/30/2030 - 9/30/2031
NDA sub- app
261 days
Jan 1 - Dec 31
China PK study (1434-0025)
N=286
N=28 (mainland 18, TW 8, HK 2)
RoFD endorsed on 18 Nov
BTD application approved on 26 Nov (global first)
Ph III preparation:
  CTA submission occurred on 17 Oct; clinical queries received on 10 Dec
  Global first EC approval received at 广东省人民医院
China Ph I PK study high level design received approval from global CPS committee
FSS: first subject screened; LSS: last subject screened; FSGS: focal segmental glomerulosclerosis; TRPC6i: transient receptor potential channel 6 inhibitor

## Slide 49: Current trial design prior to potential new design elements
TRPC6i in pFSGS | CONFIDENTIAL
Screening
(week -4)
Randomization
(Day 1)
Matching Placebo once daily on top of SoC* (n=143)
1:1
Up to 4 weeks
4 weeks
Key Inclusion Criteria
≥12 years and 40 kg
eGFR ≥25 ml/min/1.73m2
UPCR >1,500 mg/g
diagnosis of
  Biopsy-proven primary FSGS OR
  FSGS related to a mutation in the TRPC6 gene
Optimized/maximally tolerated RAASi, SGLT2i, MRA, ERA, GLP1Ra for ≥8 weeks prior to screening
oral immunosuppressives on stable dose for ≥12 weeks prior to screening
patients on oral glucocorticoids have to be at a dose ≤10 mg/d prednisolone (or equivalent) 4 week prior to screening
Key Exclusion Criteria
Known mongenic or syndromic causes of FSGS (except TRPC6 gene mutation)
Rapid progressive kidney disease as measured by eGFR loss ≥ 50% over a period of 3 months prior to Screening
History of kidney transplant or planned kidney transplant
Clinical or histological evidence of secondary FSGS
i.v. immunosuppressive treatment ≤6 months prior to screening
Glucocorticoid naïve patients or re-exposure to high dose due to disease relapse (if Glucocorticoids and indicated and tolerated)
Screening Period
Follow-up
Period
BI764198 20 mg once daily on top of SoC* (n=143)
104 weeks
Primary Endpoint
Percentage change in 24-hour urinary protein-to-creatinine ratio (UPCR, measured in g/g) from baseline to Week 104
Visit 8
(Week 52)
End of Treatment
(Week 104)
End of Study
(Week 108)
Key 2ary Endpoint Family
Change in eGFRcys measured in ml/min/1.73m² from baseline to Week 104
Treatment response, defined as 24-hr UPCR <1.0 g/g at Week 104
Other 2ary Endpoints (all measured at wk 104)
treatment response, defined as 24-hr UPCR <1.0 g/g and eGFRcys ≥85% and no treatment failure during trial
complete remission, defined as 24-hr UPCR <0.3 g/g
change from baseline across Clinical Outcome Assessment (COA) KDQOL-36
Change from baseline across disease-specific COA NS-SIM-PRO at

## Slide 50: BI 764198 (TRPC6i), Podocytopathies Development Plan
2025
69 days
2028
64 days
381 days
289 days
Global
1434-0027
Ph II
China
1434-0027
Ph II
Today
2025
2026
2027
12/12/25 - 3/19/26
CTA sub-app
7/11/25 - 10/9/25
pre-IND sub - feedback
Final CTA package
11/28/25
2/4/26 - 7/22/27
FSS - LSS
6/12/26 - 7/22/27
fSIV - LSS
2028
key results
4/16/28
Pre-IND final feedback received on 28 Nov. CDE insisted their initial position about diagnosis of pMN with biopsy only and diagnosis of Alport Syndrome with gene sequencing only.
  Team took immediate action to incorporate the changes in the ongoing local CTP amendment without shifting the target CTA submission date.
CTA submission occurred as planned on 12 Dec
N=132
N=14 (mainland 10, TW 4)

## Slide 51: 1434-0027 – Potential phase 2, multi-center, randomized, double-blind, placebo-controlled basket trial to evaluate BI 764198 in proteinuric glomerular diseases with podocyte involvement
TRPC6i in CKD with podocyte pathology | CONFIDENTIAL
Inclusion criteria
Age ≥18 (≥12 for AS and MCD)
Biopsy proven disease (genetic diagnosis in AS, and serology in primary TR-MN are sufficient)
eGFR ≥25 ml/min/1.73m2
Optimized and stable SoC, including RAASi, SGLT2i and immunosuppressives (if indicated)
Increased UPCR (varies by aetiology)
Exclusion criteria
Rapid progressive kidney disease as measured by eGFR loss ≥ 50% over a period of 3 months prior to Screening
History of kidney transplant or planned kidney transplant
IV immunosuppressive treatment ≤6 months prior to screening
Note: FSGS, focal segmental glomerulosclerosis; IA, interim analysis; MN, membranous nephropathy; sFSGS, secondary FSGS; R, randomization; TR-MCD: treatment-resistant minimal change disease; TRPC6, transient receptor potential canonical 6; UPCR, urine protein creatinine ratio; SoC, standard of care; FMV, first morning void​

## Slide 52
2025
65 days
2028
30 days
289 days
Global
1434-0019
Ph II
China
1434-0019
Ph II
Today
2025
2026
2027
2028
5/17/26 - 8/14/26
CTA sub-app
12/19/25 - 1/30/26
pre-IND sub - feedback
Final CTA package
4/17/26
6/16/26 - 7/26/27
FSS- LSS
pre-IND sub
11/26/25
key results
5/4/28
179 days
11/17/26 - 7/26/27
fSIV- LSS
BI 764198 (TRPC6i), DMD Development Plan
Pre-IND under preparation with planned submission on 19 Dec. The review will follow the Type I HAI for 30 WD.
Prof. Dai, Yi (北京协和) and Prof. Hong, Siqi (重庆儿科医院) are nominated to participate in the Asia-centric ad-board meeting in Mar 2026
FSS: first subject screened; LSR: last subject randomized; FSGS: DMD: Duchenne Muscular Dystrophy; TRPC6i: transient receptor potential channel 6 inhibitor

## Slide 54: BI 3034701 (GGY2Ra.), Obesity Development Plan
2025
65 days
65 days
96 days
47 days
2027
Global
1507-0002
Ph II
China
1507-0002
Ph II
Today
Q4
Q1
Q2
Q3
11/30/25 - 2/28/26
Ph II pre-IND sub - feedback
Q4
Q1
Q2
Final CTA package
2/13/26
3/13/26 - 6/12/26
Ph II CTA sub - app
7/6/26 - 11/17/26
Ph II FSS - LSS
9/11/26 - 11/17/26
China fSIV - LSS
2025
2026
2027
key results
12/27/27
Q3
Q4
PoC release
11/26/25
Ph I readout for PoC
11/14/25
2.5 months
Recruitment window only 2 months (could be longer if new CTA process can be implemented)
PoC was achieved; the Ph I results are not released yet
Phase II design is under re-discussion for acceleration: Ph II/III seamless? Shortened maintenance dose period? Reduce dose groups?
China Pre-IND submission was cancelled because
  Global team doesn’t allow inclusion of any actual Ph I data in HAI BB before press release
  Safety margin is narrow and difficult to explain to CDE without actual data
  Mitigation strategy is to be planned once the data is released
China development proposal shared with global team for further discussion
China Leading PI candidate under final discussion

## Slide 55: Phase II trial design (1507-0002) DRAFT for dose strategy consideration

## Slide 56: TA Portfolio Key Update- BI 7703711 (SIRPa antagonist)
Asset Name-MoA | Indication | China Approval (base case) | Update | Next Step
BI 7703711 (SIRPa antagonist ) | MASH cirrhosis | Nov 2034 | <Global status> Phase 2a: On track. No safety signal seen yet. Go-criteria has been updated: A 20% Threshold for Pro-C3 Ph2b (1501-0005) planning: The operation module changed from Hybrid trial to in housing module. Initiate the draft TDO communication and country feasibility 3) Pre-IND for Ph2b is not planned by global team. | To monitor the global Ph2a results and Ph2b planning
 |  |  | <China status> 1) China to be kick-off the country and site allocation survey on phase 2b trial 2) Prof. Hong You attended the virtual 1:1 consultancy meeting and provided valuable comments on phase 2b design on 2nd Dec; 3) Prof. Minghua Zheng is recommended by local team to attend the in-person global advisory board meeting in Q1 2026. | Country and site allocation feedback by 21-Jan-2026 Continue to follow with global on involving Chinese experts opinion in the planning of Phase 2b.

## Slide 57: TA Portfolio Key Update- BI 3802876 (FAP/TRAILR2)— MASH cirrhosis
Asset Name-MoA | Indication | China Approval (base case) | Update | Next Step
BI 3802876 (FAP/TRAILR2 biospecific antibody) MOA: halt/reverse liver fibrosis by removing FAP+ TRAILR2+ activated Hepatic Stellate Cells | MASH cirrhosis | Aug 2037 | <Global status> A slight increase in hs-cTNT indicating cardiovascular concerns was observed in Phase I among healthy volunteers. A Phase 2a trial (US and Canada only) will be initiated to demonstrate the anti-fibrosis effect and to assess the benefit-risk profile in MASH cirrhosis patients. | Global Phase 2a will be initiated in Dec 2025. 1st site SIV: Dec 2025 1st subject screen: Jan 2026
 |  |  | <China status> The joint Asian Phase 1 proposal with integrated timeline by China and Japan was endorsed by global team. Global team confirmed to deliver essential documents to support China and Japan HA interaction. | Continue to discuss with global team on target population for Asian Ph1

## Slide 58: Asset overview
Drug candidate
  BI 3802876 is a bispecific molecule binding FAP and TRAILR2.
Clinical hypothesis
  Selectively removing FAP+ TRAILR2+ activated Hepatic Stellate Cells will halt/reverse liver fibrosis
Unique MOA
  Directly targeting the source of liver fibrosis
  FAP binding provides cell specificity and clusters TRAILR2 mediates cell killing
Indication
  NASH cF4 is a sentinel population with the potential to expand to other etiologies as a Pan-Cirrhotic Therapy
Treatment paradigm
  Intravenous drug, monthly or longer
  Short term/Cycling/Induction therapy
Competition
  No direct clinical competition for MoA in MASH
Pre-clinical results
  Demonstrated anti-fibrotic PoC in LiverChip (in vitro) fibrosis model with clinically relevant biomarkers (see next slide)
Phase I results
  BI 3802876 may cause small increases in hs-cTnT, which are of uncertain clinical significance at this time.

## Slide 59: Global clinical development timeline and China integration plan
China Integration Plan:
China will be included in the global development program beginning with the Phase IIb (PoCC) trial.
The Phase IIa PoCP trial is restricted to sites in the US and Canada only.
Asian Phase 1 Plan:
Objectives: 1) Collect data from Chinese participants to support advancement to subsequent trial phases; 2) Potentially waive the need for a separate China PK study for registration purposes.
Trial design: Similar to the global Phase IIa but simplified.
Tentative timeline: Q1-Q3 2027 (very preliminary).
Current status: Proposal has not yet submitted to IUPC.

## Slide 60: Template for reference

## Slide 61: TA CRM Portfolio Summary - Pipeline Projects
Please focus on the portfolio changes.
A summary report can be exported from the TCM asset dashboard.
Guide for template use
New projects/studies:
  e.g. Project name, MoA. Additional comments if needed.
Status change: (e.g. →ongoing/under planning/under evaluation)
  e.g. Project name, MoA,, xxxx-1234, Ph II→ongoing. Additional comments if needed.
Completion/Termination:
  e.g. Project name, MoA, xxxx-1234, Ph III completed. Additional comments if needed.
Please label the projects/ studies with the appropriate changes as needed.
template

## Slide 62: TA CRM Portfolio Summary - PMS Studies
Please focus on the portfolio changes.
A summary report can be exported from PMS dashboard.
The traffic light status needs to be manually added to the slide.
Guide for template use
New studies:
  e.g. xxxx-1234, (study short description, e.g. ORIENTAL, Real-world study of Jardiance in Chinese patients with HFpEF), Additional comments if needed.
Status change: (to ongoing)
  e.g. xxxx-1234, (study short description)→ongoing. Additional comments if needed.
Completion/Termination:
  e.g. xxxx-1234, completed, Additional comments if needed.
Please label the studies with the appropriate changes as needed.
template

## Slide 63: Projects/Studies with Red-Light
Please provide details for pipeline project/studies and PMS studies with red-light and add additional slides if needed.
Guide for template use
***
Key issues
***
Mitigation actions
***
Status update
Project/study
e.g. BI123456, MoA in Obesity/XXXX-1234, PhII
Red-light starts from
e.g. Aug 2025
template

## Slide 64: Guidance on Portfolio Highlights
Each TA may define the contents of its portfolio highlights according to TA presentation needs.
Please ensure that updates on key projects and key studies(e.g. recruitment curve) within the TA are included.
The templates for the development plan and recruitment curve in slides 8 and 9 can be used as references and adapted as needed to suit the TA’s requirements.
Content
Format

## Slide 65: BI 123456/INN (MoA), indication Development Plan
The template can be adjusted based on project needs.
Guide for template use
65
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 20230 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2/3-
xxxx-xxxx
FPI
Jun 2025
Ph2/3, N=***
Ph2/3, N=**
17 Nov 2025
CTA Review + EC + HGRAC + 1st SIV
Apr 2025
1st SIV
CTA Sub
LPI
Jul 2026
LPI
Jul 2026
Ph2/3-
xxxx-xxxx
Key results
Mar 2027
Key results
Mar 2027
Apr 2027
BTD sub.
Apr/May 2027
BTD sub.
Aug 2027
NDA sub.
Dec 2027
NDA app.
Sep 2027
NDA sub.
Sep 2028
NDA app.
Updates on the project and studies for global
Updates on the project and studies for China
template

## Slide 66: xxxx-xxxx BI 123456/INN indication Global/China Recruitment
Chart: Global recruitment curve
| 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
Patients Enrolled/Randomized (Actual) | 0 | 1 | 4 | 5 | 22 | 69 | 221 | 369 | 574 | 905 | 1124 | 1177
Patients Enrolled/Randomized (Planned) | 0 | 1 | 6 | 29 | 76 | 167 | 265 | 364 | 473 | 585 | 686 | 780 | 886 | 993 | 1080 | 1080
Patient Screened(Actual) | 0 | 3 | 6 | 30 | 124 | 295 | 609 | 852 | 1399 | 1720 | 1720 | 1720
Patient Screened(Planned) | 3 | 9 | 31 | 91 | 173 | 299 | 432 | 568 | 702 | 830 | 960 | 1084 | 1225 | 1360 | 1450 | 1450
Cut-off date: 2024.1.2
Total Screened : xxx
Total Randomized: xxx
Total Screen failure: xxx
In screening : xxx
Screen failure rate = xx %
template