## Slide 1: Metalyse Late Time Window HA Interaction Strategy
For endorsement

## Slide 2
Background
PEC Discussion
Discussion Purpose
Team Proposal
Rationale for PEC Discussion
Confirm the HAI strategy for the sister trial
Pre-IND is necessary, due to the complexity of the current development strategy.
1.Current proposal from the local team is not aligned with BUPC recommendations.
2.Guidance from PEC members is requested.
□ For Sharing □ For Advice √ For Endorsement
The decision from BUPC (11 Dec 2025)
Global recommends submitting the CTA directly, without prior CDE consultation.
The regulatory strategy for the China sister trial is pending CN RA agreement.

## Slide 3: Local assessment of HAI (PROS & CONS)
 | PROS | CONS
With Pre-IND | Value: An opportunity for in-depth communication & alignment with CDE on overall development strategy. Mitigate potential risk for NDA approval at early stage | None
 | Timeline: Proactively identify and resolve potential issues to minimize timeline impact on overall development plan. Meanwhile, no impact to following sister trial process. (placebo preparation is on critical path) | 
 | No Impact for TENACITY’s execution | 
Without Pre-IND | Save limited resource for pre-IND preparation | Lose opportunity for in-depth communication with CDE on overall development strategy to leave a significant uncertainty for NDA-approval.
 |  | Queries during CTA stage might be challenging and may impact following timeline
CDE pre-IND consultation is necessary based on local assessment.

## Slide 4: HA interaction (HAI) plan
Next step
Post PEC endorsement on HAI: Share HAI strategy with global team & reach alignment
Kick off HAI preparation with global team, covering BB/TDO preparation.
Timeline: Submit HAI Application (60WD) by the end of Jan 2026, CDE feedback expected around end of Apr 2026.
HAI questions: 1.Overall development Strategy; 2.Sister Trial Design - Statistical Analysis & Sample Size;3.Metalyse placebo: Leverage 50 mg Stability Data to support 60M shelf life for 25mg placebo.etc.