## Slide 1: (Title from slide 3)
1
 | Status | Next steps
Global | Part 3 patient number will increase from 30 to 50 and be incorporated into primary analysis. | New CTP and timeline will be released in end of June.
China | Target to recruit the first patient for part3 in Jul 2026. | To get the endorsement from global to meet 15% CN patients in total (part 2+3). Discuss HA interaction plan after CTP amendment finalization.
Risk/Issue | Mitigation/Action
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2-
xxxx-xxxx
—
—
—
—
—
—
—
—
Ph2-
xxxx-xxxx
—
—
—

## Slide 2: Dareon-5 (1438.5)/ 2L+ epNEC (AA)/ SAT （Data as of 09Jun2026）
Project Milestones – Part 3 (CTP 6.0) |  | 
Milestone | China | 
 | plan | Actual
Patient number | Part1: 12; Part2: 5; Part3: 4 | Part1: 12; Part2: 5; Part3: TBD
Site number | 4-5 | 4(part 3)
CTA amendment submission(CTP6.0) | 8-Mar 2026 | 2-Mar-2026
CTA amendment approval(CTP6.0) | 27-May-2026 | 7-Apr-2026
EC amendment submission(Leading site，CTP6.0) | 15-Mar-2026 | 10-Mar-2026
EC amendment approval(Leading site，CTP6.0) | 15-Apr-2026 | 15-Apr-2026
HGRAC amendment submission(CTP6.0) | 30-Apr-2026 | 14-May-2026
HGRAC amendment approval​(CTP6.0) | 29-May-2026 | 21-May-2026
First Subject Screened​ （CTP 6.0）​ | 21-Jul-2026 | 
First Subject Randomized（CTP 6.0）​ | 11-Aug-2026 | 
Last Subject Screened​ （CTP 6.0）​ | 10-Dec-2026 | 
Last Subject Randomized （CTP 6.0）​ | 31-Dec-2026 (Trial LPI)- will be updated | 
DBL | 6-Apr-2028 | 
Asset information and Global status
Based on the data from futility analysis, global revised the development strategy: Thirty patients from part 3 will be included in primary analysis. Therefore, timeline has been delayed for 8 months.
China development strategy
PV： Part 3 is an outpatient monitoring setting, and after confirmation with ABRT Chair, this change will not pose a potential increase in patient risk. RA： NDA timeline will be updated in late June to early July once updated trial timeline released. Planned CTP amendment to include part3 for primary analysis. HA interaction /BTD plan will be re-evaluated after CTP amendment available. CO: Part 3 key updates： China allocation: Screened: 16 pts, enrolled: 4 pts. Timeline → As shown in the table on the right. EC to be submitted in Mar. Leading site EC approved on 15Apr 2026 HGRAC Approved on 21-May-2025. Recruitment: Global: First subject screened in USA on 12-May-2026, no patient randomized. China: Site re-training is ongoing, some patients identified in CHN14 & CHN15, but DLL3 testing await SECCR approval, delaying readiness at IQVIA laboratories. – released on 8Jun 2026 2L epNEC preferred
Status:
Notes: „Dareon“ (Darius – Persian for ocean  Empowerment, new horizons, game changer)

## Slide 3: Obrixtamig (DLL3/CD3 TcE) – 2L epNEC (single arm study) Update
Project Milestones |  |  |  |  |  |  |  | 
Milestone | Global |  |  |  | China |  |  | 
 | Ph2- 1438-0005 Dareon-5 | Note （展示在时间条内信息） | Ph2- 1438-0005 Dareon-5 | Note （展示在时间条内信息） | Ph2- 1438-0005 Dareon-5 | Note （展示在时间条内信息） | Ph2- 1438-0005 Dareon-5 | Note （展示在时间条内信息）
Pre-IND |  |  |  |  | Jan 2023 |  | Jan 2025 | 
CTA-s |  |  |  |  | Apr 2023 |  | Apr 2025 | CTA Review + EC + HGRAC + 1st SIV
1st SIV |  |  |  |  | Nov 2023 | Ph2, N=*** | Nov 2025 | Ph3, N=***
FPI | Jun 2023 | Ph2, N=*** | Jun 2025 | Ph3, N=*** |  |  |  | 
LPI | Jul 2024 |  | Jul 2026 |  | Jul 2024 |  | Jul 2026 | 
Key results | Jan 2025 |  | Mar 2027 |  | Jan 2025 |  | Mar 2027 | 
NDA-s |  |  | Aug 2027 |  |  |  | Sep 2027 | 
NDA-a |  |  | Dec 2027 |  |  |  | Sep 2028 | 
根据Page 2的时间线整理的milestone表格