## Slide 1: Goal Setting – China Early Asset Team in TA Mental Health & Eye Health (1)
Category | Target details | 
 | Mental Health | Eye Health
Co-create corporate early assets documents and activities: Inputs are provided promptly to corporate asset teams to co-create the key documents and activities, to reflect China insights and to support corporate asset team decision-making. | NR2B NAM light IAP co-creation AEP evidence gap for China: NR2B NAM, GOATi, mGluR4 NAM, etc. Support NR2B NAM Global AB meeting Provide price assumptions for NR2B NAM in 25LTF (2030 launch) | Light IAP review and input for Anti-Sema3A and Anti-C3 AEP evidence gap for China: PKKi, Anti-Sema3A, Anti-C3, PAFR antago., etc. Provide price assumptions for Anti-Sema3A and Anti-C3 in 25LTF (2030 launch)
China integration: Team to develop a well-defined China integration strategy and a clear plan for integration discussions with global teams, ensuring timely aligned decisions on China integration and the initiation of trials in China. | China integration plan development and timeline for decision alignment: NR2B NAM Ph3 trials in MDD integration: Q2 2025 China integration/launch strategy in CT-155/156: Q3 2025 (based on global Ph3 readout) SSTR4 ago. Ph2 PoCP trial integration: Q2-Q3 2025 GOAT inh. Ph2 PoCC trial integration: Q4 2025 | GA ECR: Leverage RWE from GA ECR to address evidence gap and support Asian strategy in GA assets of Anti-C3 and PARF.
Execution excellence in clinical development of early Assets in China: Ensure the timely and high-quality delivery of clinical trials milestones, and fulfill the committed patient contribution to global trials. | NR2B NAM: Pre-IND for Ph2 trial in BD in Q3 2025 EoPII meeting for MDD Ph2 trials in Q3 2025 CTA for Ph3 trials in MDD in Q4 2025 | PKKi: CTA for Ph2 in DME in Mar/Apr 2025 1st SIV for Ph2 in DME in Q4 2025 to Q1 2025
Early engagement of key stakeholders: Develop and implement a clear plan for the early engagement of key external stakeholders, particularly for new indications in China portfolio, and provide insights from China to corporate asset teams. | NR2B NAM: MDD KEE mapping and KEE engagement NAB meeting in Q3 to collect KEE insights Ph2 Data dissemination and communication Precision psychiatry clinical development: Engage with CDE and seek strategical advice on “precision psychiatry approach to clinical development” in Q2. Complete and release < MDD Clinical Trial Willingness & Placebo Drivers > at DIA CNS innovative forum in Aug.2025 | DR/DME: 1st NAB meeting on DR/DME to collect KEE insights

## Slide 2: Goal Setting – China Early Asset Team in TA Mental Health & Eye Health (2)
Category | Target details | 
 | Mental Health | Eye Health
Support strategic planning of asset development Asset strategy making need to align and fit the China dynamic market development. Value function closely monitors status quo and analyzes trend to support the strategy making. | Solid market understanding composed of patient journey, competitive intelligence etc. to support team on making strategy of asset. Based on market understanding, conduct economic evaluation in terms of topline and promotion cost to support further business case analysis. In early ICP, collaborate closely with team members and cross-functional to formulate strategies and develop actionable plans tailored to local customer engagement. Comprehensive price & market access landscape analysis and updated pricing assumptions to support China P&MA strategy. | 
Smooth handover to local asset teams: Ensure a seamless transfer of knowledge and related documents to local asset teams | Ensure smooth handover of NR2B NAM to local asset team once local full execution mode is requested by RMM after Ph2 readout. | NA
Other: Other activities not covered by the above categories | NA |