## Slide 1: TENACITY & PersisTENce Evaluation
For PEC advice and endorsement

## Slide 2
Clinical Development and Operations
1120-0060 TENACITY -China recruitment analysis- Cumulative Data as of Mar 2026
Chart: China Pre-Screen Failure Data Analysis
| NIHSS ≤5 or >25 | Planned/Performed Thrombectomy | Imaging/Perfusion Mismatch | Family Requested Conservative Treatment | Thrombolysis Already Performed at Another Hospital | History of Stroke with Diabetes | Family Strongly Requested Thrombolysis | Pre-Stroke mRS Score of 2 | May exceed 24 hours prior to randomization | Large Cerebral Infarction/Brain Herniation | Transferred Back to Local Hospital Without Treatment | Bleeding Disorders/History of Hemorrhagic Stroke | Other Comorbidities or Untraceable Cases
 | 106 | 28 | 26 | 14 | 12 | 7 | 5 | 4 | 3 | 3 | 2 | 2 | 35
 | 0.429 | 0.113 | 0.105 | 0.057 | 0.049 | 0.028 | 0.02 | 0.016 | 0.012 | 0.012 | 0.008 | 0.008 | 0.142
Ineligibility Breakdown by Criteria (TENACITY) | Pt Number | Rate | Eligibility criteria in ORIGINAL
NIHSS ≤5 or >25 | 106 | 42.90% | Inclu: (0< NIHSS ≤25); if NIHSS <4, patients have to be with at least a measurable deficit on motor power (upper or lower limbs ≥1)
Planned/Performed Thrombectomy | 28 | 11.30% | No restriction
Imaging/Perfusion Mismatch | 26 | 10.50% | No restriction
Patient Prefer Conservative Treatment | 14 | 5.70% | Not applicable
Thrombolysis Already Performed at Another Hospital | 12 | 4.90% | Not applicable
History of Stroke with Diabetes | 7 | 2.80% | Not applicable
Patinet Prefer Thrombolysis | 5 | 2.00% | Will be enrolled
Pre-Stroke mRS Score of 2 | 4 | 1.60% | Inclu: Patients with premorbid mRS 0 or 1
May exceed 24 hours prior to randomization | 3 | 1.20% | Inclu: Within 4.5 hs
Large Cerebral Infarction/Brain Herniation | 3 | 1.20% | Exclu: Imaging demonstrates multi-lobar infarction (hypodensity >1/3 cerebral hemisphere)
Transferred Back to Local Hospital Without Treatment | 2 | 0.80% | 
Bleeding Disorders/History of Hemorrhagic Stroke | 2 | 0.80% | Exclu: Acute bleeding diathesis
Other Comorbidities or Untraceable Cases | 35 | 14.20% | 
Total | 247 | 100.00% | 
NIHSS=4：13pts
NIHSS=5：4pts
NIHSS=28: 1pts

## Slide 3: TENACITY Recruitment Mitigation
Increasing up to 55 sites with additional ones proposed by BI CN or selected from top recruiting sites in similar-design IIS
Do best to accelerate SIV to include the high-performance sites earlier
Enhance site engagement visits to boost recruitment – implemented by CRO and BI(CTM resource normally assigned 0.2 FTE)
To engage leading PI for further support, may explore co-leading PI (candidate: Prof. Xin Cheng and Prof. Min Lou) pathway according to leading PI attitude

## Slide 4
Site Distribution Analysis: CHESTNUT & TNK-LATE vs. Tenacity
03 爱设计
Among the top 20 sites in the CHESTNUT, 5 sites that meet GCP standards and investigator qualification criteria for registration trial are also participating in the Tenacity.
2 of these sites have been activated recently, while 3 sites remain pending activation.
CHESTNUT
Tenacity
TNK-LATE
Site Name | PI | Recruitment in CHESTNUT
复旦大学附属华山医院 | 程忻 | 28
临沂市人民医院 | 王自然 | 24
成都市第二人民医院 | 王健 | 6
赤峰市中医蒙医医院 | 鲁国志 | 5
惠州市第一人民医院 | 蔡春生 | 5
The PI overlap rate between the TNK-LATE and Tenacity is 0%.
The 10 sites contributing to enrollment in TNK-LATE did not participate in Tenacity, with 8 of them lacking GCP standards or investigator qualification criteria for registration trial. 1 rejected, 1 quality issue(六安二院，赣州市人民）

## Slide 5: Consideration on PersisTENce (triggered by TENACITY）
PersisTENce recruitment will be more challenging than TENACITY
Overlap recruitment period with TENACITY
Double blind study design
Thrombolysis usage in late window AIS will be more widespread
中国卒中学会急性缺血性卒中再灌注治疗指南2024
对于NIHSS评分≥ 6 分、发病时间4.5～24 h内，前循环LVO且灌注成像提示梗死核心/低灌注不匹配，但无法进行机械取栓的急性缺血性卒中患者，推荐使用替奈普酶0.25 mg/kg进行静脉溶栓治疗（Ⅰ类推荐，A级证据）
Mitigation plan
Site selection: high performance sites from TENACITY will be selected and need further discussion and alignment with recruitment prioritization for both trials; explore more high potential sites with acceptable quality
To engage leading PI for further support, may explore co-leading PI (candidate: Prof. Xin Cheng and Prof. Min Lou) pathway according to leading PI attitude

## Slide 6: Registration Strategy – PersisTENce
CTA Review
There is potential uncertainty associated with waiving pre-IND meeting. CDE’s attitude is expected at the later stage of CTA review.
CTA-s
Apr 2026
CTA-a
Aug 2026
Go
(conduct trial)
Scenario 1 Approve CTA without major comments
No major comments for study design and sample size
No major comments for overall development strategy.
Scenario 2 Approve CTA with major comments
Major comments for study design or sample size
Revisit strategy
HAI
Aug 2026
Nov 2026
Scenario 3 Not agree CTA (POS low)
Scientific rationale of the strategy
Statistical consideration

## Slide 7: Timeline Re-assessment – PersisTENce
2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
today
CO frontloading activity
N=200 (9 M)
fSIV
Nov 2026
NDA sub.
Apr 2028
NDA app.
Apr 2029
LPI
Aug 2027
DBL
Dec 2027
CSR
Feb 2028
Apr 2026
IMP ready in local depo
Nov 2026
CO frontloading activity
N=? (?M)
fSIV
NDA sub.
NDA app.
LPI
DBL
CSR
Aug 2026
Senario 1
N=200
Senario 2
N=200+
（Need to apply for additional budget)
Start-up activity
Start-up activity
Aug 2026
Apr 2026
Further evaluation
Ph3, N=1325 (China ~ 340pts), 18M
Feb 2026
CTA Review + EC + HGRAC + 1st SIV
1st SIV
LPI
Mar 2027
CSR
Jul 2027
DBL
(Key results +1W)
Sep 2027
TENACITY

## Slide 8: Back up

## Slide 9: Site Engagement Plan & Status (The SPOC is responsible for coordinating EE activities for the R/OPU. SPOC is not responsible for any operational issues)
Site Name/PI Name | Attending Function | Planned Date | Status | Visit Purpose/ Comments (important issues and risks regarding site feedback)
首都医科大学附属北京天坛医院/ 赵性泉 | CDO & Medicine & MSL | 12-Feb-26 | Completed | Leading PI visit，Site engagement visit for 1st SIV
南阳市中心医院/ 温昌明 | CDO | 1-Apr-26 | Completed | Site engagement visit for recruitment boosting
安阳市人民医院/杨清成，张建刚，郭艳平 | CDO | 2-Apr-26 | Completed | Site engagement visit for recruitment boosting
广州医科大学附属第三医院/梁燕玲 | CDO | 15-Apr-26 | Completed | Site engagement visit for recruitment boosting
南京医科大学第二附属医院/吴晋 | CDO & MSL | 28-Apr-26 | Planned | Site engagement visit for recruitment boosting
湖南省人民医院/赵志鸿 | CDO & MSL | 13-May-26 | Planned | Site engagement visit for recruitment boosting
南华大学附属第一医院/武衡 | CDO & MSL | 15-May-26 | Planned | Site engagement visit for recruitment boosting
临沂市人民医院/王自然 | CDO & MSL | 20-May-26 | Planned | Site engagement visit for recruitment boosting
郯城县第一人民医院/杜伟 | CDO & MSL | 22-May-26 | Planned | Site engagement visit for recruitment boosting
临汾市中心医院/戴红果 | CDO & MSL | 15-Jun-26 | Planned | Site engagement visit for recruitment boosting
Note: These plans (including sites / visit date) will be adjusted as needed based on actual recruitment status.