## Slide 1: Portfolio Executive Committee (PEC) Review Meeting TA MHEH
  Yuting Li, Freya Zhu| 23 Apr 2026 | 10 min
To insert a wordmark:
Add (e.g. via drag and drop) your wordmark file (in RGB) to this slide (in alignment with our brand governance and architecture guidelines)
Change the size of the wordmark according to the height reference (magenta placeholder)
Select the “guides” in the navigation bar and move the wordmark to the right and top line (orange)

## Slide 2: Part I: Follow-up Actions from the Previous PEC
PEC action log

## Slide 3: Part II: Discussion/Endorsement

## Slide 4: Part III: Update

## Slide 5
TA MHEH Portfolio Summary - Pipeline Project
Sustain
FIH-PoC
Stop/ Park
CS-FIH
Post PoC
SSTR4 ag
CIAS
mGluR4 NAM
BPD
GOATi
OUD
Anti-Sema3A
NPDR
CI-DME
iRVO
PKKi
DME
nAMDp
Anti-C3
GA
PAFR
GA
Anti-VEGF/TNFa
nAMD
BCL-xL inh
nPDR
STING inhibitor
DME
Mental Health
Eye Health
Next wave
Ongoing/under planning
Under evaluation
FZD4_LRP5
CI-DME
Eye Health
Further alignment might be needed due to potential ethnic difference in disease.
Eye Health
A successful meeting was held on Apr 17th. with Experimental Medicine EH LT to introduce China capability in early clinical development.
Follow-up activities with BCL-XL inhibitor, anti-VEGF/TNFα and IVT-XR (NCE) teams are planned to explore early phase study opportunities (e.g. FIH, PoM)
FiH
PoC
CN App
2027
2027
2029
2026
2031
2029
2030
2026
2027
2026
2027
Notes: 感谢Lincy Alex

## Slide 6: 2026 TA Key Milestone Overview – Eye Health
PKKi - PoC
ARVO/
4Sight NETWORK (DR/DME and AMD/GA)
aC3 – GA
Light GBP Workshop
2026 Visionary Pathway
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OTC | NOV | DEC
Global milestones
Study start/ read-out
Milestone
Termination
Phase I
Phase II
Phase III
1st Submission
CS (SoD)
PoC
RoFD
Other Activities
TLR
HAI
PKKi - DME
THULITE Ph2b LPI
Anti-Sema3A - DR
CRIMSON Ph2b LPI
PAFR - GA
JADE Ph2b IA
PKKi - DME
THULITE Ph2b IA
FZD4/LRP5 - DR/DME
Ph1/2 FPI
PAFR - PoC
C3 peptide inh. IVT XR – CS moved to 2027 Q1/Q2
aC3 XR – CS from Aug to end of 2026
PKKi – nAMD
Global Think Tank
PKKi - DME
THULITE Ph2b LPI
GA
COMPASS IA2
PKKi – DME
THULITE Ph2b China IM
GA Scientific Exchange Meeting with KEE
THULITE China Workshop
DR/DME RWS
GA NAB
GA Pipeline HAI
PKKi - DME
THULITE Ph2b China FPI
GA
COMPASS IA1
China milestones
China Top Tier KEE Mapping
Anti-VEGF/TNFa – CS
From Apr-Jul
aC3 - GA
VERDANT Ph2b IA
BCL-xL inh – CS (from May-Sep)
BCL-xL inh – DR SoD
STING IVT XR – DME SoD
Anti-VEGF/TNFa – nAMD SoD
Anti-VEGF/TNFa
Ph 1/2 China Integration Strategy
BCL-xL inh
Ph 1/2 China Integration Strategy

## Slide 7: 2026 TA Key Milestone Overview – Mental Health
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OTC | NOV | DEC
Global milestones
China milestones
mGluR4 NAM – Imp in BPD
Path to PoC (IUEC)
SSTR4 ag – CIAS
Ph1b FPI
SSTR4 ag – CIAS
Path to PoC (IUPC)
Study start/ read-out
Milestone
Termination
Phase I
Phase II
Phase III
1st Submission
CS (SoD)
PoC
RoFD
Other Activities
TLR
HAI
COMTi – Fx in SCZ
Termination
COMTi – Fx in SCZ
Back-up CS
GOATi – Other SuD/Imp
Global AB
mGluR4 NAM – Imp in BPD
Global AB
mGluR4 NAM – Imp in BPD
CoA prototype (FDA)
mGluR4 NAM – Imp in BPD
Ph2a PoC China Integration Strategy
mGluR4 NAM – Imp in BPD
CoA China Bridging Strategy
Delicado – SZ SoD
mGluR4 NAM – Imp in BPD
China NAB
mGluR4 NAM –
Imp in BPD
CoA Obs FPI
Introduction of China Overview in Global ExpMED N&MH Community Forum
GOATi–OUD
Ph2a PoC China Integration discussion

## Slide 8: Study Status
TA MH&EH Portfolio Summary - PMS Studies
1346- GlyT1
1484- PAFR and anti-C3
1485- Anti sema3A and Pkki
1346-0089, (BJ Perfect)→ongoing
Study data analysis will be completed in Jun 2026.
1484-0020, (COMPASS)→ongoing
Study is in the enrollment stage.
1485-0034, (DR and DME)→plan
Study proposal released on Apr 9th (later than endorsed timeline)
Potential delay in protocol approval
Notes: ECR
No alt text provided
pivotTable
No alt text provided
image
No alt text provided
textbox
No alt text provided
textbox
No alt text provided
card
No alt text provided
IIS
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
slicer
No alt text provided
BI-ONISed
No alt text provided
BI-ONISnd
No alt text provided
EAP
No alt text provided
BI-Clinical trial
No alt text provided
image
No alt text provided

## Slide 9: Mature Product/PMS Overview - MH&EH
Product/Study | Indication | Study type (Study no.: FPI-LPO, CTR) | Current status | Next Milestone | Key Updates | 
GlyT1 (BJ-PERFECT VR Version Validation) （Peking University Sixth Hospital， Prof. Shi） | BJ-PERFECT VR Validation and norm | ECR (1346-0089; Sep 2024- Dec 2025, Dec 2026) | Data analysis completion (Mar 2026) | Data analysis completion (Jun 2026) | Data analysis has been conducting Sponsor-investigator is preparing study report | 
PAFR and anti-C3 (COMPASS) （Chinese Academy of Medical Sciences & Peking Union Medical College, Prof. Chen） | GA | ECR 1484-0020 (Jun2025-Oct 2027, May 2030) | FPI （Jun 2025） | 1st interim analysis （Mar 2026） | Contract was signed on 12 May 2025. The 1st interim analysis completed on 27 Feb 2026 Study recruitment progress: Study recruitment progress: Retrospective part: 120/63 (+1 than last month); Prospective part: 70/14(+3 than last month); Site initiation progress: 16/10(+0 than last month) | 
anti sema3A and Pkki (Patient journey and treatment pattern and of DR and DME in China (Peking University Third Hospital, Zhuolin) | DR and DME | ECR 1485-0034(Jan 2026-Dec 2026，Jun 2027) | Proposal release (Apr 2026) | Protocol approval (Apr 2026) | Proposal global release completed on 9 Apr 2026 | 

## Slide 10: Eye Health Assets

## Slide 11: Overview of Eye Health Early Assets for China Integration
2025
2028
Today
Jan
Apr
Jul
Oct
Jan
Apr
Jul
Oct
Jan
Apr
Jul
Oct
2026
2027
2028
GA – gPh2 (1479-0002, VERDANT)
PoC, Feb 2027
GA – gPh3 (1479-0003/0004)
Nov 2027
DME – gPh2 (1485-0018, THULITE)
Feb 2026
PoC, Oct 2026
DME – gPh3 (1485-0019/0020)
Aug 2028
nAMD – gPh2 (1485-0004)
Aug 2028
NPDR – gPh2 (1436-0007, CRIMSON)
PoC, May 2027
NPDR – gPh3 (1436-0009/0010)
May 2028
PDR – gPh3 (1436-0012)
May 2028
GA – gPh2 (1484-0005, JADE)
PoC, Aug 2026
GA – gPh3 (1484-0015/0016)
Feb 2028
Acceleration under discussion
aC3
PKKi
aSema3A
PAFR
FZD4/
LRP5
CI-DME – gPh1/2 (1523-0001)
PoC/RoFD, Jul 2027
CI-DME – gPh3 (1523-0003/0004)
May 2028
Potential acceleration
Further alignment might be needed due to potential ethnic difference in disease.

## Slide 12: BI 1815368 / PKKi, Diabetic Macular Edema (DME), Development Plan
China CIQ: China Entry-Exit Inspection and Quarantine; nAMD: neovascular age-related macular degeneration
12
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2 -
1485-0018
THULITE
FPI
May 2025
THULITE Ph2, N=300
Ph2, N=8
26 Jan 2026
CTA Review + EC + HGRAC + Contract
Mar 2025
1st SIV
CTA Sub
LPI
Sep 2026
LPI
Sep 2026
Key results
Key results
Nov 2027
Nov 2027
Global Update:
THULITE Ph2 Ongoing: : 61 patients enrolled vs.153 planned, by 24 Apr;
2 x Ph3
FPI
Aug 2028
Ph3 -
1485-0019/
1485-0020
Ph2 -
1485-0018
THULITE
CoA
21 Jan2026
IA*
PoC *
Today
THULITE Trial Update:
All 5 sites activated by 30 Mar.
Recruitment:
  FPS achieved: 27 Mar.
  Screened: 3 actual vs. 6 planned (1 Screen failure; 2 ongoing)
  Pre-screened: 431 patients (incl. 16 PI-referred); 29 high potential patients further assessed with 22 failed (incl. 7 refusals)
Other:
Site engagement:
  CHN2 (West China Hospital) visited for recruitment boost on 8 Apr
Oct 2026

## Slide 13: Recruitment Status - Global

## Slide 14: Recruitment Status - China

## Slide 15
Chart: Distribution of Pre-Screening Failure Reasons (Total including HIS pre-screen)
| ★Top 1 E4-Anti-VEGF Tx History (>4) | ★Top 2 E34-Enrolled in Other Trials | ★Top 3 E7-Vitreoretinal/Intraocular Surgery | E5-PRP History | E2-Proliferative DR | E14-Other Diseases Impairing BCVA | E11-Cataract Surgery within 3mo | E12-Ocular Inflammation History | E16-Diseases Affecting Imaging | Patient Preference-Refusal | E9-Dexamethasone Implant History | E17-Poor Fellow Eye BCVA | I7-BCVA Score Not Met | E24-Cerebrovascular Disease History | E1-Non-CI-DME Macular Edema | E8-IVT/Periocular Steroids | E25-Severe Fundus Hemorrhage | E31-Prohibited Medication Use
 | 155 | 98 | 48 | 45 | 15 | 11 | 10 | 9 | 7 | 7 | 6 | 4 | 3 | 2 | 1 | 1 | 1 | 1
Chart: Key Patient Pre-screening Failure Reasons
| ★Top 1 Patient Preference - Patient/Family Refusal | ★Top 2 E5 - PRP History | ★Top 3 E12 - Ocular Inflammation History | E14 - Other Diseases Impairing BCVA | E2 - Proliferative DR | E4 - Anti-VEGF Tx History (>4) | E8 - IVT/Periocular Steroids | E11 - Cataract Surgery within 3mo | E24 - Cerebrovascular Disease History | E25 - Severe Fundus Hemorrhage | E31 - Prohibited Medication Use
 | 7 | 4 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
China Pre-Screen Failure Data_20260420
Global Pre-Screen Failure Data_20260331
Actions taken by local team to promote recruitment:
Conducted 3 site engagement visits since SIVs to enhance recruitment efforts.
Maintained close collaboration with the IQVIA China team through:
  Weekly updates on site recruitment status, including pre-screening number and reason.
  Bi-weekly catch-up meetings to discuss site recruitment challenges and align strategies.
  Regular huddle meetings with BI & IQVIA global and local teams.
Performed detailed recruitment analysis for each site, including:
  Evaluation of recruitment routes and measures implemented.
  Identification of challenges and development of mitigation strategies.
VS.
Pre-screen Failure Reasons: China vs. Global with Similarity and Differences
Similarity
IVT history
Differences* （China)
Joining other trials
  Patient Refusal
  PRP Laser
  Macular Laser
  Metformin
To be optimized
Due to local treatment pattern
*Some differences are due to different starting point or screening funnel

## Slide 16: BI 764524 / Anti-Sema3A, Diabetic Retinopathy (DR), Development Plan
DR: Diabetic Retinopathy; CI-DME: Center-Involved Diabetic Macular Edema; RNP: Retinol Non-Perfusion; PRP: Panretinal Photocoagulation
16
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2b -
1436-0007
CRIMSON
FPI
May 2024
Ph2b in NPDR without CI-DME, CRIMSON, N=178
Ph3 in NPDR without CI-DME
Ph3 in PDR
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
LPI
Apr 2026
Final results
Oct 2027
52-wk key results
May 2027
FPI
2 x Ph3 in NPDR wo CI-DME
1 x Ph3 in PDR
LPI
May 2029
52-wk
primary results
May 2030
Ph3 -
1436-0009/
1436-0010/
1436-0012
May 2028
Sep 2030
NDA sub.
Ph3 -
1436-0009/
1436-0010/
1436-0012
LPI
Oct 2030
CN NDA sub.
May 2029
PoC
Today
China Update:
  DR/DME ECR based on Beijing Healthcare Insurance Study:
    Proposal approved and released on 9 Apr
    Ophthalmology investigator, Prof. Kang Feng, proposed and engaged F2F on 31 Mar
  Global/China brand team regular meeting kicked off on 25 Mar.
Global Update:
  Phase IIb CRIMSON: LPI milestone achieved on 3 Apr, approximately one month ahead of revised projections

## Slide 17: BI 771716 / Anti-C3 AB, Geographic Atrophy (GA), Development Plan
Today
17
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2 -
1497-0002
VERDANT
FPI
Jan 2025
LPI
Sep 2025
China Update:
GA pipeline consultation: BB input completed and under review by global LT. Submission targeted by Apr/May depending on question list alignment with global.
Local workshop planned in May to evaluate the impact of different Ph3 integration scenarios and evidence generation plan.
Key results
Jan 2027
FPI
2 x Ph3 in GA
LSS
Oct 2028
Ph3 -
1497-0003/
1497-0004
Oct 2027
May 2030
NDA sub.
IA
May 2026
Nov 2029
Primary results
Dec 2030
Key results
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
Ph3 -
1497-0003/
1497-0004
Ph3 in GA
LPI
Jun2030
NDA sub.
VERDANT Ph2b in GA, N=180 (US)
Global Update:
IA to be achieved in May with GNG decision.
Sep 2027
Mar 2028
PoC
RoFD
Feb 2027
May 2027
Notes: Izervay, the C5 inhibitor from Astellas, with registrational trials (GATHER1 & GATHER2 in US/EU) demonstrating positive results in reduction in GA lesion growth but no significant effect in visual function, was approved by FDA (2023), rejected by EMA, and now conditionally approved by PMDA in Sep 2025 waiving clinical data in Japanese patients. External information shows that an experts consultation panel was organized by CDE recently to evaluate Izervay approval in China waiving clinical data in Chinese patients. Local team is closely monitoring on the status.

## Slide 18: 1484-0020 COMPASS BI 771716 / Anti-C3 AB, GA, China Recruitment
Study timeline was confirmed by Sponsor in Mar and endorsed by CEC in Apr.
Report of retrospective analysis on APVRS (Aug 2026): APVRS submission achieved in Apr.
Cut-off date: 2026.03.31
Total Enrollment:
Prospective group: 14(+3)/70
Cross-sectional group: 63(+1)/120
Site initiation: 10/16

## Slide 19: BI 1815368 / PKKi, Diabetic Macular Edema (DME), Development Plan
China CIQ: China Entry-Exit Inspection and Quarantine; nAMD: neovascular age-related macular degeneration
19
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2 -
1485-0018
THULITE
FPI
May 2025
THULITE Ph2, N=300
Ph2, N=8
26 Jan 2026
CTA Review + EC + HGRAC + Contract
Mar 2025
1st SIV
CTA Sub
LPI
Sep 2026
LPI
Sep 2026
Key results
Key results
Nov 2027
Nov 2027
Global Update:
THULITE Ph2 Ongoing: IA reprojected to Oct*.
  Early-discontinuation** rate higher than estimated
  “Global Huddles”- Regular joint meeting set up for China & Japan (global/local/IQVIA)
  Global IEP update in progress
  * Recruitment delay: 46 patients enrolled
  ** Maily due to violation of eligibility criteria
2 x Ph3
FPI
Aug 2028
Ph3 -
1485-0019/
1485-0020
Ph2 -
1485-0018
THULITE
CoA
21 Jan2026
IA*
PoC *
Today
THULITE Trial Update:
SIV: All 5 sites initiated and 3 activated.
IMP: Site shipment delay due to Almac issue
Recruitment status: 15 patients prescreened, 5 failed, 2 proceeded to screening
Other:
Site engagement:
  Leading site SIV (Feb 24)
  CHN5 site boost visit for recruitment discussion (Mar 06)
Oct 2026

## Slide 20: 1485-0018 PKKi/DME (Global recruitment status)
As of 11 Mar 2026:
Total Screened = 173
Total Randomized = 46
Screen Failure Rate = 69%

## Slide 21: 1485-0018 PKKi/DME (China recruitment status)
Chart: 
| 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295
Patients Enrolled/Randomized (Actual)
Patients Enrolled/Randomized (orginial plan) | 0 | 2 | 3 | 5 | 6 | 7 | 8
Patient Screened(Actual)
Patient Screened(Planned) | 3 | 6 | 9 | 15 | 18 | 21 | 24
As of 12 Mar 2026:
Total Screened = 0
Total Randomized = 0
Screen Failure Rate = 0%

## Slide 22: BI 771716 / Anti-C3 AB, Geographic Atrophy (GA), Development Plan
Today
22
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2 -
1497-0002
VERDANT
FPI
Jan 2025
LPI
Sep 2025
China Update:
GA pipeline consultation: Application submission planned by end of Apr.BB sent for global review on Mar 13. Discussion with global on consultation questions needed.
The GA scientific exchange follow up meeting with Prof. Sun on Mar 13. A high‑quality China dry AMD cohort to support GA studies under preparation by Prof. Sun’s team
Key results
Jan 2027
FPI
2 x Ph3 in GA
LPI
Oct 2028
Ph3 -
1497-0003/
1497-0004
Oct 2027
Apr 2030
NDA sub.
IA
May 2026
Oct 2029
Primary results
Dec 2030
Key results
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
Ph3 -
1497-0003/
1497-0004
Ph3 in GA
LPI
May 2030
NDA sub.
VERDANT Ph2b in GA, N=180 (US)
PoC/RoFD
Global Update:
aC3 light GBP reviewed by focused country
Notes: Izervay, the C5 inhibitor from Astellas, with registrational trials (GATHER1 & GATHER2 in US/EU) demonstrating positive results in reduction in GA lesion growth but no significant effect in visual function, was approved by FDA (2023), rejected by EMA, and now conditionally approved by PMDA in Sep 2025 waiving clinical data in Japanese patients. External information shows that an experts consultation panel was organized by CDE recently to evaluate Izervay approval in China waiving clinical data in Chinese patients. Local team is closely monitoring on the status.

## Slide 23
Status for CDE Meeting
CDE Meeting Types | Scope
Type I Meeting Type II Meeting | Type I: address the major safety issues encountered during the clinical trials of drugs, and the major technical issues in the R&D process of the breakthrough therapeutic drugs or held in other prescribed situations. Type II: held at the key stages of drug R&D process, including pre-IND meeting, EOP2/Phase III pre-clinical trial meeting, pre-NDA meeting and risk assessment and control meeting. Meetings to obtain CDE official opinions with minutes Data fully reviewed
Type III Meeting | Preliminary consultation, pipeline consultation, etc Non-binding meeting High level advices on 1) key issues and 2) data sufficiency to be addressed for consultation meeting, and 3) contents to be included in briefing book for consultation meeting.
*Although it may not be possible to obtain explicit answers from CDE, it is a chance for applicants/sponsors to ask questions about Agency's opinion.
As a scientific exchange meeting, no strong commitment is expected from either perspective. The meeting minutes will be reviewed and confirmed by BI team before finalization.
F2F meeting
Jul(75wds)*
Questions:
1.Does the Agency agree that a globally consistent GA population definition will be used, excluding non-AMD-related GA?
2.Does the Agency have comments on GA lesion size progression as the primary endpoint?
HAI submission
Mar/Apr
BB send to global review
Mar 13th
* might be written response
Slides preparation near BB almost final

## Slide 24: 1484-0020 COMPASS BI 771716 / Anti-C3 AB, GA, China Recruitment
The updated study timeline is confirmed by PI
Report of retrospective analysis on APVRS (Aug 2026): BI review comments have been sent to sponsor-investigator.
Cut-off date: 2026.03.02
Total Enrollment:
Prospective group: 11/70
Cross-sectional group: 62/120
Site initiation: 10/16

## Slide 25: 1484-0020 COMPASS BI 771716 / Anti-C3 AB, GA, China Recruitment
The updated study timeline is confirmed by PI.
Report of retrospective analysis on APVRS (Aug 2026): BI review comments have been sent to sponsor-investigator.
Cut-off date: 2026.03.02
Total Enrollment:
Prospective group: 11/70
Cross-sectional group: 62/120
Site initiation: 10/16

## Slide 26: BI 764524 / Anti-Sema3A, Diabetic Retinopathy (DR), Development Plan
DR: Diabetic Retinopathy; CI-DME: Center-Involved Diabetic Macular Edema; RNP: Retinol Non-Perfusion; PRP: Panretinal Photocoagulation
26
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2b -
1436-0007
CRIMSON
FPI
May 2024
Ph2b in NPDR without CI-DME, CRIMSON, N=178
Ph3 in NPDR without CI-DME
Ph3 in PDR
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
LPI
Apr 2026
Final results
Oct 2027
52-wk key results
May 2027
FPI
2 x Ph3 in NPDR wo CI-DME
1 x Ph3 in PDR
LPI
May 2029
52-wk
primary results
May 2030
Ph3 -
1436-0009/
1436-0010/
1436-0012
May 2028
Sep 2030
NDA sub.
Ph3 -
1436-0009/
1436-0010/
1436-0012
LPI
Oct 2030
CN NDA sub.
May 2029
PoC
Today
China Update:
  DR/DME based on Beijing Healthcare Insurance Study:
    Proposal approved and protocol under review via lectrona
    Contract and metformin analysis expected in Aug

## Slide 27: Eye Health KEE Mapping Overview
Criteria alignment
Initial screening (List 1)
List Expansion (List 2)
Scoring and Ranking
(Top-tier List)
Review and Refinement
(Final Top-tier List)
Aligned on the KEE evaluation criteria for each indication (DR/DME and AMD/GA).
Conducted the initial screening via Monocl database.
Supplemented additional KEE candidates with domestic data sources.
Scored and ranked KEEs from Lists 1 and 2 based on predefined criteria.
Reviewed and prioritized top KEEs.
Objective
To systematically map and prioritize KEEs to provide a solid foundation for strategic activities, including clinical trials, scientific meetings, advisory boards, publications, etc. in DR/DME and AMD/GA.
Mid-Nov. 2025
Dec. 2025
Mid-Jan. 2026
List 1 = 397
List 2 = 62
Total = 459
Prioritized top 15
Results
Notes: 基于既定的标准，识别重要KEE，为未来的活动（临床试验、会议活动、咨询、文章发表等）作为基础
流程：
  团队内部商定评估标准，纳入的维度和阈值
  Monocl初筛-list 1
  根据国内其他数据源增补list 1漏掉的其他KEE-list 2
  根据评估标准，对list 2进行打分和排序，筛选针对不同应用场景的top KEE list – list 3
  团队内部review，基于对专家的了解、既往的合作等，refine 形成 final list。
11.21 kick-off, align了标准
12月进行检索和排序
12.30 review名单和做refinement
1月中final

## Slide 28: Prioritized 15 KEEs – Key Activities in 2026
Name |  | Established Collaborations | Engagement Plan in 2026 | 
Xun, Xu | 许迅 | 2025 NAB Chair, THULITE Leading PI |  | 
Xiao Dong, Sun | 孙晓东 | Think Tank, GA consultation |  | Potential AMD/GA trials leading PI, VP
You Xin, Chen | 陈有信 | COMPASS Leading PI, Think Tank |  | COMPASS interim results release
Xiao Xin, Li | 黎晓新 |  |  | Candidate for VP
Ming Wei, Zhao | 赵明威 | 2025 NAB |  | Potential DR, GA trials leading PI
Xiao Rong, Li | 李筱荣 |  |  | 
Xiao Ling, Liang | 梁小玲 |  |  | 
Da Wei, Sun | 孙大卫 | COMPASS PI |  | 
Mei Xia, Zhang | 张美霞 | COMPASS PI |  | 
Ming, Zhang | 张明 | 2025 NAB, THULITE PI |  | 
Xiang, Ma | 马翔 |  |  | 
Su Yan, Li | 李甦雁 | COMPASS PI, 2025 NAB |  | 
Xin Yuan, Zhang | 张新媛 |  |  | 
Wen Bin, Wei | 魏文斌 |  |  | 
Li, Su | 苏莉 |  |  | 4Sight Network
Congress: International - ARVO, APVRS, EURETINA, APAO; Local - Retina China, CCOS (Congress of Chinese Ophthalmological Society); VP: Visionary Pathway
National Ad Board
Clinical trials
Congress
Global Ad Board
KEE mapping results has been communicated with global team and additional engagement activities will be discussed.
China KEE involvement into 2026 APVRS AB meetings are under planning

## Slide 29: Mental Health Assets

## Slide 30: Overview of Mental Health Early Assets for China Integration
2025
2028
Today
Jan
Apr
Jul
Oct
Jan
Apr
Jul
Oct
Jan
Apr
Jul
Oct
2026
2027
2028
ADHD & BPD – gPh1b PoM (1516-0003)
PoM, Jan 2027
BPD – gPh2a PoC (1516-0032)
Sep 2027
mGluR4 NAM
SSTR4
gPh1b PoM (1427-0015)
PoM, Apr 2027
OUD – gPh2 PoC
(1427-0016)
Oct 2028
GOATi
gPh1b PoM (1526-0006)
PoM, Aug 2028
FSS for gPh1b PoM(1526-0006)
Global Update:
PoM studies for mGluR4 and GOATi are ongoing with recruitment challenges.
PoM study for SSTR4 is under preparation.
China Update:
For mGluR4 and GOATi, China integration into PoC strategy under preparation
For SSTR4, possibilities of China integration into PoM discussed with global innovation team. Waiting for global team feedback. Preliminary site feasibility evaluation ongoing.

## Slide 31: BI 3031185 / mGluR4 NAM, Impulsivity, Development Plan
ADHD: Attention-Deficit/Hyperactivity Disorder; BPD: Borderline Personality Disorder; COA: Clinical Outcome Assessment
31
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph1b -1516-0003
FPI
Jan 2025
Ph1b PoM in ADHD & BPD, N=80 (GR)
Key results
Jan 2027
Observational study -
1516-0030
Today
Global Update:
MRD ongoing. Ames test negative.
PoM protocol has been amended to include only ADHD to accelerate the timeline.
Novel COA is ready for observational study 1516-0030, with FPI aimed in June.
China Update:
The database from Wuhan Mental Health Center was introduced to Global RWE on March 27.
China team will follow up with Global on COA adaptation.
Ph2a PoC in BPD
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
Ph2 -
1516-0006
Observational COA
Ph2 -
1516-0006
Ph2a PoC in BPD
Sep 2027
Jan 2029

## Slide 32: BI 1356225 / GOATi, Impulsivity SUD, Development Plan
Impulsivity SuD: Impulsivity Substance Use Disorders; OUD: Opioid Use Disorder; CUD: Cocaine Use Disorder; CSP: Chinese Society of Psychiatry
32
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph1b -
1427-0015
FPI
Jan 2025
Ph1b PoM, N=60 (US)
Key results
Apr 2027
Ph2 -
1427-0016/
1427-0017
Today
FPI
Ph2 PoC in Opioid Use Disorder (OUD)
Oct 2028
Key results
Oct 2030
PoC/RoFD
Ph2 -
1427-0016/
1427-0017
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
Ph2 PoC in Opioid Use Disorder (OUD)
Key results
PhII-enabling DDI studies
Global Update:
PoM: Timeline is heavily delayed due to poor recruitment. Protocol amendment considered to include healthy participants.
China Update:
Waiting for global feedback regarding the evaluation material provided by China team.
Notes: PoM for OUD（Ph1b）进行中，入组缓慢。主要原因是4-CSRTT筛查冲动失败率高。已经在9月修改了protocol。本来预计26年8月完成研究，但很可能完不成。会看看改了protocol之后入组会不会加快，年底再过IUPC
中国 integration等总部ph1b年底的IUPC再进一步沟通

## Slide 33: BI 3776528 / SSTR4 Agonist, CI PSD, Development Plan
CI PSD: Cognitive Impairment in Psychosis Spectrum Disorders; HH: hippocampal hyperactivity
33
2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph1 –
1526-0001
FPI
Jan 2025
Ph1 SRD & MRD, N=118
Key results
Today
Ph1b PoM (US only)
Global Update:
MRD: CNS related AE in DG 2 and 3 (40 and 80 mg BID) need further evaluation prior to move on to the next dose step.
PoM: PennCNB was found not a reliable biomarker for HH. Study design is still under discussion.
China Update:
Kicked off China integration into PoM discussion with Global on March 23.
Preliminary site feasibility evaluation ongoing.
Ph1b -
1526-0006
FPI
Key results
Aug 2028
Oct 2026
Ph2 -
1526-0014
Ph2 PoC
FPI
Mar 2030
Pan-Asian Ph1/DDI
Aug 2026
CTA Review + EC + HGRAC + 1st SIV
1st SIV
CTA Sub
Ph2 -
1526-0014
Ph2 PoC
Notes: SRD和MRD预计延迟4个月，26年8月完成
PoCP（PoM）不变，目前计划只在US做
2期研究的plan（path to PoC）会在今年底上IUPC
中国integration plan，年底后与global catch up

## Slide 34: Mental Health Ongoing Projects
Project | Description | Leading KEE | Key Update | Next Step
BJ-PERFECT study | ECR study Aim to validate the functional capacity evaluation tool (BJ-PERFECT VR) and explore CIAS link to function. Meanwhile collect disease and economic burden of CIAS | 石川 | Recruitment completed. 160 pts (150 planned) and 757 HCs (750 planned) have been enrolled. | Enrollment completed. Next step is data analysis and research report writing.
CIAS review | Comprehensive review of CIAS literature in China, including epidemiology, burden and impact, potential pathophysiological mechanisms, clinical assessment methods, and treatment updates. | 司天梅 蒲城城 | Manuscript is resubmitted to the Jornal 《中国心理卫生杂志》 on 10th Oct. Revised manu is resubmit on 30th Dec. | Published
Checklist Development | Develop a simplified checklist using Delphi methodology for quick screening/identification of CIAS | 石川 | The project is completed as planned | -Completed.
CONNEX Pooled publication ​ | Oral presentation at SIRS congress – Apr.1st ​ Manuscript: ​ Prof. Gang Wang and Prof. Zhang had reviewed and provided feedback​ Target journal: Lancet Psychiatry ​ 1st Submission date: June 12th, 2025​ 2nd Submission date: Aug.29th , 2025 (comments received on Aug.5th)​ Published by Lancet Psychiatry on 13th Nov.
Efficacy and safety of iclepertin for cognitive impairment associated with schizophrenia (CONNEX programme): results from three phase 3 randomised controlled trials - The Lancet Psychiatry

## Slide 35: Thank You!