Agenda

Portfolio Executive Committee (PEC)

Review Meeting

_____________________________________________

Thursday, 23Apr2026

02:00-5:30

Meeting room: Microsoft Teams Meeting/28FC6

Agenda by TA

| TA | Meeting time |
| --- | --- |
| Common session | 15 min |
| INFL | 60 min |
| ONCO | 20 min |
| CRM | 70 min |
| MHEH | 10 min |

|  | Topic | Speaker | Time | Duration | Decisions/Follow up actions/Advice | Responsible person | Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Opening | Wei Zhang | 02:00-02:05 | 5 min |  |  |  |
|  | Follow-up actions (cross-TA topics) | Action owners | 02:05-02:15 | 10 min |  |  |  |
|  | TA INFL |  |  |  |  |  |  |
|  | Portfolio updates-INFL | Yuting Li, Ying Chen, Bo Wang, Yayun Zhu | 2:15-2:35 | 20 min | cGASi SLE Ph2 study - Work with HP Communication team and the site on internal/external communications highlighting this successful CTA 30wd pathway pilot. | Ying Zhang | May PEC |
|  | (A) Verducatib - Earlier NDA Submission Feasibility Analysis- Preliminary Assessment for PEC Advice | Yayun Zhu | 2:35-2:50 | 15 min | - PEC recommended clarifying the responsible parties and respective prerequisites for the accelerated submission and approvals. - Revise the slides accordingly and share with Dr. Zhang and Kun Xia for review. | Yayun Zhu/Helen Tao | Early May 2026 |
|  | (I) Exploring patients’ experiences with nerandomilast: a longitudinal qualitative research among IPF patients | Guoze Feng | 2:50-3:05 | 15 min |  |  |  |
|  | (I) Epidemiology and Disease Burden of Systemic Sclerosis (SSc) in Beijing : A Study Based on the Beijing Claims Database | Shuli Li | 3:05-3:15 | 10 min |  |  |  |
|  | TA ONCO |  |  |  |  |  |  |
|  | Follow-up actions & Portfolio updates-ONC | Catherine Zhang, Juno Hu, Donglei Zhu, Nick Xue | 3:15-3:35 | 20 min |  |  |  |
|  | Break |  | 3:35-3:45 | 10 min |  |  |  |
|  | TA CRM |  |  |  |  |  |  |
|  | Follow-up actions & Portfolio updates-CRM | Meiruo Liu, Lian Zheng, Yuling Zhang, Julia Zhu, Junxiu Che | 3:45-4:15 | 30 min | GGY2Ra. - PEC agreed with team proposal to appoint Prof Linong Ji as the leading PI for Ph3 1507-0010 study. - Follow up with global team on the inclusion of Prof. Ji in the global Executive Committee. | Project team | May PEC |
|  | (A) TENACITY & persisTENce evaluation | Yuling Zhang | 4:15-4:35 | 20 min | - PEC supports the co-leading PI proposal and reminded the team to be cautious in the communication strategy. - Team to approach Prof. Wang at the earliest opportunities, considering current recruitment challenge. | Project team | May PEC |
|  | (E) Metalyse-IIS proposal: Blood Pressure Lowering and Thrombolysis: Concurrent vs Sequential Management in Acute Ischemic Stroke (BALANCE) | Luoki Liu | 4:35-4:55 | 20 min | ☐For information sharing (I) ☐For advice collection (A) ☑For content endorsement (E) Endorsed by PEC. - Team confirmed that there is no label or registrational intention for this trial. - Boehringer’s rights will need to be further confirmed in the contract. | Luoki Liu | May PEC |
|  | # TA MHEH |  |  |  |  |  |  |
|  | # Portfolio updates-MHEH | Yuting Li, Freya Zhu | 4:55-5:05 | 10 min | - Considering potential ethnic differences in GA and the lack of sufficient data to understand the disease in China, PEC suggested following up on the COMPASS ECR prospective cohort. |  |  |
|  | Close |  | 5:05 | 185 min |  |  |  |

*Purpose of the presentation: Information sharing (I), Advice collection (A), and Content Endorsement (E)

| Standing members & Standing invitation & Guests |  |
| --- | --- |
| Standing members (Full meeting participation): Chair: - Head of Medicine: Wei Zhang Function Heads: - Head of TA CRM Medicine: Emma Xie - Head of TA INFL Medicine: Helen Tao - Head of TA MHEH Medicine and Head of PPM: Meiruo Liu - Head of TA Oncology Medicine: Sally Chen - Head of RA: Kuncy Xia - Head of CDO: Jessie Song - Head of BDS: Hongjie Deng - Head of RWE: Qiang Li - Head of PSPV: Ling Xu - Head of QM: Jennifer Tong - Head of X-TA Excellence: Grace Wang - Head of Development CMC China: Yanling Wang - Medicine Insights and PMO: Harry Hua Guests: - HR: Michelle Zhou | Standing invitation: - Head of HK Medicine: Karen Yuen - Head of TW Medicine: Carol Yang |
| Members per TA (Oncology) |  |
| - aTAH: Elaine Yu - RPL: Catherine Zhang - RA: Lijie Yu - CDO: Catherine Zhang - BDS: Eric Song - PSPV: Ruoyi Gu - RWE: Jill Zhan - QM: May Yu - CD Physician: Juno Hu, Donglei Zhu, Nick Xue |  |
| Members per TA (Inflammation) |  |
| - aTAH: Lindsay Xu - RPL: Yuting Li - RA: Lincy Liu - CDO: Ying Zhang - BDS: Hui Wang - PSPV: Hui Huang - RWE: Guoze Feng - QM: Vera Zhang - CD Physician: Ying Chen, Bo Wang, Yayun Zhu |  |
| Members per TA (CRM) |  |
| - aTAH: Jenny Yang, Di Ruan - RPL: Meiruo Liu - RA: Doris Han, Lincy Liu - CDO: Angela Xiao, Alex Zhang - BDS: Fei Ji - PSPV: Yanjie Shen - RWE: Jill Zhan - QM: Liuqiong Wu - CD Physician: Julia Zhu, Yinan Zhu, Lian Zheng, Yuling Zhang - MSL manager (Lytics MA Lead): Leo Bao |  |
| Members per TA (MHEH) |  |
| - RPL: Yuting Li - RA: Lincy Liu - CDO: Alex Zhang - BDS: Harry Hua - PSPV: Yingxia Zhang - RWE: Raven Zheng - QM: Juan Sun - CD Physician: Freya Zhu, Jingbo Xiao |  |