## Slide 1: Portfolio Executive Committee (PEC) Review Meeting Last PEC Meeting Action Following Up
  25th Apr, 2024 | 10min

## Slide 2: Actions Tracking Sheet
TA | Follow-up actions | Responsible | Due | Update | Status
CREA | Metalyse local competitor Fenghua STEMI: To provide a more detailed timeline with its initial submission and re-submission. AIS: To further get the intelligence information for the current status. | LPT | Next PEC | Will update the competitor’s status during the portfolio session. | Done
INFL | Spesolimab SCRIPTOR study To provide the study termination reasons. | Ying Chen | Next PEC | An email was sent to Dr. Zhang on Apr11 Global HAMA decided to stop SCRIPTOR study in China, due to budget increase and timeline delay caused by data export restrictions from CAC (中国国家互联网信息办公室) China team is requesting to continue the study. | Done
Onco | Zongertinib NDA strategy To communicate the potential risks of Accelerated Approval strategy with Marketing and Access colleagues. | LPT | Next PEC | Discussion with Marketing (Alice Sha, Xia Hua) and Market Access (Dongdong Liu, Emily Hu) occurred on 29 Mar After the in-depth discussion, everyone on the meeting share the same understanding about the NDA strategy, potential scenarios and associated risks Marketing and Market Access will give a heads-up about the potential risks to their management team as appropriate Scenario of 1L NSCLC AA approval will be further analyzed | Done