## Slide 1: Portfolio Executive Committee (PEC) Review Meeting Portfolio Overview Update - Inflammation
Yuting Li/Ying Chen Apr 25th , 2024
CONFIDENTIAL and for INTERNAL use only!
25mins

## Slide 2: One Page Summary-----Inflammation
TA | Ongoing |  | Endorsed | Under Evaluation | Next wave
Inflammation | Spesolimab GPP EAP （1368.77） |  |  | BI 3032950 (TREM-1 Antagonist) / IBD；CD；UC-Ph2b | BI 765250 (PD-1 agonist) / SSc
 | Spesolimab GPP (1368.25) |  |  | BI1291583 (CatC inh) nCF Bronchiectasis | BI 1819479 (Autotaxin Inhibitor) /SSc
 | Nintedanib (TKI) PF-ILD CN PAC - Ph3b (1199.434) |  |  | BI 3000202 (cGAS inh.) Interferonopathy | BI765423 (Anti-IL11 mAb) IPF/PPF
 | Spesolimab/Netherton Syndrome-Ph2/3 (1368.104) |  |  |  | BI 3000202 (cGAS inh.) SSc
 | Nerandomilast(PDE4b inhibitor)/ IPF Ph3 (1305.14) |  |  |  | BI 3009947 (STING inh.) SSc
 | Nerandomilast (PDE4b inhibitor)/ PPF Ph3 (1305.23) |  |  |  | BI 3720931 (GTC) (LV gene therapy) CF
 | BI 706321 (RIPK2 inhibitor) /CD-Ph2b (1425.4) |  |  |  | BI 3731579 (NOX4 inh.) IPF
 | Avenciguat(sGC activator)/ SSc- ph2 (1366.31) |  |  |  | BI 3009947 (STING inh.) Interferonopathy
 | Spesolimab/Hidradenitis suppurativa -Ph2/3（1368.98） |  |  |  | BI 3810477 (anti-CTGF) in IPF/PPF
 | Sepsolimab GPP Post marketing requriement (1368.120 ) (GPP flare retreatment) |  |  |  | BI 1015550 (PDE4b inhibitor)/ SSc
 | BI 1839100 (TRPA1 antagonist) IPF/PPF cough ph2 (1490.4) |  |  |  | 
 | Spesolimab (PG) ph3 (1368-0140) |  |  |  | 
 | BI 1819479 (Autotaxin inhibitor) IPF/PPF ph2 (1462.4) |  |  |  | 
Timeline: > 3 months delay
Strategic issue: project to be terminated, China integration/development undermined;
Operational issue: major enrollment delay, significantly poor retention;
Regulatory issue: negative comment from authority, major concerns due to regulation change;
Not meeting primary end point;
Quality: ≥ 1 critical and/or ≥ 4 major site audit observations; inspection readiness with critical issues; critical NC report
On track
Timeline: 1-3 months delay or potential delay;
Strategic issue: global strategy uncertain; China integration/development at risk, insufficient China sample size;
Operational issue: slow enrollment, retention rate lower than plan;
Regulatory issue: technical and/or dossier issues and/or deficiency letter with potential impact to approval and/or approval timeline;
Quality: 3 major site audit observations, inspection readiness with significant issues; major NC report
Interferonopathy:干扰素病
PG: pyoderma gangrenosum坏疽性脓皮病
Green font: Updates from last PEC
Blue font: Not covered in following detailed updates
TA priority assets： Spesolimab, Catci;
cGAS inhibitor, PD-1 agonist
Notes: Peresolimab PoC

## Slide 3: Nerandomilast Asset Team China Visit Workshop on Feb 22nd
Asset team members (Asset lead, value lead and sPM) discussed with China team on evidence generation and launch preparation topics.
Further deep dive with evidence team on Apr 29 regarding
    China joining CTD-ILD and Pediatric program
    Global support to meet local registration timeline

## Slide 4: Ongoing: Nerandomilast (PDE4b inhibitor) Idiopathic Pulmonary Fibrosis(IPF) and Progressive Fibrosing Interstitial Lung Disease(PF-ILD) (Ph3)
Sep 26
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Ph3-1305.14
Ph3-
1305.14
FSS
Dec 2024
CN ML N=97
TW: N=22
China PK 1305.24
IPF N=1077
US NDA Sub
Jan 2025
US NDA appr.
Sep 2025 – Jan 2026
NDA review for IPF
NDA Sub
NDA App
China
CTA Review + EC + HGRAC + 1st SIV (5.5 M)
Dec2022
CTA Sub
1st SIV
Jul2022
PF-ILD N=1078
Ph3-1305.23
CN PK
17Mar2023
SIV
CTA Review + EC + HGRAC (6M)
LPO
13 Jan 2023
CTR
CTA Sub
Aug 2024
Ph3-
1305.23
Allocated China ML N=155, TW: N=28
CTA Review + EC + HGRAC + 1st SIV (5.5 M)
CTA Sub
14Jul2023
Jan 2024
LSS: Last subject screening
LSLV: Last subject last visit
DBL: database lock
HAI: Healthy authority interaction
OLE: Open label extension
CAPA: Corrective and Prevention Action
BTD: Breakthrough designation
Feb2025
We are here
Nov 8
DBL
5Jun 2023
US NDA Sub
May 2025
US NDA appr.
Jan – May 2026
NDA review for PPF
NDA Sub
Ph3 OLE-
1305.31
Ph3 OLE-
1305.31
Ph3 OLE
FSS
Sep 2024
LSC
Jan 2027
CTA Review + EC + HGRAC + 1st SIV
1Nov2023
Sep 2023
FSS
Sep 2024
LSC
Jan 2027
LSS
Last patient Primary
endpoint
Feb 2026(best case), May 2026 (base case)
Apr 2026 (best case)
Jun 2026(base case)
Jun 2025
Last patient Primary
endpoint
NDA App
Considering benefit of BTD for market access, team preliminarily aligned to apply for BTD if Ph3 data is promising.
CAPA for for-cause audit at CHN1 site under development, to be finalized by end Apr
Notes: 1. For BE study, two studies are planned (9 mg, 18 mg). There might be update in the middle of this year. Team will closely monitor the update.

## Slide 5: Nerandomilast (PDE4b inhibitor) Trial Update –15Apr2024
FIBRONEER |  | Global | China mainland | Taiwan​
Fibroneer-IPF 1305.14 | Total Screening | 1720+16 rescreen | 168+1 rescreen | 41​
 | Total randomized | 1177 | 97 | 22​
 | Early discontinuation | 169→174 (14%) | 17→17(18%) | 2, 9%​
Fibroneer-ILD 1305.23 | Total Screening | 1785 | 251 | 37​
 | Total randomized | 1178 | 155 | 28​
 | Early discontinuation | 136→141 (12%) | 20→ 23 (15%) | 1→2 (8%)​
FIBRONEER-ON: EC preparation and site initiation is on track.
Notes: CTD-ILD study will generate evidence to help address 2 prioritized gaps: Data for rheumatologists, and impact of immunosuppressants on efficacy and safety.
Data on combination therapy with immunosuppressants (IS) is needed to bridge the evidence gap and support the BI 1015550 in PPF.​
​
The main objective of the CTD-ILD study is evidence generation for safety.​
​
Results will support the PPF indication and address the evidence gap for rheumatologists, helping to meet the current forecast.

## Slide 6: Fibroneer : Ranking Related to Permanent Discontinuations - 09 Apr 2024untry ranking (IRT)
1305-0014
1305-0023

## Slide 7: Focus Countries Review – 9Apr2024
As of Dec 20th, 2023
US 10.1% ; Japan 11.6%；China 14.8%；Spain 6.2%；France 13%；Germany 11.5%；Italy 10.0%；UK 10.0%
Chart: 1405-0014 Patient retention
| US | Japan | China | Spain | France | Germany | Italy | UK
Pts Randomized | 196 | 135 | 97 | 77 | 98 | 80 | 48 | 18
ongoing | 165 | 113 | 80 | 68 | 88 | 68 | 44 | 16
discontinued | 31 | 22 | 17 | 9 | 10 | 12 | 4 | 2
US 15.8%；Japan 16.3%；China 17.5%；Spain 11.7%；France 10.2%；Germany 15.0%；Italy 8.3%；UK 11.1%
Chart: 1405-0023 Patient retention
| US | Japan | China | Spain | France | Germany | Italy | UK
Pts Randomized | 139 | 146 | 155 | 65 | 46 | 52 | 40 | 30
ongoing | 125 | 129 | 132 | 61 | 40 | 46 | 36 | 27
discontinued | 14 | 17 | 23 | 4 | 6 | 6 | 4 | 3

## Slide 8: Fibroneer-IPF 1305-0014 Global recruitment information- 20231207
Global recruitment source data |  |  |  |  |  |  |  |  |  |  |  | 
Months | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23
Patients Enrolled/Randomized (Actual) | 0 | 1 | 4 | 5 | 22 | 69 | 221 | 369 | 574 | 905 | 1124 | 1177
Patients Enrolled/Randomized (Planned) | 0 | 1 | 6 | 29 | 76 | 167 | 265 | 364 | 473 | 585 | 686 | 780
Patient Screened(Actual) | 0 | 3 | 6 | 30 | 124 | 295 | 609 | 852 | 1399 | 1720 | 1720 | 1720
Patient Screened(Planned) | 3 | 9 | 31 | 91 | 173 | 299 | 432 | 568 | 702 | 830 | 960 | 1084
Chart: Global recruitment source data
| 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
Patients Enrolled/Randomized (Actual) | 0 | 1 | 4 | 5 | 22 | 69 | 221 | 369 | 574 | 905 | 1124 | 1177
Patients Enrolled/Randomized (Planned) | 0 | 1 | 6 | 29 | 76 | 167 | 265 | 364 | 473 | 585 | 686 | 780 | 886 | 993 | 1080 | 1080
Patient Screened(Actual) | 0 | 3 | 6 | 30 | 124 | 295 | 609 | 852 | 1399 | 1720 | 1720 | 1720
Patient Screened(Planned) | 3 | 9 | 31 | 91 | 173 | 299 | 432 | 568 | 702 | 830 | 960 | 1084 | 1225 | 1360 | 1450 | 1450
Total Screened = 1720+16 rescreen
Total Randomized = 1177
Total Screen failure = 559
Screen failure rate = 32%
Early discontinuation=90→111 (9%)
TLR planned 9Sep2024

## Slide 9: Fibroneer-IPF 1305-0014 China recruitment information- 20231207
Months | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | 5-Jun-23 | Jul-23 | 7- Aug-23
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 2 | 20 | 46 | 76 | 96 | 97
Patients Enrolled/Randomized (Re-Planned base on global best case) | 0 | 0 | 0 | 2 | 20 | 45 | 75 | 105 | 135
Patient Screened(Actual) | 0 | 0 | 8 | 39 | 75 | 141 | 168 | 168 | 168
Patient Screened(Re-Planned base on global best case) | 0 | 0 | 8 | 39 | 75 | 115 | 176 | 176 | 176
Chart: Patient Enrollment Status (China mainland)
| 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 2 | 20 | 46 | 76 | 96 | 97
#REF! | 1
Patient Screened(Actual) | 0 | 0 | 8 | 39 | 75 | 141 | 168 | 168 | 168
#REF! | 1
Patients Enrolled/Randomized (Re-Planned) | 0 | 0 | 0 | 2 | 20 | 45 | 75 | 105 | 135
Patient Screened(Re-Planned) | 0 | 0 | 8 | 39 | 75 | 115 | 176 | 176
Notes: 主要筛选失败原因：HRCT 24例，中国特殊的筛败原因：合并HBV 感染或TB 感染6例，以及撤回知情8例。

## Slide 10: 1305-0014 Taiwan recruitment status (Cut off date: 5 Sep 2023) Recruitment completed; Global LSR: 7 Aug 2023, Local LSR: 27 July 2023
Chart: 
| Dec-232 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23
Screening(Actual) | 0 | 0 | 2 | 14 | 18 | 37 | 41
Randomized (Actual) | 0 | 0 | 0 | 1 | 4 | 9 | 14 | 22
Screening (re-projected based on global status) | 0 | 0 | 2 | 14 | 18 | 26 | 33
Randomized (re-projected based on global status) | 0 | 0 | 0 | 1 | 4 | 9 | 14 | 18 | 23
10
Months | 2021-12 | 2023-1 | 2023-2 | 2023-3 | 2023-4 | 2023-5 | 2023-6 | 2023-7 | 2023-8
Screening (re-projected plan) | 0 | 2 | 6 | 10 | 14 | 26 | 33 | Global LPS in Jun 23 | -
Screening (Actual) | 0 | 0 | 2 | 14 | 18 | 37 | 41 | - | -
Randomized (re-projected plan) | 0 | 0 | 0 | 1 | 7 | 9 | 14 | 18 | 23
Randomized (Actual) | 0 | 0 | 0 | 1 | 4 | 9 | 14 | 22 | LPR in July 23
Total Screened = 41
Total Randomized = 22
Total in Screening = 0
Total Screen failure = 19
Screen failure rate = 46%
Early discontinuation= 2, 9%

## Slide 11: Fibroneer-ILD 1305-0023 Global recruitment information- 20231215
Global recruitment source data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Months | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 1 | 7 | 19 | 55 | 126 | 196 | 287 | 392 | 572 | 713 | 931 | 1008 | 1178
Patients Enrolled/Randomized (Planned) | 0 | 3 | 10 | 37 | 85 | 158 | 259 | 368 | 482 | 594 | 709 | 809 | 919 | 1033 | 1129 | 1129
Patient Screened(Actual) | 0 | 0 | 2 | 5 | 34 | 84 | 204 | 314 | 447 | 674 | 910 | 1133 | 1420 | 1785 | 1785 | 1785
Patient Screened(Planned) | 0 | 8 | 26 | 81 | 161 | 269 | 414 | 561 | 717 | 897 | 1097 | 1297 | 1497 | 1700 | 1700 | 1700
Chart: Global recruitment source data
| 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 1 | 7 | 19 | 55 | 126 | 196 | 287 | 392 | 572 | 713 | 931 | 1008 | 1178
Patients Enrolled/Randomized (Planned) | 0 | 3 | 10 | 37 | 85 | 158 | 259 | 368 | 482 | 594 | 709 | 809 | 919 | 1033 | 1129 | 1129
Patient Screened(Actual) | 0 | 0 | 2 | 5 | 34 | 84 | 204 | 314 | 447 | 674 | 910 | 1133 | 1420 | 1785 | 1785 | 1785
Patient Screened(Planned) | 0 | 8 | 26 | 81 | 161 | 269 | 414 | 561 | 717 | 897 | 1097 | 1297 | 1497 | 1700 | 1700 | 1700

## Slide 12: Fibroneer-ILD 1305-0023 China recruitment information- 20231207
China recruitment source data |  |  |  |  |  |  |  |  |  |  |  |  | 
Months | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 1 | 10 | 23 | 38 | 57 | 90 | 114 | 132 | 154 | 155
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 1 | 10 | 22 | 38 | 54 | 74 | 94 | 114 | 134 | 149
Patient Screened(Actual) | 0 | 0 | 3 | 20 | 40 | 66 | 108 | 150 | 186 | 231 | 251 | 251 | 251
Patient Screened(Planned) | 0 | 0 | 6 | 21 | 42 | 66 | 94 | 134 | 174 | 220 | 248 | 248 | 248
Chart: Patient Enrollment Status(China mainland)
| 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
Patients Enrolled/Randomized (Actual) | 0 | 0 | 0 | 1 | 10 | 23 | 38 | 57 | 90 | 114 | 132 | 154 | 155
Patients Enrolled/Randomized (Planned) | 0 | 0 | 0 | 1 | 10 | 22 | 38 | 54 | 74 | 94 | 114 | 134 | 149
Patient Screened(Actual) | 0 | 0 | 3 | 20 | 40 | 66 | 108 | 150 | 186 | 231 | 251 | 251 | 251
Patient Screened(Planned) | 0 | 0 | 6 | 21 | 42 | 66 | 94 | 134 | 174 | 220 | 248 | 248 | 248

## Slide 13: Fibroneer-ILD 1305-0023 Taiwan recruitment status (Cut off date: 12 Dec 2023)
1305-0014 & 1305-0023
13
Chart: 
| 22-Dec | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23
Screening (planned) | 0 | 2 | 4 | 7 | 10 | 13 | 17 | 20 | 23 | 26 | 28 | 28
Screening(Actual) | 0 | 0 | 2 | 3 | 5 | 10 | 14 | 18 | 26 | 33 | 37
Randomized (Planned) | 0 | 0 | 2 | 4 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 20
Randomized (Actual) | 0 | 0 | 0 | 1 | 2 | 2 | 6 | 9 | 13 | 19 | 22 | 28
Months | 2021-12 | 2023-1 | 2023-2 | 2023-3 | 2023-4 | 2023-5 | 2023-6 | 2023-7 | 2023-8 | 2023-9 | 2023-10 | 2023-11
Screening (planned) | 0 | 2 | 4 | 7 | 10 | 13 | 17 | 20 | 23 | 26 | 28 | 28
Screening (Actual) | 0 | 0 | 2 | 3 | 5 | 10 | 14 | 18 | 26 | 33 | 37 | LPS in Oct
Randomized (Planned) | 0 | 0 | 1 | 4 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 20
Randomized (Actual) | 0 | 0 | 0 | 1 | 2 | 2 | 6 | 9 | 13 | 19 | 22 | 28 (LPI)
Total Screened = 37
Total Randomized = 28
Total Screen failure = 9
Screen failure rate = 24%
Early discontinuation= 0, 0%

## Slide 14: 1305-0014 Early Discontinue Patient Status：CHN1 cut off 15Apr2024
Total EOT | Death | Agreed to come back in 52 week | Not agreed to come back in 52 week
7 (out of 7) | 0 | 1 | 6
No. | Subject ID | Subject Status | EOT- Discontinue Date | Discontinue Reason | if Agreed to come back in 52 week? | 52 Weeks visit date | EOS
1 | 1415600101 | Study Discontinued | 2023-12-18 | Patient decision | N – only agree the remote visit, planned on 18Apr2024 | 18-Apr-24 | 
2 | 1415600104 | Study Discontinued | 2023-10-11 | Patient lost to follow up on 18Aug2023, investigator contacted him several times and confirmed EOT on 11Oct2023 | N – only agree the remote visit, planned on 18Apr2024 | 12-Apr-24 | 
3 | 1415600105 | Study Discontinued | 2023-12-12 | Investigator decision | Y – On site visit on 16Apr2024，and will complete FVC on 29Apr2024. | 22-Apr-24 | 
4 | 1415600106 | Study Discontinued | 2023-12-4 | Patient decision-lack of efficacy | N | 4-May-24 | 
5 | 1415600110 | Study Discontinued | 2023-12-26 | Patient decision-decreased of pulmonary function | N | 14-Jun-24 | 
6 | 1415600111 | Study Discontinued | 2023-11-21 | The symptom of cough and shortness of breath increased, and early discontinue from the study was recommended by investigator | N | 3-Jul-24 | 
7 | 1415600112 | Study Discontinued | 2023-10-24 | Patient decision- due to AE Insomnia, night sweats since 20Sep2023 | N | 3-Jul-24 | 

## Slide 15: 1305-0014 Early Discontinue Patient Status：10 cut off 15Apr2024
Total EOT | Death | Agreed to come back in 52 week | Not agreed to come back in 52 week
10 | 2 | 7 | 1
No. | Subject ID | Subject Status | EOT- Discontinue Date | Discontinue Reason | if Agreed to come back in 52 week? | 52 Weeks visit date | EOS
1 | 1415604201 | Study Discontinued | 23-May-23 | Adverse Event | Y – Patient is currently hospitalized, so V10 is postponed | 29-Mar-24 | 
2 | 1415601212 | Study Discontinued | 4-Aug-23 | Subject Decision-AE | Y | 10-Jul-24 | 
3 | 1415601703 | Study Discontinued | 2-Aug-23 | Subject decision | Y | 31-Jul-24 | 
4 | 1415604402 | Study Discontinued - fetal | Unknown | The patient has been lost to follow-up. Site contacted the patient on August 9 and learned through the patient's family that the patient had passed away. The specific time is unknown. | NA | NA | NA
5 | 1415601802 | Study Discontinued | 16-Oct-23 | Subject Decision | Y | 27-Jun-24 | 
6 | 1415602001 | Study Discontinued | 23-Oct-23 | Subject decision | Y | 7-Jun-24 | 
7 | 1415605305 | Study Discontinued - fetal | 15-Nov-23 | The patient died on November 16, 2023 | NA | NA | NA
8 | 1415601208 | Study Discontinued | 5-Dec-23 | Subject decision- AE | N-Refuse to answer the phone, site will be contacted regularly according to the visit plan | 1-Jul-24 | 
9 | 1415601801 | Study Discontinued | 22-Dec-23 | Subject decision | Y | 20-May-24 | 
10 | 1415601201 | Study Discontinued | 17-Jan-24 | Subject decision | Y | 10-May-24 | 

## Slide 16: 1305-0023 Early Discontinue Patient Status： CHN1 cut off 15Apr2024
Total EOT | Death | Agreed to come back in 52 week | Not agreed to come back in 52 week
6 (out of 13) | 0 | 0 | 6
No. | Subject ID | Subject Status | EOT- Discontinue Date | Discontinue Reason | if Agreed to come back in 52 week? | 52 Weeks visit date | EOS
1 | 2315600102 | Study Discontinued | 2024-1-9 | 2024-1- 6 CT scan showed aggravation, the patient considered to enroll in other trials and asked to early discontinue from this trial. | N – only agree the remote visit, planned on 18Apr2024 | 17-Apr-24 | 
2 | 2315600105 | Study Discontinued | 2023-12-12 | Patients enrolled for half a year, symptoms did not change significantly, FVC, DLCO significantly decreased in October compared with Mar2023, it is recommended to early discontinue. | N | 17-May-24 | 
3 | 2315600109 | Study Discontinued | 2023-12-11 | Based on the 2023-12-5 CT results, the patient was recommended to enroll in another trial. | N | 12-Jul-24 | 
4 | 2315600110 | Study Discontinued | 2023-9-21 | Patient thought he took the placeable and rejected to do any further visit since 21Sep2023. | N | 24-Jul-24 | 
5 | 2315600113 | Study Discontinued | 2023-12-12 | The patient's symptoms did not improve significantly, and he agreed to early discontinue from this trial. | N | 26-Aug-24 | 
6 | 2315600116 | Study Discontinued | 2023-12-5 | Patient feel that symptoms are aggravated, and high-dose hormone therapy is prescribed. | N | 30-Jul-24 | 

## Slide 17: 1305-0023 Early Discontinue Patient Status：17 cut off 15Apr2024
Total EOT | Death | Agreed to come back in 52 week | Not agreed to come back in 52 week
17 | 1 | 6 | 10
No. | Subject ID | Subject Status | EOT- Discontinue Date | Discontinue Reason | if Agreed to come back in 52 week? | 52 Weeks visit date | EOS
1 | 2315601303 | Study Discontinued | 14-Jun-23 | Subject decision-Perceived Lack of Efficacy | N-Patient only receives remote visits. Due to his serious condition (currently receiving oxygen 24 hours a day), he cannot go out. | 20-Mar-24/ 19-Mar-24(a) | 
2 | 2315602901 | Study Discontinued - fetal | 18-Jun-23 | Death |  | NA | 
3 | 2315601801 | Study Discontinued | 18-Aug-23 | Other | N-Patient clearly expressed his unwillingness to accept any form of follow-up and to come to the hospital at 52 weeks | 25-Jul-24 | 
4 | 2315600202 | Study Discontinued | 27-Sep-23 | Acute ILD Exacerbation | Y | 5-Jul-24 | 
5 | 2315602302 | Study Discontinued | 18-Oct-23 | Other-Perceived Lack of Efficacy | Y | 25-May-24 | 
6 | 2315605505 | Study Discontinued | 28-Oct-23 | Subject decision | N-The patient is in serious condition and cannot come to site. He agreed to collect the survival status after 52 weeks. | 26-Sep-24 | 
7 | 2315600911 | Study Discontinued | 7-Nov-23 | Other-Patient didn’t meet in/ex criteria. | Y | 7-Oct-24 | 
8 | 2315604801 | Study Discontinued | 21-Nov-23 | Subject decision | N-subject refused follow-up visits and W52 visits, and only accepted telephone follow-up. | 6-Jun-24 | 
9 | 2315601210 | Study Discontinued | 13-Dec-23 | Subject decision | N-subject refused follow-up visits and W52 visits, and only accepted telephone follow-up. | 28-Aug-24 | 
10 | 2315603011 | Study Discontinued | 20-Dec-23 | Subject Decision | N-subject refused follow-up visits and W52 visits, and only accepted telephone follow-up. | 28-Oct-24 | 

## Slide 18: 1305-0023 Early Discontinue Patient Status：17 cut off 15Apr2024
Total EOT | Death | Agreed to come back in 52 week | Not agreed to come back in 52 week
17 | 1 | 6 | 10
No. | Subject ID | Subject Status | EOT- Discontinue Date | Discontinue Reason | if Agreed to come back in 52 week? | 52 Weeks visit date | EOS
11 | 2315601802 | Study Discontinued | 22-Dec-23 | Subject decision | Y | 1-Oct-24 | 
12 | 2315604501 | Study Discontinued | 28-Dec-23 | Subject decision-Perceived Lack of Efficacy | N-subject refused follow-up visits and W52 visits, and only accepted telephone follow-up. | 25-Oct-24 | 
13 | 2315600804 | Study Discontinued | 31-Jan-24 | Acute ILD Exacerbation | N- The patient‘s condition worsened acutely. The patient is currently in critical condition and unable to cooperate in completing any follow-up monitoring. | 30-Aug-24 | 
14 | 2315606302 | Study Discontinued | 31-Jan-24 | Lung transplant | N- The patient refused to come to the hospital for fear of increasing the risk of lung infection. | 15-Aug-24 | 
15 | 2315601310 | Study Discontinued | 20-Mar-24 | Malignancy(骨髓增殖性肿瘤-原发性血小板增多症) | Y | 24-Sep-24 | 
16 | 2315600201 | Study Discontinued | 28-Mar-24 | Acute ILD Exacerbation | N-His physical condition is very poor. He continues to take oxygen and cannot go out. His home and site are not in the same city. | 2-Jul-24 | 
17 | 2315606305 | Study Discontinued | 28-Mar-24 | Subject decision - The patient's dyspnea worsened, and the pain in his lower back was not relieved after being hospitalized. He started taking pirfenidone on his own from 20Mar2024. | Y | 22-Oct-24 | 

## Slide 19: Next wave: BI 1015550 (PDE4b inhibitor) SSc
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph2b-1305.40
Ph3-
1305.52
FSS
Jun2029
US NDA Sub
Oct 2029
US NDA appr.
AUG 2030
China
SSc Ph3
Ph3-1305.52
WRO: written response only
LSS: Last subject screening
LSC: Last subject complete
SQV: Site Qualification Visit
FDC: Fixed dose combination
COC: Certificate of Conformance
IMP: Investigational medicinal product
DBL: database lock
CTP： Clinical trial protocol
Jul
LSS
IA Sep 2025
Conquest
CTA Feb 2026
SSc Ph3
CTA Review + EC + HGRAC + 1st SIV (6 M)
Aug
China NDA Sub
Nov 2029
CN NDA appr.
Feb 2031
We are here
Mar Jun 2024
FSI moved from Mar to Jun 2024
Ph3 decision will be based on combined results from Conquest and PPF Ph3 results.
Notes: As mentioned, PPF approval best case could be moved up to Apr 2026. This will be our formal best case timeline for further communciaiton, if it’s endorsed by PEC today.
The CTP amendment 4.0 for fibroneer tirals （which removed IA for efficacy and added DBL2 4ms after DBL1 to collect longer term efficacy and safety data from patients on blinded treatment beyond 52 weeks ） were communicated with CDE through HAI on Nov 3.
IPF
Protocol amendment (ver4) for .14 on removing IA for efficacy and addition of DBL1 and DBL2 (similar to INBUILD). to be dispatched in Sep 2023. For .23, addition of DBL1 and DBL2 under discussion.
IPF last patient randomized 07Aug2023. 3% pts. Perm. Discontinuation.(as of aug 24) China ranked No. 4 patient randomization. IPF futility analyasis. DMC conclusion expected end of Aug 2023.
ILD trial: Base case 2m delay, best case 17d delay. China currently ranked No.2 in patients randomization. New projection of 1750 patients due to high screening failure rate
Fiboneer-on OLE CTP v1 finalized signed. FPI target in Sep2023

## Slide 20
Under Evaluation: Nerandomilast (PDE4b inhibitor) Connective Tissue Disease-associated Interstitial Lung Diseases (CTD-ILD)
2023 | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph3b-1305.46
Ph3b-1305.46
Recruitment window = 17-18 M
150 sites, N = 400
TDO: trial design outline
FSS: first subject screen
LSS: last subject screen
LPO: last patient out
We are here
LPO
Feb 2027
LSS
Jul 2026
FSS
Jan/Feb 2025
CTA Sub
Aug 2024
Final TDO
May 2024
CTR
Jul 2027
Draft TDO
Mar 2024
CTA Review + EC + HGRAC + 1st SIV (6 M)
Aug 2025
CTA Sub
FSS
Feb 2025
LSS
Jul 2026
LPO
Feb 2027
Country feasibility survey (6 sites) was completed on 12Apr2024.
China team aligned to propose at least 36 Chinese patients (16 sites) to join this study.
Final TDO will be ready on 09 May 2024.
Notes: Yixin’s email:
What is being asked?
You are asked to provide input using the Qualtrics survey with the aim to collate key insights from this expert outreach, which will be captured into INCAP CD&O and shared with the trial team to be taken into consideration during TDO finalization. Please note this exercise is separate from the Country Feasibility and Country Allocation Process (from Med Strategic Feasibility mailbox).

## Slide 21: China Sample size - preserve effect
    Power=80%; alpha=10% two-sided, Active:Placebo=1:1, 5% drop out
    N=400 (200 per arm), mean difference=-1.79%, sd=7%
China fraction/ Total pts number | 6.5%/ N=26 | 9%/ n=36 | 15%/ n=60 | 20%/ n=80 | 28%/ n=112
Method 1 Pr (ΔChina / ΔAll >0.5 ¦ Significance in entire population) | 65.32 | 66.61 | 72.43 | 76.01 | 80.04
Method 2 Pr (ΔChina < 0 & Δex-China < 0 ¦ Significance in entire population) | 77.55 | 80.71 | 87.93 | 91.30 | 94.29

## Slide 22
Under Evaluation: Nerandomilast (PDE4b inhibitor) Pediatric Fibrosing Interstitial Lung Diseases (ILD)
2024 |  |  |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 | 2031
Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 |  | 
Ph3-1305.22
Recruitment window = 30 M
N = 30
LPO
Sep 2028
LSS
Mar 2028
FSS
Sep 2025
Final TDO
Jan 2025
TBD
Ph3-1305.22
We are here
Business case: introduced at asset team China visit workshop .
Preliminary feasibility assessment :​
  Children ILD patients mostly in Children's hospital
  Beijing Children's Hospital : 5-10 children ILD patients/month from specialty outpatient clinic for pediatric ILD
TDO: trial design outline
FSS: first subject screen
LSS: last subject screen
LPO: last patient out
Notes: Director Cao Min from the Respiratory Department of Nanjing Gulou Hospital: Director Cao mentioned that in her work so far, she has only encountered 1-2 other doctors who have consulted on this type of disease. The patients with this condition are extremely rare. It may be worth checking with the Children's Hospital if they have any such patients.
Today, I contacted Director Zheng Yuejie from the Pediatric Respiratory Group at Shenzhen Children's Hospital. Director Zheng mentioned that they do not come across patients with this condition in their clinical practice, so it is not possible to conduct clinical trials.

## Slide 23
Consideration of China Joins Global Nerandomilast Pediatric Trial Business Case
chF-ILD China Patient Funnel (2030)
2-17 years old population1
219 Mn
Urban 2-17 years old population
155 Mn
Diagnosed Prevalence ch-ILD pts
586
Diagnosed Prevalence
chF-ILD pts
41
0.36/100,000 2,3
7% 4,5
~71% 1
Rate (2030 Est.)
chILD, Children Interstitial Lung Diseas; chF-ILD, Children Fibrosing Interstitial Lung Disease; Mn, Million; K EUR, 1,000 Euro; LOE, Loss Of Exclusivity; Est., Estimated; pts, patients.
1. World Bank; 2. Dinwiddie R, Sharief N, Crawford O. Idiopathic interstitial pneumonitis in children: a national survey in the United Kingdom and Ireland. Pediatr Pulmonol. 2002 Jul;34(1):23-9; 3.*Prevalence by country for 2025; estimated proportion of individuals that manifest the disorder/disease during 2025 chILD, childhood interstitial lung disease Boehringer Ingelheim. OFEV Pediatric Forecast; 4. Rice A et al. Histopathology 2013;63:743–55; 5. Nathan N et al. J Clin Med 2019;8:1312.
Chart: 
| 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
Pediatric | 13.0473 | 155.5263 | 225.0053 | 167.2878 | 165.612 | 159.8504 | 156.4093 | 151.3774
#REF! | 1
Unit: K Euro
Peak Year Assumption | Peak
Year | 2032
Eligible patient number | 39
Market share | 100%
Compliance rate | 82%
Net price (EUR/day) | 20.7
Net Revenue (K EUR) | 225
With potential LOE extension

## Slide 24: Ongoing: Nintedanib (TKI)1199-0434: Progressive Fibrosing Interstitial Lung Disease(PF-ILD)
We are here
2020 |  | 2021 |  | 2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  | 
H1 | H2 | H1 | H2 | H1 | H2 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
PF-ILD
PF-ILD NDA App
9 Mar 2020
NDA review
9 Dec 2019
NDA App
NDA Sub
15th Dec 2020
China
PF-ILD
1st SIV
LPO
PAC Study
25 Nov 2021
May
2024
DBL
CTR
Sep
2024
Jue
2024
LPR
9May2023
81 patients randomization, as of Apr 22nd
  46 completed treatment
  6 ongoing
  29 early treatment discontinued (36%)
Final DBL planned on Jun 24th.
CTR sub.
Sep
2024
Oct
2025
CDE
Feedback
Ph3b
1199-003

## Slide 25: Function update-Statistics and Programming
FVC change from baseline trend (with data cut off 18Apr2024)

## Slide 26: Ongoing: BI 1839100 (TRPA-1 antagonist): IPF/ PPF Cough
Pre-IND 3m for written response
2023 |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4
Ph2 IPF N=230 (IPF 180+50 PPF)
LSR
FSS
Ph3 in PF-ILD
Apr 2026
CTA sub
Jan 2026
FSS: First subject Screen
LSC: Last Subject complete
LSR: Last subject randomization
SQV: Site qualification visit
AEP: Asset evidence plan
HAI: Health authority interaction
Sep 2028
US NDA
Jan 2029
US Launch
Feb 2030
LSR-Key results*
Aug 2024
FSS
Key results
Sep
CTA Review + EC + HGRAC + 1st SIV (6m) *
Aug
Nov 2023
N = 14
Recruit. Window ~7m
LSR-Key results
Feb
LSR
1st SIV
CTA Review + EC + HGRAC + 1st SIV (6m)
Ph3 in PF-ILD
Jan 2026
Jul 2026
1st SIV
Key results
Sep 2028
CN NDA
Feb 2029
CN approval
2030
PoCP
Jul 2023
CTA sub
Feb 2024
6 Nov2023
PoCC
JP PK study
FSS
Jul 2023
Jan
2024
MRD
May
2023
Ph2-
1490-0004
Ph2-
1490-0004
Ph3-
1490-0004
Mar 2025
JP PK data
Mar
CTA approval expected in May. 1st EC approval from leading site: Mar 20. 1st SIV planned in Aug
IMP will be ready in depot on Aug 19. Short shelf life (expire on Nov 2nd) of 1st batch might potentially impact FSS in China for 1m.
We are here
Apr
Ph2 PPF cohort
Ph2 PPF cohort 4m
Mar
Jul
Oct

## Slide 27: 14 Sites are selected
类别 | 研究中心名称 | 主要研究者
组长单位 | 四川大学华西医院 | 罗凤鸣
参与单位 | 首都医科大学附属北京朝阳医院(北京朝阳医院 ) | 崔瑷
参与单位 | 天津医科大学总医院 | 曹洁
参与单位 | 中南大学湘雅二医院 | 彭红
参与单位 | 上海肺科医院 | 徐金富
参与单位 | 上海胸科医院 | 李锋
参与单位 | 安徽省立医院 | 徐晓玲
参与单位 | 徐州医科大学附属医院 | 陈碧
参与单位 | 杭州市第一人民医院 | 王利民
参与单位 | 四川省人民医院 | 郭璐
参与单位 | 广州医科大学附属第一医院 | 韩茜
参与单位 | 南京鼓楼医院 | 代静泓
参与单位 | 浙江大学附属邵逸夫医院 | 吴晓虹
参与单位 | 沈阳市胸科医院 | 王笑歌

## Slide 28: Ongoing: BI 1819479 (AutoTaxin inhi): IPF/ PPF
2023 |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4
Ph2 IPF (N=300)
LSR
FSS
Ph3 in IPF
Mar 2027
FSS: First subject Screen
LSC: Last Subject complete
LSR: Last subject randomization
Sep 2029
US NDA
Feb 2030
US app
Feb 2031
Jul 2024
FSS
LSC
Jun 2026
CTA Review + EC + HGRAC + 1st SIV (6m) *
Sep 2024
Recruitment window
~12m (Site: 15 N=18)
Mar 2024
LSR
1st SIV
Ph3 in PPF
CTA submitted on Mar 28 as planned, accepted on 11 Apr, target approval before 8 Jul 2024.
1st SIV planned in Sep.
CTA sub
Mar 2024
PoCP/PoCC in IPF
Aug 2026
Ph2-
1462-0004
Ph2-
1462-0004
Ph3
Oct 2025
LSC
RoFD
Jan 2027
Oct 2025
LSC
Jun 2026
Ph3
CN NDA
2030
CN app
2031
We are here
Ph3 in PPF
FSS
LSC
Ph3 in IPF

## Slide 29
2023 |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph2a/Ph2b
Ph1 SRD
China approval
Q4 2030
Ph3
Under Evaluation: BI 765432 IL-11 in IPF/PPF
We are here
US approval
Apr 2031
PoCP
HAI: Health authority interaction
US NDA
Apr 2030
Jun 2025
  HAI on PK strategy for joining global phase II study (1493-0002) submitted to CDE on 8 Feb 2024: vague feedback from CDE clinical dept. Final feedback back can be expected by mid of May.
Ph2
1493-0001
Ph3
Ph1 JP PK
Ph1 MRD
TBD
Q1 2028
Q4 2029
Oct 2027
Ph2a/Ph2b
Ph2
1493-0001
Ph3 TBD
Notes: SRD follow up period is ongoing. Asset team is planning to conduct HAI in focus regions to ask whether we could use the rodent species alon for chronic toxicology studies. The feedback expected by mid feb next year, to facilitate the future planning for toxicology studies. Submisison in China is planend on Nov 22.
To seek considerations from health authoroities.

## Slide 30
 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  | 2030 | 
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Airleaf Ph II 1397-0012
1397-0014 PhIII
Clairafly 1397-0013 CF Profiling study
China approval
2030 (TBC)
Under evaluation: BI1291583(Catc inhibitor): nCF Bronchiectasis
We are here
PhIII
US approval
Mar 2029
PoCP
PoCC
BTD: Breakthrough designation
PIP: Pediatric investigation plan, EoP2: End of Phase 2
*Based on “model based digital” PoCP
US NDA
Jul 2028
Nov 2023
Q4 2024
Apr
Feb 2028
LSC
Aug 2022
Jun 2024
Ph2-
1397-0012
Ph3
1397-0014
Ph2
1397-0013
RoFD
Dec 2024
Jan 2023
Sep 2023
LSS
EoP2 meeting request submission
Sep 2024
China team input to AEP, TDO and IAP ongoing. China site pre-feasibility ongoing to collect site comments on draft TDO.
China nominees for global site advisory board
  Yu Li, Shengjing hospital of China Medical University, has been confirmed and under contracting.
China local patient AB meeting was successfully held on 19th Apr 2024, as the 1st local patient AB meeting for clinical trial in China.
CTA
Jan 2025
AB: Advisory board
TDO: Trial Design Outline
AEP: Asset evidence plan
IAP: Integrated Asset Plan
CTA Review + EC + HGRAC + 1st SIV (6m) *
Jul
Jan 2025
1st SIV
China PK
CTA Review + EC + HGRAC + 1st SIV (6m) *
Jan 2025
Dec
LSC
PK results
May 2026
Protocol develop
Positive feedback from FDA on our proposal to include CF and non-CF Bronchiectasis patients in one phase III confirmatory study, Global will have further discussion on ‘One-BE’ strategy.
Notes: ANCA-AV: Anti-Neutrophil Cytoplasmic Antibody-Associated Vasculitis 抗中性粒细胞胞浆抗体相关性血管炎
HS: Hidradenitis Suppurativa
MASH:Metabolic deficiency Associated SteatoHepatitis 代谢缺乏相关脂肪性肝炎
CRS:Chronic RhinoSinositis 慢性鼻窦炎
NE: Neutrophil elastase中性粒细胞弹性蛋白酶

## Slide 31: Ongoing: Avenciguat (sGC Activator): Systemic Sclerosis (SSc)
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028 | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 |  | 
Ph2
1366-0031
Ph2
1366-0031
Ph3
Ph3
1366-0033
Ph3
1366-0033
Recruitment Window: TBD
Global
China
2029 Sep
FSS
China Ph2b CTA sub.-1st SIV (6M)
Ph2 1366.31 recruit. wind. ~22m
CN ML: 18 sites/25 patients; TW: 2 patients
CTA
Dec 2022
1st SIV
Apr 2025
LSS-Key results
2026 Sep
Jun 2022
We are here
sGC: soluble guanylate cyclase
LSS: Last subject screening
LSC: Last subject complete
SQV : site qualification visit
FSS: First subject screening
CN ML: China mainland
Launch
Feb 2031
NDA sub
Jan 2030
China NDA sub
Feb 2030
China NDA App
May 2031
Ph2 N=200
Dec 2022
LSS-key results
Oct 2024
Feb 2026
Decision: go/no go
early launch
Ph2 OLE
1366-0032
Ph2 OLE FSS-Key results
Nov 2025
Feb 2028
LSS
31 patients screened, 10 (+1) randomized in China. Global TOP 1 for recruitment.
HGRAC approval for CTP v4.0 on 19Apr2024.
IA 160 patient 24W
225 patients screened, 92 randomized globally as of 24Apr2024.
Notes: In case the results for the phase 2 study show compelling medical meaningfulness and statistical significance, early submission based on a single phase 2 study will be considered.
Lupus,

## Slide 32
Global enrollment (COD=23-Apr-2024)
Global | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24
Screening-p | 2 | 7 | 12 | 26 | 31 | 38 | 51 | 66 | 82 | 101 | 124 | 148 | 172 | 196 | 220 | 244 | 268 | 292 | 316 | 340 | 364 | 388 | 400 | 400
Screening-a | 2 | 7 | 12 | 26 | 31 | 38 | 52 | 68 | 86 | 102 | 115 | 144 | 151 | 180 | 193 | 203 | 225 |  |  |  |  |  |  | 
Enrollment-p | 0 | 2 | 6 | 9 | 11 | 13 | 14 | 17 | 21 | 27 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 158 | 172 | 186 | 200
Enrollment-a | 0 | 2 | 6 | 9 | 11 | 13 | 14 | 19 | 29 | 34 | 41 | 57 | 57 | 71 | 73 | 83 | 92 |  |  |  |  |  |  | 
Chart: 
| 44926 | 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626
Screening-p | 2 | 7 | 12 | 26 | 31 | 38 | 51 | 66 | 82 | 101 | 124 | 148 | 172 | 196 | 220 | 244 | 268 | 292 | 316 | 340 | 364 | 388 | 400 | 400
Screening-a | 2 | 7 | 12 | 26 | 31 | 38 | 52 | 68 | 86 | 102 | 115 | 144 | 151 | 180 | 197 | 203 | 225
Enrollement-p | 0 | 2 | 6 | 9 | 11 | 13 | 14 | 17 | 21 | 27 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 158 | 172 | 186 | 200
Enrollement-a | 0 | 2 | 6 | 9 | 11 | 13 | 14 | 19 | 29 | 34 | 41 | 57 | 57 | 71 | 75 | 83 | 92

## Slide 33
China Mainland enrollment (COD=23-Apr-2024)
China Mainland | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24
Screening-p | 0 | 0 | 1 | 3 | 5 | 8 | 10 | 13 | 14 | 15 | 17 | 19 | 23 | 25 | 26 | 29 | 32 | 35 | 38 | 41 | 44 | 47 | 50 | 50
Screening-a | 0 | 0 | 0 | 5 | 6 | 10 | 10 | 13 | 15 | 16 | 18 | 19 | 23 | 23 | 24 | 25 | 31 |  |  |  |  |  |  | 
Enrollment-p | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 20 | 21 | 22 | 24 | 25
Enrollment-a | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 7 | 7 | 9 | 9 | 9 | 10 |  |  |  |  |  |  | 
Pre-screening 1214 pts, 1149 pre-screening failure, 34 in follow up, 31 screened.
Chart: 
| 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597
Screening-p | 0 | 0 | 1 | 3 | 5 | 8 | 10 | 13 | 14 | 15 | 17 | 19 | 23 | 25 | 26 | 29 | 32 | 35 | 38 | 41 | 44 | 47 | 50 | 50
Screening-a | 0 | 0 | 0 | 5 | 6 | 10 | 10 | 13 | 15 | 16 | 18 | 19 | 23 | 23 | 25 | 25 | 31
Enrollement-p | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 20 | 21 | 22 | 24 | 25
Enrollement-a | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 4 | 5 | 7 | 7 | 9 | 9 | 9 | 10

## Slide 34: Mitigation Plan for patient recruitment in China
  Interim Investigator meeting (online) on 09May2024
  Patient engagement materials developed to distribute to investigators and SSc pts.
  Cross-functional boosting visits to non-performing sites (CDMA)
  Catchup weekly with recruitment vendor to identify more potential patients from patient organization.
  KL-6 assay ready in China for patient selection by Apr 2024, if timely delivery of kit reagents needed to assay validation to Teddy Labs in China.
  Public patient education short videos on multiple platforms, including patient communities

## Slide 35: Under Evaluation: BI 765250 PD-1 agonist in SSc
Ph1 SRD HV
JP Ph1
Placeholder
Ph1 MRD in Pso
1474.2
US Submission
2032 Jul
We are here
Ph2in SSc
2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 |  | 2033 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
SRD
MRD
Ph2 in SSc
PoCP
Nov 2024
Ph3 in SSc
Ph3 in SSc
JP Ph1
SSc
US launch
Aug2033
  PD-1 agonist elevated to TA priority asset.
  Scenarios for overall development plan and Ph2 dose finding strategy under evaluation. Will discuss with HPSC end of Apr.
  Asset team preliminary plan is to include China to ph2.
Ph2 in SSc
Ph3 TBD
Ph2in SSc
Ph3 in SSc
HAI: Health authority interaction
Development plan
To be updated
Notes: Peking Union Medical College Hospital, Shenzhen Children‘s Hospital, People's Liberation Army General Hospital (301 Hospital)
As mentioned, cGAS asset team has initiated the evaluation of China and Jp integration to inteferferonopathy program. China team had a cross functional evaluation. Based on literature research, we have identified at least 25 cases from 3 hospitals in China. Therefore we proposed to join global pivotal program starting from 2026, and non-IMP study and chart review study to be initiated next year，with the purpose is to gain knowledge on the natural course of the disease to inform trials and support future regulatory needs, and identification of patients for later interventional study.
Team will discuss with asset team end of Nov about the China integration proposal
Pediatric and adult patients with select type 1 monogenic interferonopathies, including and limited
to AGS, SAVI, FCL and COPA, with confirmed genetic mutation in the cGAS/STING pathway (

## Slide 36: PD-1 agonist：Integrated Development Plan
EoP2/pre-BLA interaction (depends on PhII results & HA feedback)
PhII in SSc (2 active doses)
Scenario 1:
D-F Phase 2 in PMR followed by Phase 3’s in PMR & GCA.
Registrational intent Phase 2 in SSc with potential for early BLA
MRD/PoCP in Psoriasis
PhII in PMR (3 active doses)
PhIII in PMR (1 active dose)
Q3/2033
PhIII in GCA (1 or 2 active dose)
TBD
Enables potential SSc launch in 2031 (fastest possible entry to market) + PMR launch in 2033
PhIII in SSc (1-2 active doses)
Q3/2033 to Q2/2034
Q2/2037 to Q2/2038
PhII in PMR (3 active doses)
PhIII in PMR (1 active dose)
Q3/2033
PhII or III in SSc (1-2 active doses)
Scenario 2:
D-F Phase 2 in PMR followed by Phase 3’s in PMR & GCA.
SSc development starts after positive PMR D-F results
MRD/PoCP in Psoriasis
PhIII in GCA (1 or 2 active dose)
TBD
PhIII in SSc (1-2 active doses)
Q1/2031
Gain confidence in Phase II PMR D-F before investing in other indications
Q1/2035
with 1 or 2 active dose groups
with 1 or 2 active dose groups
Registrational intent PhII study
SSc timelines are based on recruitment rates projected for currently ongoing studies (sGCa VitaliSSce, anifrolumab DAISY) whereas PMR timelines are based on recruitment rates achieved in a completed study (sarilumab PhIII Saphyr)
Polymyalgia rheumatica (PMR) & Giant cell arteritis (GCA)
风湿性多肌痛&巨细胞动脉炎
Notes: 1)

## Slide 37: Under Evaluation: BI3000202 (cGAS inh.) in Interferonopathy (干扰素病)
JP Ph1
Ph1 SRD HV
JP Ph1
Placeholder
Ph1 MRD HV
1509.2
Ph1c MTD
1509-0003
US Lunch
2033 Jun
We are here
Ph2in SSc
Chinese adult patient information (e.g. number and mutation) under collection, for feasibility evaluation of China joining global ph1c study. Will provide to asset team early May.
2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 |  | 2033 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
SRD
MRD
Ph2 in SSc
PoCP
Mar 2026
Ph3 in SSc
Jul 2026
Ph3 in SSc
Ph2/3 adult Neonates (staggered) N=~54
US launch
JuL 2031
Jan 2027
Jan 2029
INFopathy
Jan 2032
Ph2/3 in INFopathy
1509-0018
Jun 2030
Non-IMP low interventional study
Non IMP
1509-0019
Chart review
chart review
SSc
Interferonopathy
Jan 2025
Mar 2028
Dec 2028
Notes: Peking Union Medical College Hospital, Shenzhen Children‘s Hospital, People's Liberation Army General Hospital (301 Hospital)
As mentioned, cGAS asset team has initiated the evaluation of China and Jp integration to inteferferonopathy program. China team had a cross functional evaluation. Based on literature research, we have identified at least 25 cases from 3 hospitals in China. Therefore we proposed to join global pivotal program starting from 2026, and non-IMP study and chart review study to be initiated next year，with the purpose is to gain knowledge on the natural course of the disease to inform trials and support future regulatory needs, and identification of patients for later interventional study.
Team will discuss with asset team end of Nov about the China integration proposal
Pediatric and adult patients with select type 1 monogenic interferonopathies, including and limited
to AGS, SAVI, FCL and COPA, with confirmed genetic mutation in the cGAS/STING pathway (

## Slide 38: Ongoing: BI 706321 (RIPK2 inhibitor): Crohn’s Disease (CD)
2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
TNF failure (N=700)
Ph2a-
1425.3
N=50
Oct 2021
2024 Dec
LPO
FPI
Sep 2031
Ph3-
1425.5
LPO
FPI
Ph2b-
1425.4
Sep 2028
Aug 2025
LPO
FPI
NDA APP
Jul 2033
Ph3-
1425.6
TNF naïve & non-failure (N=700)
Ph2b-
1425.4
CN NDA App
2034
JP Ph1-
1425.8
FPI
PoCP
Aug 2024
Primary endpoint LPO
Jun 2024
Pre-IND
Aug
2021
Pan Asia PK
Feb 2022
Aug 2022
N=210
MR Sub
WR
Dec
2021
LPO
CTA submission for Ph2b moved from Sep 2024 to May 2025, to reduce early frontloading activities until the key results of the PoCP trial becomes available. (Jul-Aug 2024)
CTA sub
Sep 2024
May 2025
China Ph2 1425.4 recruitment wind. 17~20m
.
Chinese HV PK data available
CTA Review + EC + HGRAC + 1st SIV (6m)
China Ph2 1425.4 recruitment wind. ~20m
LSS-LSC
(# additional 1-3m might be needed for another round of EC review on PK data)
1
CDE accepts JP
PK data (Low POS)
2
Hold Chinese cohort
after Ph2b CTA feedback
(Agreed by asset team)
Sep 2028
LPO
LPR
Sep 2027
May 2025
Nov 2025
Jun 2028
CTA
sub
-app
Ph2 sites set up#
LSS-LSC
LPO
LPR
Chinese
part
TNF naïve & non-failure
Ph3-
1425.5
Ph3-
1425.6
TNF naïve & non-failure
CDE
feedback
Dec 2025
Dec 2025
Mar 2032
LPO
FPI
Jun 2028
We are here

## Slide 39: Under Evaluation: BI 3032950 (Anti-TREM1): Crohn’s Disease (CD)
JP Ph1/Pan Asia
Ph1 SRD-
1486.1
Oct 2022
JP Ph1
1486.4
Ph1 MRD-
1486.2
Ph2a in UC-
1486.5
US Lunch
2033 Aug
We are here
Ph2b
Therapeutic Area Management cost saving efforts for 2024 and 2025: Pan –Asian Ph1 study postponed to 2026.
Scenarios evaluation to allow Japan/China join global PhIIb to be discussed on Apr 25. China team proposal: to initiate Pan Asian PK or dedicated China PK study from the beginning of 2026
2022 |  | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 |  | 2031 |  | 2032 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
SRD
Sep 2023
MRD
May 2023
Jan 2024
Q4 2024
Ph2a in UC
PoCP
Jul 2026
Ph2b
Oct 2026
Nov 2029
Ph3
Jul 2029
Jul 2032
Ph3
China Ph2b CTA sub.-1st SIV (6M)
China Ph2b recruitment TBD
Ph3
Nov 2029
CN NDA App
2033 TBD
Ph2b
Ph3
Dec 2024
Aug 2028
JP cohort FPI
CN cohort
FPI
CN cohort
LPO
PK data (TBD)

## Slide 40: China joining TREM-1 Ph2b timeline
2025 |  |  |  | 2025 |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |  | 
5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Ph2b recruitment
FSS Oct 2026
CTA submission
Jun 2026
PK sample export (2m)+analysis 1m
+1m report
Chinese cohort initiation
Mar 2026
FSS
Jan 2026
China PK study
LSC
Jun 2025
Pan Asian PK
PK results
Aug 2026
LSR
Sep 2028
Pan Asian PK-Chinese cohort
LSC
Jul 2026
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 17m
FSS
Jan 2026
PK result
Oct 2026
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 15m
1st SIV
Mar 2027
Option 1: Pan Asian PK initiation in Jan 2026
Option 2: China PK study if JP PK is not needed based PMDA feedback (protocol development and CTA frontloaded)
CTA submission
Oct 2026
1st SIV
Feb 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Jun 2025
1st SIV
Dec 2025
China PK Protocol develop
kick off Feb 2025
PK sample export (2m)+analysis 1m+1m report
FSS
Nov 2026
China PK study
LSC
Apr 2027
PK result
Aug 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 5m
1st SIV
Feb 2028
Option 3: China PK study if JP PK is not needed based PMDA feedback (protocol development and CTA not frontloaded)
CTA submission
Aug 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
1st SIV
Oct 2025
Protocol development
China PK Protocol develop
kick off Jan 2026
CTA
Apr 2026
Most China sites have only 2m recruitment

## Slide 41: China PK Strategy Options
Option 1: Pan Asian PK study initiation from beginning of 2026
  Protocol and CTA needs to be frontloaded
Option 2: China PK study in China, JP PK is not needed based PMDA feedback (with China PK protocol and CTA frontloaded before 2026)
  Study Design: Single dose evaluation with healthy volunteers
    6 active + 2 placebo for each dose groups (total 8 x 3 = 24 subjects)
    i.v. 2 dose (2nd dose evaluation will be started one month later from 1st dose with safety monitoring)
    s.c. 1 dose (parallel with 1st i.v. dose)
    evaluation period for each cohort will be 4 months
Option 3: China PK study in China, JP PK is not needed based PMDA feedback (with China PK protocol kick off in 2026)
  Study Design: same as Option 2

## Slide 42: China joining TREM-1 Ph2b timeline (back up option 4)
2025 |  |  |  | 2025 |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  |  |  |  |  | 
5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Ph2b recruitment
FSS Oct 2026
CTA submission
Jun 2025
PK sample export (2m)+analysis 1m
Chinese cohort initiation
Mar 2026
FSS
Jan 2026
China PK study
LSC
Jun 2025
Pan Asian PK
PK results
Aug 2026
LSR
Sep 2028
Pan Asian PK-Chinese cohort
LSC
Jul 2026
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 17m
FSS
Jan 2026
PK result
Sep 2026
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 16m
1st SIV
Mar 2027
Option 1: Pan Asian PK initiation in Jan 2026
Option 2: China PK study if JP PK is not needed based PMDA feedback (protocol development and CTA frontloaded)
CTA submission
Sep 2026
1st SIV
Feb 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
CTA
Jun 2025
1st SIV
Dec 2025
China PK Protocol develop
kick off Feb 2025
PK sample export (2m)+analysis 1m+report 1m
FSS
Aug 2026
China PK study
LSC
Jan 2027
PK result
Apr 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
Ph2b recruitment window in China~ 8m
1st SIV
Nov 2027
Option 4: China PK study if JP PK is not needed based PMDA feedback (ONLY protocol development frontloaded)
CTA submission
May 2027
CTA Review + EC + HGRAC + 1st SIV (6m) *
1st SIV
Jul 2026
Protocol development
China PK Protocol develop
kick off Sep 2025
CTA
Jan 2026

## Slide 43: PDE4 PK study budget reference
Total budget 1,393,125 Euro
Before SIV, the payment was 436,580 Euro, around 31% of total budget.

## Slide 44: TREM-1 development Schedule and Option for JP
②Pan-Asian Ph1
(Japanese part)
①Consultation before Ph2a
Yes
Aug
2026
Jan
2026
Jun
2026
Feb 2025
Feb
2027
③Consultation
before Ph2b
Oct
2026
Yes
No
Try to recruit Asian patients
(living in U.S, European countries etc)
No
Jun
2027
Yes= acceptable to join gPh2 w/o J-Ph1 data
No=J-Ph1 data to be available before gPh2

## Slide 45: China PK Study Needs
PK data on Chinese population is considered pre-requisite to further join global MRCT study, based on industry intelligence.
  We learn from some industry intelligence that evaluation division of IBD in CDE require PK study in Chinese subjects prior to further trials in China. (5 companies got CDE reviewer's request to conduct China PK study ahead of join global Ph2 or Ph3. The requests seem neither related to study phase (ph2 or ph3), nor related to compound modality (small molecule or biologics), nor JP PK data availability.)
If Pan Asian PK study is not planned in JP, to ensure China can join global phase IIb study smoothly with enough recruitment window, a dedicated China PK study is necessary.

## Slide 46: Inflammation Product Overview
Substance/ MOA/Formulation | Indication | Study type/Global Status (Study no.: FPI-LPO, CTR) | China Dev. Strat. | Current Status | Next Mile-stone | Key Updates | 
China IPF Registry Study (PORTRAY) | IPF | IIS (1199-0302) (Jul2018-July2026,July2027) | China alone | Follow up | LPO： July 2026 | Completed recruitment in Apr 2023 Follow up ongoing | 
IPF SURVEY | IPF | ECR(1199-0562) (Sep2023-Jul2026) | China alone | EC approval | Contract effective(Jul2024) | Protocol approved 20Feb2024 EC approval 11Mar2024 Contract review process | 
Development and Validation of a Patient Reported Outcomes (PRO) Questionnaire of Patients with Pulmonary Fibrosis in China | IPF | ECR（2024-2025） | China alone | PEC endorsement | Proposal approval(Mar2024) | PEC endorsed this study in Dec 2023 Further revision on the proposal (including PI, timeline, etc.) ongoing. | 
A Prospective, Multi-Center Registry Study of Progressive Pulmonary Fibrosis (PPF) in China (PROFINA) | PPF | ECR (2023-2027) | China alone | PEC approval | Global endorse(Apr2024) | PEC approval obtained on 28Feb2024 Under hybrid review process | 

## Slide 47
Spesolimab Update

## Slide 48: Spevigo sNDA Roadmap – GPP flare prevention
Global
China
48
Nov
US Pre-submission Interaction
2022
2023
Feb 27
US BTD Submission
Feb 17
Pre-NDA Interaction Request
Feb 24
BTD Submission
May 11
sNDA Submission
May 25
Accepted by CDE
Feb 10
Global Top-line Results
Feb 13
Chinese Subgroup Top-line Results
Apr 19
BTD Granted
PR Applied
Apr 28
US BTD Granted
May 18
US sBLA Submission
May 18
US Priority Review Application
Globally first approval in China!
May 30
Pre-NDA Interaction
Feedback
Jun 29
PR Granted
Jul 24
FDA noticed standard review
2024
Mar 05
China Approval
Mar 18
US Approval

## Slide 49: Spevigo sNDA for GPP flare prevention in China – Best Case
NDA Submission 11 May 2023
May 2023
Jun 2023
Jul 2023
Aug 2023
Oct 2023
Nov 2023
Jan 2024
Feb 2024
Mar 2024
NDA Submission
CDE Technical Evaluation (1st round) May 2023 – Oct 2023
QC Testing Jul 2023 – Nov 2023
GCP Inspection Jul 2023 – Nov 2023
Registration Testing
Start 20 Jul 2023
GCP Inspection Notice
11 Jul 2023
Deficiency Letter
27 Oct 2023
Approval
05 Mar 2024
Inspection Report Transferred to CDE 08 Nov 2023
10 Months
Sept 2023
Dec 2023
Registration Testing Finish 07 Nov 2023
CDE Technical Evaluation (2nd round) Nov 2023 – Feb 2024
We are here
NMPA Review
Supplementary Submission
24 Nov 2023
PR Granted 29 Jun 2023
Panel meeting (Jan 19)
Labeling discussion (TC on Feb 02)
MTP,CNTS finalized
Approved indication 本品适用于减少12岁及以上青少年（体重≥40 kg）和成人的泛发性脓疱型银屑病（GPP）发作。

## Slide 50: Status in Other Regions
EMA D 120 LoQ response submitted 18 Jan, D 150 AR received on 27 Feb, Day 180 LoQ by mid Mar.
FDA action and approval of the Spevigo sBLA on Mar 18. The approved FDA indication from the US PI is “SPEVIGO is an interleukin-36 receptor antagonist indicated for the treatment of generalized pustular psoriasis (GPP) in adults and pediatric patients 12 years of age and older and weighing at least 40 kg”.
JP submission plans under discussion
Taiwan DL response due date Feb 26, approval is planned in JUL 2024
HK planned to submit on 1/15/2025 (best) or 4/15/2025 (base) , approval on 10/15/2025 or 4/15/2026

## Slide 51: Ongoing: BI 655130 (Anti-IL36R): General Pustular Psoriasis (GPP)
2020 |  | 2021 |  | 2022 |  | 2023 |  | 2023 |  | 2024 |  | 2024 |  | 2025 |  | 2023 |  | 2026 |  | 2024 |  | 2027 | 
Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4
FSS
N=130
May 2019
LSS
Feb 2023
LSC
Jan 2028
N=14
Sep 2020
1st SIV
Ph2 OLE-1368.25
Ph3 OLE-1368.25
Ph2b-1368.27
Ph2b-1368.27 (Effisayil 2)
LSS
Oct 2022
LSC
China ML N=18, TW N=4
CTA Review + EC + HGRAC + 1st SIV
Jan 2020
Oct 2020
1st SIV
CTA Sub
Aug 2021
FSS
Flare Prevention (N=123)
Jun 2020
LSR
Nov 2022
NDA Review
18May 2023 (US)
NDA Sub
NDA App
NDA Review
11 May 2023
NDA Sub
NDA App
5Mar 2024
Dec 2027
18Mar 2024
LSR
Ph3b/4-1368.120
LPO (CN)
Sep
LSC
Dec 2022
LPO (G)
We are here
NDA App (US)
for GPP Flare Sep 2022
Dec 2021
14m recruitment (N=40)
Oct 2023
FSS
LSS
Dec 2024
LSC
Apr 2027
~14m recruitment window
China Mainland: N=5 TW: N=2
16Oct2023
1st SIV
LSS
Dec 2024
LSC
Apr 2027
Ph4-1368.120
NDA App for GPP Flare
CN ML: 13Dec2022
TW: 6Jan2023
EC + HGRAC + 1st SIV
1368.120 (PAC)
7 patients screened, 4 randomized, 1 in screening. 1 early discontinued.
TW: 7 patients screened, 4 randomized.
IMP ordered for extra patients, arrived local depot on Apr15.
Jun 2023
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
CN ML: China mainland
TW: Taiwan
SF: Screen failure
1368.120 (PAC)
44 patients screened, 25 randomized, 15 in screeing as of 16Apr.
Global recruitment is speeding up. only to screen patient who are flaring.
1368.25 (OLE)
A CTP amendment under discussion: update the treatment duration to be such as ‘up to 5 years or until s.c. spesolimab is available in the market, whichever is shorter’
Notes: 1368-0025: concern that CDE required to complete the ongoing trial 1368-0025 and submit clinical trial report in the approval letter of initial NDA. If the trial duration is shortened (since sc would be available in China market soon) , it seems the trials is ‘not’ completed in this way and long term safety data cannot be collected as planned.
1368-0120:
15+ in screening waiting for flare.
HGRAC approval on 15 patients recruitment on 28Dec2023.

## Slide 52: 1368-0120-Global Recruitment Curve (as of 16Apr2024)
Total Screened = 44
Total Randomized = 25
Total in Screening = 15
Total Screen failure = 3
Treatment complete=4
Screen failure rate = 6%
Early discontinuation study =0

## Slide 53: 1368-0120-China Reruitment Curve (as of 15Apr2024)-No update
Total Screened = 7
Total Randomized = 4
Total in Screening = 1
Total Screen failure = 2
Screen failure rate = 28%
Early discontinuation treatment =1
Early discontinuation study= 0
China recrutiment source data |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Months | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24
Patients screened (planned) |  | 1 | 1 | 1 | 2 | 4 | 4 | 4 | 6 | 6 | 6 | 7 | 7 | 7 | 8
Patients screened (Actual) | 1 | 5 | 7 | 7 | 7 | 7 | 7 |  |  |  |  |  |  |  | 
Patients Enrolled/Randomized (Planned) |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5
Patients Enrolled/Randomized (Actual) |  | 1 | 2 | 3 | 4 | 4 | 4 |  |  |  |  |  |  |  | 
Screening Failure Rate |  |  | 14% |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 54: Ongoing: BI 655130 (Anti-IL36R): Hidradenitis suppurativa (HS)
 |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
FPI
Ph2b/3 Lunsayil-1 -
1368.98
Ph IIb part FSS-LSR
(N=200)
Apr 2023
We are here
IA @ week 16
Nov 2024
Ph III part (FSS-LSR)
~17m for recruitment
CTA
CTA Review + EC + HGRAC (6m)
1st SIV
ready
RoFD: Release of full development
HAI: Health authority interaction
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
EoP2: End of Phase 2
Feb2023
Aug2023
17 patients screened. 10 patients randomized (originally committed 8 patients, achieved 5 months ahead of the recruitment plan), 3 patients under screening​
China interim investigator meeting (experience/case sharing) successfully held on 22nd Apr 2024.
EoP2 HAI planned in Jan. 2025.
Sep 2024
Week 8 analysis
LSR-LSC
Ph3-
1368.0100
Sep 2025
Jun 2024
EoP2 Meeting US
Jan 2025
CTA
Jul 2025
Oct 2025
Apr 2027
LSR-LSC
Aug 2028
BLA submission
Apr 2028
sNDA approval
Apr 2029
Interim analysis
Dec 2027
Ph III part (FSS-LSR)
~17m for recruitment
LSR-LSC
Ph IIb (N=8)
LSR-LSC
CTA Amend+ EC + HGRAC (6m)
Ph III part (FSS-LSR)
~13m for recruitment
Mar 2026
LSR-LSC
CN sNDA approval
Jul 2029
CN sNDA sub
Apr 2028
Sep 2025
DMC review
Nov
21Dec 2023
248 patients screened, 164 patients randomized as of 24Apr.​
Ph2 recruitment timeline and key milestones updated with 3-month acceleration
EoP2 HAI planned in Jan. 2025. Detailed timeline and core BB including question list are under discussion
Ph2b/3 OLE-
1368.0130
Ph2b/3 OLE FSS-key results
Apr 2024
Jul 2029
1st SIV
Ph2b/3 Lunsayil-1 -
1368.98
Ph2b/3 OLE-
1368.0130
Ph2b/3 OLE FSS-key results
Jul 2029
TBD
CTA
Dec 2024
EoP2 Meeting Jan 2025
Notes: Milestone achieved 5 months ahead of the recruitment plan
Leading PI suggested to plan case sharing meeting with other sites to make sure all the efficacy assessment are consistent. The meeting scheduled on 22Apr2024 at 19:00
The drug stock is available for 12 cases. The third batch is expected to be in place in April.
SIV status: 8 sites initiated. 1 site plans to initiate on 18Mar2024. 1 site pending contract negotiate.
New shipment completed inbound on 26Feb2024.
HGARC: CTP 2.0 has fully completed filling on 29Feb2024.
End of Phase II HAI will be moved to Jan 2025 with BB ready in Dec 2024. Core BB drafting was kicked off in Feb and prosed question list is under discussion, China team can input anytime from now on.
H2H study in planning, planned early next year, to be updated.
The commitment was stated in a cover letter that treatment in the trial may only be started in China after at least one patient has received 1800mg dose for 4 weeks in the study and no serious safety observation is raised for ph2b part of 1368-0098
 OLE (1368-0130) for HS, as long as participate in 1368-0098, then will roll over to 1368-0130
 The final TDO will be ready on 28 Aug, there is ongoing discussion that will be self-administered treatment at home;
 Final protocol planned on 23 Oct; final CTA package planned on 27 Nov 23 with IMPD V4.0 (vs V3.0 for 1368-0098);
 CTA is needed in China, target submission in Dec, approval in Mar 2024;
 First site initiated 12-Apr 24.

## Slide 55: 1368-0098 HS Global recruitment information- 24Apr2024
 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24
Plan screen | 1 | 5 | 21 | 39 | 55 | 76 | 91 | 111 | 125 | 141 | 154 | 168 | 178 | 192 | 204 | 215 | 220 | 220
Actual screen | 2 | 7 | 15 | 34 | 67 | 79 | 107 | 116 | 148 | 177 | 184 | 216 | 248 |  |  |  |  | 
Plan randomization | 0 | 4 | 9 | 24 | 37 | 55 | 70 | 91 | 104 | 121 | 131 | 147 | 154 | 165 | 179 | 189 | 196 | 200
Actual randomization | 0 | 5 | 7 | 15 | 37 | 53 | 62 | 93 | 108 | 126 | 135 | 147 | 164 |  |  |  |  | 
Total Screened = 248
Total Randomized = 164
Total Screen failure = 63
Screen failure rate = 25%
Early discontinuation= 12% (21)

## Slide 56: 1368-0098 HS China recruitment information- 24Apr2024
 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24
Plan screen | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual screen | 1 | 6 | 6 | 10 | 17 |  |  |  |  | 
Plan randomization | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Actual randomization | 0 | 1 | 1 | 5 | 10 |  |  |  |  | 
Total Screened = 17
Total Randomized = 10
Total Screen failure = 2
Screen failure rate = 11.8%
Early discontinuation= 0%
Notes: 6 patients screened by Feb2024, 4 patients screen failure due to TB positive and pending re-screen after CTP 2.0 approval (HGRAC approved, EC approved in 2 sites)

## Slide 57: Ongoing: BI 655130 (Anti-IL36R): Netherton Syndrome (NS)
Cross-over and OLE
Cross-over and OLE
OLE: open label extension
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
Ph2/3- 1368.0104
Ph II/III N=39
Jun2023
sNDA submission
Sep 2025
7 patients screened, 6 randomized (~15% of entire population, original committed 3 patients), 1 discontinued (withdraw by subject), continue to enroll adolescents.
CTP amendment (a 2-year OLE added) submitted on Feb 24, target approval in May
FSS
LSS
Aug 2024
Recruitment Window: ~18m (N=3/39)
Ph2/3-
1368.0104
CN sNDA approv.
Best case: Jul 2026
Base case: Dec 2026
CTA
CTA Review + EC + HGRAC (6m)
1st SIV
Pre-IND
Dec 2024
China LSS
Sep 2025
CN sNDA sub.
Sep 2025
Dec 2022
Jun2022
19Jun 2023
FSS: First subject screening
LSR: Last subject randomization
LSC: Last subject complete
LSLV Primary End Point
LSS
Aug 2024
LSC
Jan 2028
LSC (G)
Oct
2028
LSC
(CN)
May2026
43 patients screened, 36 randomized as of Apr 15.
9 months acceleration. Last subject randomization by 09Sep2024.
No new screenings of adults. Only continue to enroll adolescents.
TLR is target in Feb 2025, BTD and pre-NDA HAI will be followed in Apr 2025.
Final decision on submission strategy: with w32 cutoff data submitted in Sep 2025, target approval in 2026
1368-0121 Natural course of disease
NIS- 1368.0121
Dec 2024
LSLV Primary End Point
* Different submission scenarios are still under discussion
US Approv.
Best case: Mar 2026
Base Case: Jul 2026
Readout Part 1
May 2024
Jan
2028
We are here
Notes: Planning Meeting B on May 2-3.
HGRAC amendment approved. (25 screening, 15 randomization)
China recruitment will end 3-month earlier to facilitate the sample (NAb) exportation. – still pending confirm with CTL

## Slide 58: Global Spesolimab NS – w32 submissions
 |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
 | USA (Priority review) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | USA (Standard review) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EU (Standard review) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Japan (Priority review 9m) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Japan (Standard review 12m) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | China (Priority review 10m) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | China (Standard review 15m) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2025
2026
Priority Application
Priority Designation
JNDA
JP Approval
“priority”
BLA
Approval best case
D90 safety update
Approval
Standard Designation
D120 safety update
MAA
Slot 15.10.25
(best case)
Approval base case
D 90 RSI
Clock stop
LSC w52 30.12.25
LSLV w52
JNDA
JP Approval
“standard”
Potential extension of review
LSLV w32– 21Apr
CO w32–20 Aug
CTR w32–28 Jul
Best case approcal
CDE sNDA
CN Approval
“priority”
CDE sNDA
CN Approval
“standard”
Dec 26
EU Rapp mtg
HAI placeholder
BTD request
HAI placeholder
HAI placeholder
DBL w16 – 27 Jan
TLR w16 – 17 Feb
CTR w52–18 May 26
Val rep – 30 Jun
BTD request

## Slide 59: Submission scenarios
Scenario 1
Week 16 data cut off
Scenario 2
Week 32 data cut off
Additional data available at w16 cut off:
W32 data from ~ 37 patients
W52 data from ~ 22 patients
W52 data from ~ 37 patients

## Slide 60: 1368-0104 Global recruitment curve (as of 15Apr2024)
Months | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25
Patients Enrolled/Randomized (Actual) |  | 1 | 1 | 3 | 7 | 10 | 14 | 15 | 20 | 29 | 36 | 36 |  |  |  |  |  |  |  |  |  |  |  |  | 
Patients Enrolled/Randomized (Planned) |  | 1 | 2 | 3 | 7 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 34 | 36 | 39
Patient Screened(Actual) |  | 1 | 2 | 6 | 12 | 16 | 18 | 22 | 27 | 42 | 42 | 43 |  |  |  |  |  |  |  |  |  |  |  |  | 
Patient Screened(Planned) | 2 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 22 | 25 | 28 | 31 | 34 | 37 | 40 | 43 | 46 | 48 | 50 | 52 | 54 | 55 | 55
Total Screened = 43
Total Randomized = 36
Total Screen failure = 10
Screen failure rate = 23.2%
Early discontinuation=0
As of 15Apr, the enrollment curve is not revised in CTMS

## Slide 61: 1368-0104 China recruitment curve (as of 15Apr2024)
Months | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24
Patients Enrolled/Randomized (Actual) |  |  | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 |  |  |  | 
Patients Enrolled/Randomized (Planned) |  |  |  | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 6 | 6 | 7
Patient Screened(Actual) |  | 1 | 2 | 4 | 5 | 5 | 5 | 6 | 7 | 7 | 7 |  |  |  | 
Patient Screened(Planned) |  | 1 | 1 | 2 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 7 | 8 | 8 | 
Total Screened = 7
Total Randomized = 6
Total Screen failure = 1
Screen failure rate = 14%
Early discontinuation=0
Original commitment 3 pts. achieved
China recruitment end date is under final confirmation with CTL

## Slide 62: Ongoing: BI 655130 (Anti-IL36R): Pyoderma Gangrenosum (PG)
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECR:1368.0134
ECR (FSS-LSC)
CTA
CTA Review + EC + HGRAC
1st SIV
Pre-IND
Meeting
request
Jan2024
ECR: External collaborative research
HAI: Health authority interaction
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
IA results
Ph3 Pivotal 1368-0140
FDA Meeting/WRO
Mar 2024
BLA submission
Apr 2027
US sNDA approval
Sep 2027
CN sNDA approval
Jul 2028
CN sNDA sub
Apr 2027
FSS-LSR
CTA
Q1 2024
1368-0140 recruit. window: ~8m
Ph3 Pivotal 1368-0140
Jul 2024
Feb2025
Oct 2026
Jul
Jan 2025
LSR-LSC
Oct 2025
LSR-LSC
US request for preliminary advice regarding Breakthrough Therapy Designation (PBTDAR) submitted 30 Nov – pending response
Target date for 'first patient randomized' was shifted from Nov2024 to 31Mar2025, due to a HPBU budget reduction target for 2024.
Pre-IND meeting request submission on Feb 1. Feedback from CDE clinical dept was received: most comments are general without additional actions; China team is requesting to add Chinse expert to global adjudication committee.
Feasibility Check for 16 sites completed,.
We are here
Timeline to be updated
Notes: 1.Our target date for 'first patient randomized' was shifted to 31Mar2025. Background: At the beginning of the year, the HPBU was given a budget reduction target for this year. As you can imagine, finding savings that can still be realized in the very year you are in, is not easy and limits one's options to delaying the start of activities rather than stopping ongoing ones. Thus, TA Infl Medicine leadership identified our PG program as one of the activities to propose for 2024 budget reductions. Our PG program featured a 2024 budget of 10.5 Mio€ . This was based on a PhII/III start mid-year, which we (optimistically) estimated when the 2024 budget was created. Shifting the FPR to the November date realized some savings, shifting it further to 31Mar2025 now realizes saving of ~9 Mio€. This was proposed to and endorsed by HPBU leadership - who in turn will present the overall budget adjustments to the board soon. Bottom line: This shift does not represent a loss of faith in or support of the PG program, but a reaction to the budget adjustments our most senior leadership deemed necessary to accommodate the business needs of the company.
2.Our target date for RoFD was shifted from April to June. Background: While preparing for the RoFD presentation in April, we realized that it would be prudent to shift this presentation to the next HPSC in order to fully incorporate Health Authority feedback and allow the overall presentation to be more thoroughly aligned cross-functionally. As the presentation itself is not on the critical path to our clinical trial, this shift did not change our overall timelines. It's of course unfortunate when deadline shift on rather short notice. The efforts put into this milestone will not be in vain but will still be part of the RoFD presentation and the PG program. The shift was pre-aligned with and endorsed by TA leadership.
16 sites contacted, 15 interested, 1 rejected. Pending for an on-site visit with Prof. Zheng Jie from Ruijin Hospital.
Regarding comments on Chinese adjudication committee, LPT propose to involve Chinese experts into the global adjudication committee instead of set up separate China adjudication committee in MRCT. Local evidence lead has engaged with global team on this topic before and LPT will discuss with global team on this further

## Slide 63: Ongoing: BI 655130 (Anti-IL36R): Pyoderma Gangrenosum (PG) - before update for reference
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ECR:1368.0134
ECR (FSS-LSC)
CTA
CTA Review + EC + HGRAC
1st SIV
Pre-IND
Meeting
request
Jan2024
ECR: External collaborative research
HAI: Health authority interaction
FSS: First subject screening
LSS: Last subject screening
LSC: Last subject complete
LSR: Last subject randomization
IA results
Ph3 Pivotal 1368-0140
FDA Meeting/WRO
Mar 2024
BLA submission
Mar 2027
US sNDA approval
Sep 2027
CN sNDA approval
Jul 2028
CN sNDA sub
Apr 2027
FSS-LSR
CTA
Q1 2024
1368-0140 recruit. window: ~8m
Ph3 Pivotal 1368-0140
Jul 2024
Oct 2024
Oct 2026
Jul
Jan 2025
LSR-LSC
Oct 2025
LSR-LSC
US request for preliminary advice regarding Breakthrough Therapy Designation (PBTDAR) submitted 30 Nov – pending response
Pre-IND meeting request submission on Feb 1.
Feasibility Check ongoing.
We are here

## Slide 64: Inflammation product Overview
Substance/ MOA/Formulation | Indication | Study type/Global Status (Study no.: FPI-LPO, CTR) | China Dev. Strat. | Current Status | Next Mile-stone | Key Updates | 
Spesolimab EAP | GPP | EAP(1368-0077) | Global | CTR | close | CTR is finalized on 27Mar 2024 China Investigator meeting planned on May10 2024. Site close out in process. | 
Experience of Adults with Generalized Pustular Psoriasis (GPP) or Palmoplantar Pustulosis (PPP) | GPP/PPP | NIS (1368-0058) | Global (Fully out- sourced) | DBL | CTR | Patent recruitment in China has ceased om 20 Dec2022 , final recruitment： GPP survey/interview : 9/5, PPP survey/interview:5/3 Interim analysis posted at 2023 WCD conference Follow up the CTR from global | 
SCRIPTOR Study- Retrospective Chart Review | GPP | NIS(1368-0085) | Global (Fully out- sourced) | SSU | FPI | Global HAMA decide to stop SCRIPTOR study in China, due to budget increase and timeline delay caused by data export restrictions from CAC (中国国家互联网信息办公室) With resolutions, China team will continue to seek the study restarts China legal team confirmed that the data export issue has been resolved. current timeline suggest that continue this study may be a better choice than a new study | 
Exploration of the pathogenesis of GPP and PV​ | GPP/PV​ | IIS(1368-0133) (Nov2023-Apr2024, Jun2024) | China alone​ | FSI | LSI | HGRAC online approval on Oct 30th, wet-ink obtained on Apr 9th Enrolment: GPP+PV: tissue 5/4; blood 4/4 GPP: tissue 2/4; blood 2/4 PV: tissue 4/4; blood 2/4 | 
Spesolimab​ | PG&HS&NS​ | ECR​ (2023-2027)​ | China alone​ | PEC endorse​ | Global endorse​ | PEC endorsed PG and HS at PEC of Dec 2023, PEC endorsement for NS is pending. Feasibility check completed, will submit for PEC endorsement in Apr2024 | 
CAC (the Cyberspace Administration of China)中国国家互联网信息办公室; PV: Psoriasis Vulgaris

## Slide 65: Back Up

## Slide 66: TRPA-1 Ph2 study design

## Slide 67: Mitigation status update of FVC data missing
No | Mitigation | Status
1 | Trial team to release the “Dear investigator letter” and newsletter to clarify the visit procedure requirement after treatment early discontinued. | Completed
2 | Refresh training for CRA, Investigators/CRC to highlight the importance of FVC data per visit. | Completed
3 | CTM track the treatment discontinued subjects with CRAs to follow up weekly | Tracker Completed
4 | Site staffs refresh training for AE management and encourage keeping subject treatment with closely follow up. | Completed
5 | On site visit by CD&O for high risk sites (5 sites identified and planned within one month) | Completed
6 | FVC test reimbursement /ICF update | Completed
7 | commercial drug donation for placebo group initiated | Ongoing (contract negotiation ongoing)
8 | Trial Team update the MQR Plan to include the monitoring of QTL*regarding FVC data in IQRMP and deliver the risk/issue to CTMs. | Completed
9 | CTL/TSTAT to set up the output for FVC data per visit monitoring and shared with team monthly. | Completed
10 | CTL/SML provide the analysis FVC data report for CRA team weekly and create the tracker with planned visit after treatment discontinued for CRA team closely follow up. | Completed
11 | CTL/SML update TLMM* to specific the monitoring details for treatment discontinued and highlight data entry timeline and pay more attention on data entry oversight. | Completed

## Slide 68: Early EOT pts update since last meeting (9 Oct 2023)
Subject Number | Update on 28Aug2023 | Update on 8 Oct 2023
1156031005 | 7.26患者自诉服用试验药胃不舒服（7.10）并伴有稀便，自行停药（7.15-8.1）， 8.2来院进行剂量调整访视（降低至100mg），大约8.5反馈胃还是不舒服伴有恶心和呕吐（8.2检查肝酶正常），患者自行停药至今，并表示想居家修养一些时间再到医院就诊。 8.21研究者表示将再次联系患者确认情况。 下次计划访视V7（2023-09-15），研究者和患者保持联系，请患者尽可能回院按照计划完成V7访视 | 于2023-09-12 完成EOT 访视，目前表示可回院进行后续随访
1156005015 | NA | 该受试者因居住地变更，离医院3小时车程，患者状态较差需随身携带制氧机； 无法回院进行常规随访和肺功能检查，于2023-09-15登记EOT
Below two new EOT subject status details
Subject 1156031004 who discontinued on 29 June 2023 potentially lost to follow up
No other potential early EOT pts by now