## Slide 1: Portfolio Executive Committee (PEC) Review Meeting Portfolio Overview Update - Oncology
Donglei Zhu and Nick Xue, post-PoCP assets
Meiruo Liu, early assets
25th Apr 2024, 20 min
CONFIDENTIAL and for INTERNAL use only!

## Slide 2
One Page Summary — Oncology
TAFD | Ongoing* |  | Endorsed | Under Evaluation | Next wave
Oncology | Brigimadlin (MDM2/p53) /DDLPS - Ph2/3 (.8, BL-1) |  | Brigimadlin (MDM2/p53)/ BTC – Ph3 (.20, BL-5) [global FPI TBD] | Brigimadlin (MDM2/p53)/ 2L NSCLC- Ph3 (.38, BL-7) [feasibility request received, global FPI in Jan 2025] | BI 1821736 (VSV-CD80-Fc) / HNSCC, Melanoma
 | Brigimadlin (MDM2/p53) /BTC & solid tumors -Ph2 (.11, BL-2) |  | Brigimadlin (MDM2/p53)/ DDLPS - China EAP [China FPI in Dec 2024] | Brigimadlin (MDM2/p53)/ rollover study –Ph2 (.32) [feasibility request received, global FPI in Dec 2024] | VSV-GP-GSDME-IL12 / TNBC SoD endorsed in Nov 2023 HPSC
 | Brigimadlin (MDM2/p53) + Ezabenlimab/ 2L STS- Ph3 (.6, BL-3) [global FPI in Jun 2024] |  | BI 765179 (CD137-FAP) / 1L HNSCC – Ph1b [global FPI in Aug 2024] | Brigimadlin (MDM2/p53)/ 1L GBM- Ph2 (.30, BL-6) [feasibliy request not received, global FPI in Jun 2025] | BI 3018078 [ATP 128] (Recombinant Vaccine) + BI 3024308 (VSV-GP-128) / CRC
 | Zongertinib (HER2 TKI) /2L NSCLC-Ph1b |  | BI 1831169 (VSV-GP) /SCLC –Ph1 China alone [CEC decision pending] | BI 764532 (DLL3/CD3) / 2L SCLC – Ph3 [global FPI in Feb 2025] | BI 3720589/BI 3720590 (Heterologous Prime & Boost Vaccine) / PDAC
 | Zongertinib (HER2 TKI) /1L NSCLC – Ph3 |  |  | BI 764532 (DLL3/CD3) / 1L epNEC – Ph3 [global FPI in Apr 2025] | BI 765883 (TRAILR2/CDH3) / 2L PDAC- Ph1b [global FPI in Jan 2026]
 | Zongertinib (HER2 TKI) / BC & GC – Ph1b/Ph2 [CTA approval on 19th Apr, global FPI in mid-Jun 2024] |  |  | BI 764532 (DLL3/CD3) / 1L SCLC – Ph3 [global FPI in Jun 2025] | BI 3810944 (ODC-IL12)/ melanoma- Ph1b [global FPI in Jul 2026]
 | Zongertinib (HER2 TKI) / solid tumors - Ph2 [CTA kick-off, global FPI in Oct 2024] |  |  | BI 764532 (DLL3/CD3) / LS- SCLC – Ph3 [global FPI in Q1 2025] | 
 | BI 764532 (DLL3/CD3) /SCLC, epNEC, LCNEC - Ph2 |  |  | BI 3706674 (GDP KRAS inh.) / GC, EC, GEJC – Ph1b [global FPI in Aug 2025] | 
 | BI 765049 (B7-H6 /CD3) / GC – Asian Ph1 |  |  | BI 770371 (SIRPa next gen.) /HNSCC –Ph2 [global FPI in May 2025] | 
 |  |  |  | BI 1831169 (VSV-GP) /HNSCC, Melanoma, PDAC, solid tumors – Ph1b expansion [global FPI in Nov 2024] | 
mBC: Metastatic Breast Cancer
mGC: Metastatic Gastric Cancer
GEJC: Gastroesophageal Junction Cancer
EC: Esophageal Cancer
NSCLC: Non-Small Cell Lung Cancer
SCLC: Small Cell Lung Cancer
epNEC: Extrapulmonary Neuroendocrine Carcinoma
LCNEC-Lung: Large Cell Neuroendocrine Carcinoma in Lung
On track
Global strategy uncertain
* Ongoing indicates the trial has kicked off the preparation activities for pre-IND or CTA
Zongertinib (HER2 TKI))
Brigimadlin (MDM2/P53)
DLL3/CD3
B7-H6/CD3
Oncology TA Priority
OneHP Priority
KISIMA-02

## Slide 3: Brigimadlin (BI 907828, MDM2/p53)

## Slide 4
Impact:
So far, there is no impact on trials’(including BL-1, BL2 and BL-3) timeline in China.

## Slide 7
Ongoing: Brigimadlin (MDM2/p53 antagonist): 1L Dedifferentiated Liposarcoma (DDLPS)
2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2
Ph2/3-1403. 8
Brightline-1
We are here
FPI
Apr 2022
Ph2/3, N=390, 1L DDLPS
CN Recruit. win: 9M
planned N=36 (Main. 25, TW 9, HK 2)
17 Nov 2022
CTA Review + EC + HGRAC + 1st SIV
28 Apr 2022
1st SIV
CTA Sub
LPI
Aug 2023
LPI
Aug 2023
Ph2/3-1403. 8
Brightline-1
Key results
Jun 2024
Key results
Jun 2024
Jun 2024
BTD sub.
Jun/Jul 2024
BTD sub./
Pre-NDA, PR sub.
Abbreviations FPI: first patient in
LPI: last patient in
BTD: breakthrough designation
PR: priority review
NDA sub.: new drug application submission
NDA app.: new drug application approval
Main.: China Mainland
EAP: early access program
Oct 2023
04Oct2024
NDA sub.
27Jan2025
NDA app.
04Nov2024
NDA sub.
04Nov2025
NDA app.
Type II on CMC; Type I on accelerated NDA
Apr 2024
Type II sub. on CMC
Upcoming milestones:
Data cutoff - mid Apr
iDBL - 28 May
Topline results (TLR) - 04 Jun
BTD sub. - 11 Jun
NDA sub. - 04 Oct
Upcoming milestones:
BTD sub. - end Jun, feedback early Aug
Pre-NDA/PR sub – end Jul, feedback end Oct
NDA sub – 04 Nov

## Slide 8
Ongoing: Brigimadlin(MDM2/P53): 2L Biliary Tract Carcinomas (BTC)
2022 |  | 2022 |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028 | 
 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2
Ph2-1403.11
Brightline-2
We are here
FPI
Dec 2022
Ph2, BTC Cohort 1 N=90, 2L BTC and other solid tumors
LPI
Nov 2024
IFA (30pts)
not pass
Nov 2023
Key result
Apr 2025
Jan 2026
NDA AA
Jul 2025
NDA sub
Apr 2024
IA (60+pts)
BTC recruitment pause (Cohort 1& 1-CN)
Very unlikely
Decision on Ph3 trial Brightline-5
Ph2-1403.11
Brightline-2,
Cohort 1-CN
Dec 2023
CTA Review + EC + HGRAC + 1st SIV
Jun 2023
1st SIV
on hold
To resume after CTP amendment
CTA Sub
CTA prep.
BTC Cohort 1-CN N=25
LPI
Apr 2025
DBL
Aug 2025
Nov 2026
NDA AA
Jan 2026
NDA sub
Very unlikely
Timing of amendment under further discussion
IA analysis in end Apr, CEC on 29 Apr, TALC on 14 May
China participation in non-BTC cohorts was rejected by global trial team, because the central biomarker testing lab in China is not set up for those indications
no update

## Slide 9
Endorsed: Brigimadlin (MDM2/p53 antagonist) + ezabenlimab (PD-1 Ab): 2L Soft Tissue Sarcoma (STS)
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Ph3-1403.6
Brightline-3
We are here
FPI
Aug 2024 ?
Ph3, N=263, 2L STS
LPI
Key results
Aug 2026
IFA with 3m enrollment hold
Dec 2025
Ph3-1403.6
Brightline-3
Mar 2027
NDA app.
Nov 2026
NDA sub.
Abbreviations AT: Asset Team
w/: with
FPI: first patient in
LPI: last patient in
IFA: Interim Futility Analysis
Sep 2023
FDA Type C meeting
pre-IND
CTA + EC + HGRAC
N=24 (may be adjusted)
Mar 2025
Jul 2024
1st SIV
CTA Sub
LPI
Key results
Sep 2026
Dec 2027
NDA app.
Dec 2026
NDA sub.
Apr 2024
Pre-IND Sub
Mar 2024
CTP v1 final
IFA with 3m enrollment hold
Dec 2025
CTA app.
Late Sep 2024
Global Eza
IMPD
Expected in early of Sep.
  TALC endorsed China participation on 27 Feb
  Pre-IND and CTA kick-off meeting with gAT of brigimadlin and ezabenlimab on 25 Mar
    Timeline has been confirmed with both global teams
    Pre-IND submitted on 15 Apr, written response expected on 2nd Aug(type II→type III)
    CTA submission planned on 27 Sep due to global Eza IMPD

## Slide 10: Questions to be discussed
Question to CDE: China plans to join the global pivotal Phase III study (1403-0006). Based on the global overall study design and available safety, efficacy data and PK data from Phase I studies, does the CDE agree that China can join the Phase III pivotal study directly?
Potential risk: safety run-in potentially requested by CDE, but all efforts will be made for mitigation.
Company position:
RP2D of combination, eza mono and brigimadlin mono has already been determined.
Data of combination, eza mono and brigimadlin mono from all available trials in East Asian will be leveraged to demo the sufficient safety data to waive safety run-in:
  No safety profile difference (Asian vs. non-Asian) observed, and no overlapping toxicities observed in combination so far.
  Sufficient on-market PD-1/L1 use experience in Chinese patients supports the general similar safety profile in the PD-1/L1 class, and current safety profile of ezabenlimab shows no difference based on over 1200 patient exposure.

## Slide 11: Preliminary timeline comparison with vs without safety run-in
 | Scenario 1: + pre-IND No safety run-in required | Scenario 2: + pre-IND safety run-in required
Pre-IND submission | Apr 2024 | Apr 2024
Pre-IND response | Jul 2024 | Jul 2024
Protocol Amendment | / | Oct 2024
CTA submission | Jul 2024* | Nov 2024
CTA approval | Oct 2024 | Feb 2025
fSIV | Jan 2025 | May 2025**
FPI | Feb 2025 | Jun 2025
Safety run-in completion*** | / | Dec 2025
LPI | Jun 2026 | Jun 2026
Recruitment window**** | 13 months | 3 months
Assumptions:
*timeline pending global team confirmation
**trial level EDC and vendor database update to accommodate safety run-in sample and data collection required and completed before fSIV
***safety run-in includes 2 dose levels and takes ~6 months. Data from patients enrolled in the safety run-in part cannot be used to support registration.
**** subtracted 3 months of enrollment hold due to IFA
Possibility not high but cannot be completely excluded; robust data package is important to support the request to waive safety run-in

## Slide 12: BI764532, DLL3/CD3 TcE

## Slide 13
2022 | 2023 |  |  | 2023 | 2024 |  |  | 2024 | 2025 |  |  | 2025 | 2026 |  | 2027 | 2026 | 2027 | 2027 | 2028
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1
We are here
Ongoing: BI764532 (DLL3/CD3): 3L+SCLC / 2L+ epNEC / 2L+ LCNEC
Phase 2, N=120, SCLC, epNEC, LCNEC-Lung
Ph2-1438.5
Dareon-5
Oct 2023
FPI
Ph2-1438.5
Dareon-5
Apr/Jun
IA1/IA2
Jun Mar 2024
LPI
Expansion, 2L LCNEC-Lung
Jan 2026
NDA sub
May 2026
NDA AA
Sep 2024
FPI
Aug 2025
Key results
CN recruit. win: 8-9M
N=18 (Mainland 12 + TW 6)
25th Sep 2023
CTA Review + EC + HGRAC + 1st SIV (6M)
27th Apr 2023
1st SIV
CTA Sub
CTA prep
5th Dec 2022
Kick-off
Expansion, N=50, 2L LCNEC-Lung
Feb 2026
NDA sub
Feb 2027
NDA app (AA)
Sep 2024
FPI
Aug 2025
Key results
Apr/Jun
IA1/IA2
Abbreviations FPI: first patient in
LPI: last patient in
IA: interim analysis
AA: accelerated approval
sub.: submission
AA.: accelerated approval
SOD: start of development
Expansion, 3L SCLC
Mar 2026
NDA sub
Jul 2026
NDA AA
Nov 2024
FPI
Expansion, 2L epNEC
May 2026
NDA sub
Sep 2026
NDA AA
Nov 2024
FPI
Expansion, 3L SCLC
Apr 2026
NDA sub
Apr 2027
NDA AA
Nov 2024
FPI
Expansion, 2L epNEC
Jun 2026
NDA sub
Jun 2027
NDA AA
Nov 2024
FPI
4-month shift
4-month shift
  1st IA data available 18 Apr.
  2nd IA: 31 May, FDA dose justification Aug 2024.
  Global is preparing 4 phase III trials (2L SCLC, 1L SCLC, 1L epNEC, LS-SCLC)
Sep 2025
Key results
Nov 2025
Key results
Jan 2026
Key results
CTP amendment v3 – substantial and Type II HAI
  CHN1 EC amendment submission/approval for CTP 3.0 planned in Mar / Apr 2024
  HGRAC amendment approval for CTP 3.0 planned in Jun/Jul 2024 → We will restart the enrollment per the decision from global team.​

## Slide 14: Zongertinib (BI 1810631, HER2 TKI)

## Slide 15
Beamion LUNG-1 (1479.1 ) | 1479.1 Beamion Lung 1 |  | 2022 |  | 2023 |  |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 
 |  |  | H1 | H2 | Q1 | Q2 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 
Global | Phase Ia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Phase Ib |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
China | Phase Ia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Phase Ib |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cohort 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Ongoing: Zongertinib (HER2 TKI): 2L and 1L Non Small Cell Lung Cancer (NSCLC)
Active brain lesions (N=30)
LPI: 29Dec’23
FPI: Mar’23
2L NSCLC (N=136 | 70 at 120 mg)
FA
IA1
IA2
1L NSCLC (N=70)
FPI: Sep’23
LPI: Aug’24
NDA AA
02Feb’25
14Apr’25
NDA sub.
04Oct’24
16Dec’24
TLR
05Jun’24
10Sep’24
Cohort 3 (N=3)
Cohort 4 (N=2)
Cohort 5 (N=3)
FPI: Mar’23
2L NSCLC (N= 33 | 18 at 120mg)
1L NSCLC (N=11)
NDA AA
Dec’25
Jan’26
NDA sub.
Dec‘24
Jan‘25
Ph1a Dose Escalation
SIV: Feb’22
CTA-EC-HGRAC-SIV (4m)
Sep’22 - Jan’23
HER2 ADC pretreated (N=30)
non-TKDm+ NSCLC (N=30)
FPI: 15Sep’23
For 2L registration
Exploratory
Ph1a Dose Escalation
LPI: Aug’24
today
FPI: Sep’23
FPI: Sep’23
FPI: 10Oct’23
LPI of 33 pts
8Dec’23
NDA sub.
22Mar‘25
NDA AA
21Jul’25
For 1L registration
IA3
NDA timeline shift for 2.5 months to ensure data package sufficiently mature
BTD will sub to FDA by end of Apr based on IA3 data (an option with a risk)
NDA timeline shift for 1 month to target within 1 month after US submission
  Sub: Jan 2025
  Approval: Jan 2026
HA interaction for SAT as pivotal trial in 2L and 1L is planned on 17 May,2024
BTD is planned on 31 May, 2024 based on IA3 data
2.5-month shift
Primary analysis
05Jun’24
1-month shift
Notes: LPT has communicated with Marketing and Access colleagues regarding the potential risks of Accelerated Approval strategy, including different scenarios. And suggest to give a heads-up about the potential risks to corresponding management team within China and Asset team as appropriate
LPT will further evaluate the impact to1L AA.

## Slide 16: Recruitment status of Beamion LUNG-1 as of 15 Apr 2024
 | Global Planed Total/120 mg | Global Actual Total/ 120mg | China Planed | China Actual Total/ 120mg | Comment | 
Cohort 01 : HER2 TKD mut+ non-squamous NSCLC previously treated | 136/70 | 132/75 | 30 | 33/18 | Global enrollment completion | 
Cohort 02 : HER2 TKD mut+ non-squamous NSCLC first-line treatment | 70 | 75/60 | 11 | 21/14 | China enrollment completion | 
Cohort 03 : non-TKD HER2 mut+ NSCLC and HER2 TKD mut+ squamous NSCLC previously treated | 30 | 18/13 | 3 (regardless of dose) | 3/1 | China target achieved | 
Cohort 04 : HER2 TKD mut+ NSCLC with active brain metastases | 30 | 25/24 | 2 (regardless of dose) | 3/3 | China target achieved | 
Cohort 05 : HER2 TKD mut+ non-squamous NSCLC previously treated with HER2 directed ADC | 30 | 38/30 | 3 | 5/4 | Global enrollment completion /China target achieved | 

## Slide 17: Zongertinib (HER2 TKI) 1479-0001: Recruitment Status as of 15Apr2024
Chart: 
| Australia | Austria | Belgium | China | France | Germany | Hong Kong | Israel | Italy | Japan | Netherlands | Portugal | Singapore | South Korea | Spain | Sweden | United Kingdom | United States
Plan | 1 | 0 | 1 | 30 | 12 | 8 | 1 | 1 | 1 | 18 | 20 | 1 | 2 | 15 | 11 | 1 | 1 | 7
Actual | 0 | 0 | 0 | 33 | 11 | 8 | 0 | 1 | 1 | 18 | 20 | 0 | 0 | 19 | 14 | 0 | 0 | 7
Cohort 1 OPU recruitment chart
Cohort 2 to 5 OPU recruitment chart
Chart: 
| Australia | Austria | Belgium | China | France | Germany | Hong Kong | Israel | Italy | Japan | Netherlands | Portugal | Singapore | South Korea | Spain | Sweden | United Kingdom | United States
cohort 2 | 0 | 0 | 1 | 21 | 5 | 5 | 2 | 2 | 0 | 9 | 10 | 0 | 1 | 0 | 5 | 0 | 5 | 9
cohort 3 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 5 | 0 | 0 | 1
cohort 4 | 2 | 0 | 0 | 3 | 4 | 1 | 1 | 0 | 0 | 1 | 4 | 0 | 1 | 4 | 2 | 0 | 0 | 2
cohort 5 | 1 | 0 | 0 | 5 | 6 | 3 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 8 | 3 | 1 | 0 | 7

## Slide 18: Ongoing: Zongertinib (HER2 TKI): 1L Non Small Cell Lung Cancer (NSCLC)
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028 |  | 2029 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2
Ph3-1479.8
Beamion LUNG-2
FPI
Ph3 Pivotal in 1L NSCLC (N=272)
Key results
Mar 2027
Feb 2024
Ph3 Pivotal in 1L NSCLC (CH 46: Mainland 34 + TW 7 + HK 5)
12 Mar 2024
Key results
Mar 2027
LPI
LPI
May/Jun 2026
CTA Review + EC + HGRAC + 1st SIV
30 Oct 2023
CTA-s
Pre-IND & CTA prep
(6M)
Apr2023
Pre-IND sub
1st SIV
May/Jun 2026
NDA app.
Mar 2028
NDA app.
Jun 2028
NDA sub.
Aug 2027
RoFD
Jul 2023
We are here
NDA sub.
Jul 2027
FPI achieved on 20 Mar 2024
3 sites initiated and 4 SIV planned in Apr
3 subjects were screened and randomized as of18-Apr-2024.
Ph3-1479.8
Beamion LUNG-2
Patient enrollment: 14 subjects screened, 10 subjects randomized as of 18 Apr 2024

## Slide 19
Site Enrollment Status
Chart: China Enrollment Plan
| 45352 | 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327
Patients Randomized Cumulative (Actual) | 1 | 3
Patients Randomized Cumulative (Planned) - Adjusted | 0 | 0 | 1 | 2 | 3 | 4 | 6 | 7 | 9 | 12 | 14 | 17 | 19 | 22 | 25 | 28 | 31 | 34
Patients Randomized Cumulative (Planned) - Original | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 14 | 15 | 17 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 28 | 29 | 30 | 31 | 32 | 33 | 34
As of 18 Apr 2024
Global: 14 subjects screened, 10 subjects randomized
China: 3 subjects were screened and randomized

## Slide 20: Endorsed: Zongertinib (HER2 TKI): Pan-tumor expansion (basket trial)
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 | 2031
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 |  | 
We are here
Ph2 - 1479.9
(Beamion PANTUMOR-1)
Global
China
Ph 2 (selected solid tumors; HER2 amp./mut.) N = up to 200 pts
FPI
Oct 2024
CTA-s
May‘24
1st key results for HER2 mut.
1st key results for HER2 amp.
LPI
Jun 2026
CTA Review + EC + HGRAC + 1st SIV (6m)
May 2024
CTA-s
1st SIV
Ph 2 (selected solid tumors; HER2 amp./mut.) N=10
Nov 2024
LPI
Jun 2026
SoD
Jul 2023
Ph2 - 1479.9
(Beamion PANTUMOR-1)
CTP final
Mar’24
CTP V1 finalized and released on 04Apr2024.
Global(US) CTA submission planned in May.
CTA submission is expected to be completed by the end of Apr 2024.
Sites selection has been finalized in China, totally 3 sites confirmed.

## Slide 21: Endorsed: Zongertinib (HER2 TKI): 1L/3L Breast Cancer and 2L Gastric Cancer
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028 |  | 2029 |  | 2030 | 2031
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | H1 | H2 | H1 | H2 |  | 
We are here
Ph1b/2 - 1479.12
Beamion BCGC-1
Global
China
Ph1b/Ph2 (BC & GC) – outsourced to IQVIA
N=234
FPI
Jun 2024
Ph3 (3L BC)
1479.16
Ph3 (1L BC)
1479.17
Ph3 (2L GC)
1479.13
Phase 3 (3L BC)
Phase 3 (1L BC)
Phase 3 (2L GC)
CTA Review + EC + HGRAC + 1st SIV
31 Jan 2024
CTA-s
1st SIV
Ph1b/Ph2 (BC & GC) – outsourced to IQVIA
N=67
Jul 2024
RoFD
(3L/1L BC)
Dec’26
RoFD
(2L GC)
Feb’27
Ph3 (BC,GC)
1479.13/16/17
Phase 3 trials (BC, GC)
FDA MR-s
04Aug’23
FDA WRO
02Oct’23
CTA-s
Jan 2024
NDA-a
2030
NDA-a
2034
NDA-a
2031
SoD
Jul 2023
Ph1b/2 - 1479.12
Beamion BCGC-1
Pre-IND not needed
CTA submission on 31 Jan and acceptance received on 05 Feb;
CTA was approved by CDE on 19th Apr 2024. (49 working days since acceptance)
5 China trial sites were selected , another 3 sites will be selected in due course.
Protocol version 2.0 was released in Mar.
Updated protocol (and US speicfic ICFs) submitted to the FDA on March 12, 2024.

## Slide 22: Early Assets
B7/H6-CD3 (BI 765049)
CD137/FAP (BI 765179)

## Slide 23
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 |  | 2028
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | 
Ph1-1454.1
Ph1 Dose escalation (Reg A & B)
28Dec2023
CTA Review + EC + HGRAC + 1st SIV
Site ready*
Join in 1454.4 Part II
21Aug2023
CTA-s
Ongoing: BI 765049 (B7/H6-CD3): Colorectal Cancer (CRC), Gastric Cancer (GC)
We are here
Ph1 Part I Mono dose escalation
(6 Dose Levels)
FPI
Ph1-
1454.4
(GC cancers)
Global
China
PoCP
Jun 2024
Sep2028
Ph2-1454.10
(3L CRC)
Ph2 Mono Dose Optimization in 3L CRC
(outsourced to Parexcel)
May2028
PoCP timeline shift from Jun2024 to Dec2024:
A temporary dose de-escalation resulting from two DLTs in the step-in dose resulting in 2-additional dose levels to the escalation (according to BLRM requirements) was necessary
Several patients needed to be replaced due to last moment screen fails or specific patients not being evaluable, extending the enrollment period
PoCP
Dec 2024
Ph1b Combo with eza (Reg C) &
Mono fixed dosing (Reg B) & Mono s.c. dosing (Reg D)
Postponed
FPI
Ph3-1454.7
(3L CRC)
Ph3 Mono Pivotal in 3L CRC
FPI
Postponed
Ph1 Part II Mono expansion
Ph1 Part III & IV Combo escalation & expansion (optional)
FPI
16Feb2024
Ph1 Part II Mono expansion
Nov2026
AA
NDA-a
AA
NDA-s
May2025
May2025
FPI
May2025
*site ready for CTP v3.0 except IMP & kit which will only be shipped when Part II initiates.
Abbreviations FPI: first patient in
PoCP: Proof of Clinical Principle
AA: Accelerated Approval
NDA-s: New Drug Application Submission
NDA-a: New Drug Application Approval
Asian Trial
LPI
Feb2025
LPI
Aug2025
LPI
Aug2025
LPI
May2026
China Status:
Global evidence team may consider to have China sites joining in 1454-0004 Part I escalation depending on the global enrollment speed (and China assay availability by then).
No Major Update

## Slide 24
CTA prep
Mar
2024
2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  | 2028 |  | 2029
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | H1 | H2 | H1 | H2 | 
Ph1-1463.1
Ph1a Escalation in mono (Arm A) & combo (Arm B) & BioD (Arm C) & PET (Arm D)
Join in 1463.1 Ib
Ongoing: BI 765179 (CD137/FAP): 1L R/M Head and Neck Squamous Cell Carcinoma (HNSCC)
Global
China
*This timeline exhibits the scenario where safety run-in is not required by HA.
We are here
FDA interaction
May
2024
Lean PoCP
CTP
amend
Jul
2024
FPI
Nov
2024
Ph1b Combo Dose Optimization
in 1L R/M HNSCC (N = 60)
CN Recruit. win: 10-11M
(6 patients with 4 sites)
Feb
2025
CTA Review + EC + HGRAC + 1st SIV
Aug
2024
1st SIV
CTA Sub
LPI
Jan
2026
May
2026
Ph2/3 Combo in 1L R/M HNSCC
BLA
sub.
Oct
2029
BLA
app.
Oct
2030
FPI
Oct
2026
PoCC-like PoCP
Ph2/3
(1L R/M HNSCC)
LPI
Jan
2026
May
2026
PoCC-like PoCP
BLA
sub.
Nov
2029
BLA
app.
Nov
2030
Global Status:
TALC endorsed biomarker-based Lean-PoCP criteria on 2024-04-02. HPSC planned in 2024Jun for formal endorsement.
No asset maximization planned for lean PoCP. mNSCLC may be considered as the 2nd indication in addition to HNSCC for further development. Updated strategy will be endorsed in June HPSC.
Abbreviations FPI: first patient in
PoCP: Proof of Clinical Principle
PoCC: Proof of Clinical Concept
AxMP: Auxiliary Medicinal Products
SQV: Site Qualification Visit
AA: Accelerated Approval
BLA: Biologics License Application
Sub.: submission
App.: approval
China Status:
CTA kick-off is planned at the week of 2024-05-06 targeting CTA submission by Aug 2024. The critical path is the amended CTP with Ib design planned on 2024-07-17 after FDA interaction.
Site feasibility training was completed on 2024-04-10; SQVs will be completed by end of May; 4 sites selection will be confirmed by end of Jun.
Follow up with global TMCP lead on assay transfer timeline.
May
2024

## Slide 25: ONIS & IIS

## Slide 26: Portfolio Overview TA Oncology- ONIS & IIS
Product | Indication | Study type (Study no.: FPI-LPO,CTR) | Next Mile-stone | China Dev. Strat. | Current status | Key Updates | 
Afatinib 30mg & 40mg | NSCLC | PMO-NISnd (1200-0318): May.2019-Dec.2023, Sep.2024 | CTR (Sep 2024) | China alone | DBL (10Apr2024) | FSI & FPI achieved on 20May2020; LPI achieved on 22Dec2021. 76 patients recruited from 10 initiated sites till end 2021 LPO on Dec22 2023 DBL on 10Apr 2024 CTR process SEAP 2.0 in BI review & approve process | 
Afatinib 30mg & 40mg | Non-SqCC NSCLC Neoadjuvant | IIS (1200-0328): Jul.2020 - May.2022(stage 1), Apr.2025 (stage 2), Sep.2025 | LPO (Apr 2025) | China alone | Follow up | Enrollment completion on 9Feb2022 ,total 47 patients enrolled primary endpoint (stage 1) results has reached: Abstract has oral presented at 59th STS done in Jan 2023，Report accepted by Nature communications on 26July2023. DIM report submitted successfully in Aug2023 Stage 2 follow up on track | 
Afatinib 40mg | Chordoma | IIS (1200-0329): Oct.2022 – Dec.2025, Mar2026 | LPI (Dec 2024) | China alone | Enrollment | Clinical trail agreement fully signed, SIV:30Sep2022（sample size: 20) Actual recruit/ Planned recruit: 9/20 (by 18Apr)​ FPI：26Oct2022 | 
Brigimadlin | DDLPS | ONISed (1403-0024） Mar.2024, Aug.2024 | Final Report (Aug 2024) | China alone | Data analysis | Summary approval: Jan 2023 Visited target PI on 15Feb 2023 Got formal EC approval letter in Nov 2023. SIV: 13Mar 2024 | 
Afatinib 40mg | SqCC | IIS (1200-0279): Feb.2019-Dec.2022, Sep.2023 | Close (Jul 2024) | China alone | CTR | Termination/waiting for final report Agreement is under site reviewing. Unilateral termination notice is in communication with legal. | 
Afatinib 40mg | NSCLC NRG1 ≥2nd line setting | IIS (1200-0332) Aug.2021– Apr.2024, Oct.2024 | Close (Dec 2024) | China alone | CTR | FPI achieved on 27th Sep(sample size: 15, Actual recruit:2) Termination/waiting for final report. | 
Notes: 目标： 主要目标 描述中国DDLPS患者的总生存期 次要目标 描述中国DDLPS患者的人口统计学和临床特征 描述中国DDLPS患者的治疗模式和结局 次要目标 描述中国DDLPS患者的直接医疗成本和医疗资源利用率
设计： 这项研究将是基于现有数据的非干预性研究。这是一项描述性的疾病流行病学研究，不涉及BI产品。

## Slide 27: Back-up

## Slide 28: 1403.8 (BL-1) Study design
HR<0.80
HR<0.55

## Slide 29: 1403.11 (BL-2) Study design
30pts, 12 wks, ORR>20%
90pts, 12 wks, p<2.5% ORR>23.3%
25pts, 12 wks
45 mg

## Slide 30: 1403.6 (BL-3 for STS) Study design
Estimated timeline: FPI Apr 2024 Jul 2025 Dec 2025 Feb 2026 Mar 2028
HR<0.85

## Slide 31: 1403.20 (BL-5) Study design

## Slide 32: Integrated Asset Plan - Asset View
PoS – Probability of Success, MaR – Money at Risk until RoFD, – First Approval
?
Notes: Mehdi
Total Dev costs – includes both medical and drug development costs

## Slide 33: 1438.5 Study design
IA1: 6-wk FU Apr 2024
IA2: 12-wk FU May/Jun 2024
IA3: 12-wk FU Nov 2024