## Slide 1: Portfolio Executive Committee (PEC) Review Meeting Metalyse & Actilyse Overview
  Jiaqi Lu, Leo Bao | 22nd Apr, 2024 | 15 min

## Slide 2
China BLA Overview
Metalyse TNK-tPA — Acute Ischemic Stroke (AIS)
2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4
today
BLA process
BLA-app
31Mar2025
BLA-sub
28Dec
DL response
Dec
DL
Nov
Inspection:
Notification
13Mar
Inspection:
On-site May
Inspection:
CFDI conclusion Jul
Inspection:
Report to CDE
Sep
GCP Inspection
Samples: Ready
Mar
Online sub: NIFDC
Apr
NIFDC: Conduct test
90 WDs
QC-testing: Report to CDE
Oct
QC testing
Samples: Sub
End of Apr
BLA Review Process
BLA-acc
22Jan
sub: submission
acc: acceptance
app: approval
DL: Deficiency Letter
acc→DL: 200WD
Global
China
EMA BLA-sub
24Jul
Pre-BLA CMC
Sub
11Sep
11Oct
Feedback
EMA BLA-app
12Jan
Local Repack
Apr 2025
CDE review status:
Currently under review, expect to receive CDE questions starting from Jul-Aug 2024.
New CCDS expected to be ready in Aug 2024, with company position on low body weight limitation and etc.
Team will discuss if can take DL response chance to submit the new analysis data.

## Slide 3: Lytics AT CN Visit - successful global visit and productive exchange meeting with great teamwork
Date: Mar 25th – 28th , 2024
Highlight activities:
  Evidence/Value/Drug Device extensive exchange
  Metalyse LRR preparation
  Corporate Senior Management exchange
  Metalyse IAP co-creation
  KEE Visits

## Slide 4: Meet with Bijoy and Craig on ACT-Global
Way of collaboration with Tiantan
Definition of Co –leading
Further clarify the steering committee mechanism to Prof Wang
Tiantan’s expectation for ACT-GLOBAL
Ø BP domain, thrombolysis domain and SAH domain
Ø Prof. Bijoy Menon and Prof. Wang as Co-PIs for
Thrombolysis Domain
Ø First trial: Low dose TNK for patients with NOAC

## Slide 5: Global visit follow up action summary
Highlights for Metalyse Evidence:
CCDS update – keep close working together with global team
Maximization –
  Aligned Corporate to lead the late time window study as a MRCT.
  Aligned China to join in the "ETERNAL" trial

## Slide 6
2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
Metalyse- BI
Notes:
LPO – BLA submission for all local products: 3M (without pre-BLA meeting).
Metalyse & Fenghua: Metalyse uses the best case scenario. BLA approval is assumed by using NME & non-priority review pathway timeline (15m).
Local rPA-Crbiopharm & Pro-Urokinase: BLA approval is assumed by using indication extension CDE review timeline (12m).
BLA-s
(28 Dec’23)
Ph III, 1478 pts, 50 site, FPI-LPO: 14 Jul 2021 – 08 Oct 2023
BLA-a
(Mar’25)
Metalyse TNK-tPA & Local Competitors Development Timeline (as of 16Apr2024, Best case)
Local TNK- Fenghua
BLA-a & Launch*
(TBD)
Ph III, 1630 pts, 60 sites,
FPI-LPO: 26 Oct 2022 – Dec 2023
BLA-s
(TBD)
Pro-Urokinase – Tasly
BLA-s
(Jun’24)
Ph III, 1552 pts, 72 sites,
FPI-LPO: 29Jan2023 – Mar 2024
BLA-a & Launch
(Jun’25)
Local TNK- CSPC
Ph III, 1430 pts, 66 sites,
FPI-LPO: 12Jun2021 – 29May2022
BLA-s
(16Nov’22)
today
Launch
(Jul’25)
Fenghua | 2023 |  |  |  | 2022 | 
 | Sep 29 (LPI) | May 08 | Mar 07 | Feb 14 | Dec 08 | Oct 26
Recruited pts | 1630 | 1066 | 594 | 456 | 111 | FPI
LPI 1552 pts recruited by 03Dec2023
BLA-a & Launch
(30 Jan’24)
Local rPA – Crbiopharm
BLA-s
(05Feb’24)
Ph III, 1412 pts, 93 sites,
FPI-LPO: 21 Mar 2022 – Jun 2023
BLA-a & Launch
(Feb’25)
Reteplase | 2023 | 2023 | 2022 | 2022 | 
status | 30 | 05 | 06 | 25 | 21
 | Mar | Jan | Dec | Oct | Mar
Recruited pts | LPI | 1377 | ~1340 | 1300+ | FPI
Fenghua re-submitted the BLA for STEMI indication in Aug 2023, which may impact the review timing for AIS as 2nd indication. Currently the BLA review is pending.
Fenghua AIS is under DBL progress but may face the financial crisis, so the BLA submission timeline is TBD.
BLA-a for STEMI
(Aug’24)

## Slide 7: Actilyse Progress

## Slide 8
8
Actilyse contraindication (＞80yrs) removal overall regulatory strategy
2023 |  |  |  | 2024 |  | 2025 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Global
China
CN Variation (200WDs)
Variation sub:
18th Aug. 2023
Variation App.
Restrictions on >80 y was removed in label by EU since Jun 2018.
today
Feedback from CDE on 19 Apr.2024 :
Acknowledge the significant unmet treatment needs in elderly (> 80ys) pts in China;
The local study (0135-0349) showed numerically higher one-year all-cause mortality (39.5% vs 38.8%) and in-hospital any intracranial haemorrhage (13.7% vs 10.8%) in Actilyse group which is hard to provide strong justifications for safety consideration；
Suggest Sponsor to withdraw the current application AND re-submit it following the route of “境外已上市境内未上市药品临床技术要求“, with the content mainly based on global data and supplemented by Chinese data；
China
CN Variation (80WDs)1
Re-sub:
Early Jun. 2024
Variation App.
Aug. 2024 (if no formal queries)
Best case2：Oct. 2024
No GCP inspection is expected.
Best case: If no formal deficiency letter issued, no panel meeting or CDE internal meetings required, approval is expected in Oct 2024.
Withdraw
Apr 24th
Original Plan
Current Plan

## Slide 9
Actilyse resubmission clinical overview 2.0 timeline (BACKUP)

## Slide 10
Thank You !

## Slide 11
2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  | 2027 | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 Q2 | Q3 Q4 | Q1 Q2 | Q3 Q4
Metalyse- BI
BLA-s
(28 Dec’23)
BLA-a
(Mar’25)
Fenghua TNK Current Status
Local TNK- Fenghua
-AIS
BLA-a & Launch*
(Jul’25)
BLA-s
(Apr’24)
Launch
(Jul’25)
Local TNK- Fenghua
-STEMI
According to intelligence, 1st STEMI BLA was rejected due to unsuccessful GMP inspection and Covid-19 impact.
BLA-Rejection
(Oct’21)
BLA-sub
(Feb’18)
BLA-a-base
(Nov’24)
BLA-resub
(Aug’23)
BLA-a-best
(Aug’24)
Current Status:
CDE Clinical review finished on 2024-3-16, which took 140wds. Other departs review are not yet finished. Resub with same data package may be the cause for faster CDE review.
Best case assumption:
  140-160WD for other CDE departs review
  DL response timeline unchanged
  Inspection is not speeding limiting step
today